## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Project Kickoff | 1 day | Mon 7/01/24 | Mon 7/01/24 |  | 1
2 | Yes | Auto Scheduled | Phase 1 | 251 days | Tue 7/02/24 | Tue 6/17/25 | 1 | 1
3 | Yes | Auto Scheduled | Requirements Discovery | 25 days | Tue 7/02/24 | Mon 8/05/24 |  | 2
4 | Yes | Auto Scheduled | Review Project Scope | 5 days | Tue 7/02/24 | Mon 7/08/24 | 1 | 3
5 | Yes | Auto Scheduled | Define System Architecture and Hardware Requirements | 5 days | Tue 7/09/24 | Mon 7/15/24 | 4 | 3
6 | Yes | Auto Scheduled | Identify Functional Requirements | 5 days | Tue 7/16/24 | Mon 7/22/24 | 5 | 3
7 | Yes | Auto Scheduled | Identify All Data Sources | 5 days | Tue 7/23/24 | Mon 7/29/24 | 6 | 3
8 | Yes | Auto Scheduled | Define Project, Resource, Communication Plan | 5 days | Tue 7/30/24 | Mon 8/05/24 | 7 | 3
9 | Yes | Auto Scheduled | Environment Setup | 52 days | Tue 7/16/24 | Wed 9/25/24 |  | 2
10 | Yes | Auto Scheduled | Setup Dev Environment | 12 days | Tue 7/16/24 | Wed 7/31/24 |  | 3
11 | Yes | Auto Scheduled | Provision Hardware | 5 days | Tue 7/16/24 | Mon 7/22/24 | 5 | 4
12 | Yes | Auto Scheduled | Install and Configure Application | 5 days | Tue 7/23/24 | Mon 7/29/24 | 11 | 4
13 | Yes | Auto Scheduled | Test | 2 days | Tue 7/30/24 | Wed 7/31/24 | 12 | 4
14 | Yes | Auto Scheduled | Setup Test Environment | 12 days | Tue 7/16/24 | Wed 7/31/24 |  | 3
15 | Yes | Auto Scheduled | Provision Hardware | 5 days | Tue 7/16/24 | Mon 7/22/24 | 5 | 4
16 | Yes | Auto Scheduled | Install and Configure Application | 5 days | Tue 7/23/24 | Mon 7/29/24 | 15 | 4
17 | Yes | Auto Scheduled | Test | 2 days | Tue 7/30/24 | Wed 7/31/24 | 16 | 4
18 | Yes | Auto Scheduled | Setup UAT Environment | 20 days | Thu 8/01/24 | Wed 8/28/24 |  | 3
19 | Yes | Auto Scheduled | Provision Hardware | 5 days | Thu 8/01/24 | Wed 8/07/24 | 10 | 4
20 | Yes | Auto Scheduled | Install and Configure Application | 10 days | Thu 8/08/24 | Wed 8/21/24 | 19 | 4
21 | Yes | Auto Scheduled | Test | 5 days | Thu 8/22/24 | Wed 8/28/24 | 20 | 4
22 | Yes | Auto Scheduled | Setup Production Environment | 20 days | Thu 8/29/24 | Wed 9/25/24 |  | 3
23 | Yes | Auto Scheduled | Provision Hardware | 5 days | Thu 8/29/24 | Wed 9/04/24 | 18 | 4
24 | Yes | Auto Scheduled | Install and Configure Application | 10 days | Thu 9/05/24 | Wed 9/18/24 | 23 | 4
25 | Yes | Auto Scheduled | Test | 5 days | Thu 9/19/24 | Wed 9/25/24 | 24 | 4
26 | Yes | Auto Scheduled | Integration | 177 days | Tue 8/06/24 | Wed 4/09/25 |  | 2
27 | Yes | Auto Scheduled | Interface Specification & Configuration | 26 days | Tue 8/06/24 | Tue 9/10/24 |  | 3
28 | Yes | Auto Scheduled | Review existing interface standard | 5 days | Tue 8/06/24 | Mon 8/12/24 | 3 | 4
29 | Yes | Auto Scheduled | Develop new interface specifications (ADT & ELR) | 10 days | Tue 8/13/24 | Mon 8/26/24 | 28 | 4
30 | Yes | Auto Scheduled | Undertake document review with client | 5 days | Tue 8/27/24 | Mon 9/02/24 | 29 | 4
31 | Yes | Auto Scheduled | Publish new specifications | 1 day | Tue 9/03/24 | Tue 9/03/24 | 30 | 4
32 | Yes | Auto Scheduled | Configure base ADT interface in all environments | 5 days | Wed 9/04/24 | Tue 9/10/24 | 31 | 4
33 | Yes | Auto Scheduled | Configure base ELR interface in all environments | 5 days | Wed 9/04/24 | Tue 9/10/24 | 31 | 4
34 | Yes | Auto Scheduled | Inbound Interfaces | 146 days | Tue 8/06/24 | Tue 2/25/25 |  | 3
35 | Yes | Auto Scheduled | ADT Interfaces | 146 days | Tue 8/06/24 | Tue 2/25/25 |  | 4
36 | Yes | Auto Scheduled | Start Integration | 0 days | Tue 9/10/24 | Tue 9/10/24 | 32 | 5
37 | Yes | Auto Scheduled | Per Data Source (repeats 52 times) | 36 days | Tue 8/06/24 | Tue 9/24/24 |  | 5
38 | Yes | Auto Scheduled | Integration Kickoff Meeting With DSP | 1 day | Tue 8/06/24 | Tue 8/06/24 | 3 | 6
39 | Yes | Auto Scheduled | Assess Integration Readiness | 3 days | Wed 8/07/24 | Fri 8/09/24 | 38 | 6
40 | Yes | Auto Scheduled | Build / Unit Test Interfaces | 20 days | Mon 8/12/24 | Fri 9/06/24 | 39 | 6
41 | Yes | Auto Scheduled | Perform Integrated Testing With Data Source | 10 days | Mon 9/09/24 | Fri 9/20/24 | 40 | 6
42 | Yes | Auto Scheduled | Data Source Readiness Sign-off | 2 days | Mon 9/23/24 | Tue 9/24/24 | 41 | 6
43 | Yes | Auto Scheduled | Data Source Integration Complete | 0 days | Tue 9/24/24 | Tue 9/24/24 | 42 | 6
44 | Yes | Auto Scheduled | End Integration | 0 days | Tue 2/25/25 | Tue 2/25/25 | 36FF+120 days | 5
45 | Yes | Auto Scheduled | ELR Interfaces | 146 days | Tue 8/06/24 | Tue 2/25/25 |  | 4
46 | Yes | Auto Scheduled | Start Integration | 0 days | Tue 9/10/24 | Tue 9/10/24 | 33 | 5
47 | Yes | Auto Scheduled | Per Data Source (repeats 59 times) | 36 days | Tue 8/06/24 | Tue 9/24/24 |  | 5
48 | Yes | Auto Scheduled | Integration Kickoff Meeting With DSP | 1 day | Tue 8/06/24 | Tue 8/06/24 | 3 | 6
49 | Yes | Auto Scheduled | Assess Integration Readiness | 3 days | Wed 8/07/24 | Fri 8/09/24 | 48 | 6
50 | Yes | Auto Scheduled | Build / Unit Test Interfaces | 20 days | Mon 8/12/24 | Fri 9/06/24 | 49 | 6
51 | Yes | Auto Scheduled | Perform Integrated Testing With Data Source | 10 days | Mon 9/09/24 | Fri 9/20/24 | 50 | 6
52 | Yes | Auto Scheduled | Data Source Readiness Sign-off | 2 days | Mon 9/23/24 | Tue 9/24/24 | 51 | 6
53 | Yes | Auto Scheduled | Data Source Integration Complete | 0 days | Tue 9/24/24 | Tue 9/24/24 | 52 | 6
54 | Yes | Auto Scheduled | End ELR Integration | 44 days | Thu 12/26/24 | Tue 2/25/25 | 46FF+120 days | 5
55 | Yes | Auto Scheduled | Outbound Interfaces | 31 days | Tue 2/25/25 | Wed 4/09/25 |  | 3
56 | Yes | Auto Scheduled | Public Health Reporting - ELR Interfaces | 31 days | Tue 2/25/25 | Wed 4/09/25 |  | 4
57 | Yes | Auto Scheduled | Start Integration | 0 days | Tue 2/25/25 | Tue 2/25/25 | 45 | 5
58 | Yes | Auto Scheduled | COVID-19 Registry | 31 days | Wed 2/26/25 | Wed 4/09/25 |  | 5
59 | Yes | Auto Scheduled | Integration Kickoff Meeting With DSP | 1 day | Wed 2/26/25 | Wed 2/26/25 | 57 | 6
60 | Yes | Auto Scheduled | Assess Integration Readiness | 3 days | Thu 2/27/25 | Mon 3/03/25 | 59 | 6
61 | Yes | Auto Scheduled | Build / Unit Test Interfaces | 20 days | Tue 3/04/25 | Mon 3/31/25 | 60 | 6
62 | Yes | Auto Scheduled | Perform Integrated Testing With Data Source | 5 days | Tue 4/01/25 | Mon 4/07/25 | 61 | 6
63 | Yes | Auto Scheduled | Data Source Readiness Sign-off | 2 days | Tue 4/08/25 | Wed 4/09/25 | 62 | 6
64 | Yes | Auto Scheduled | Data Source Integration Complete | 0 days | Wed 4/09/25 | Wed 4/09/25 | 63 | 6
65 | Yes | Auto Scheduled | Epidemiology Solution | 31 days | Wed 2/26/25 | Wed 4/09/25 |  | 5
66 | Yes | Auto Scheduled | Integration Kickoff Meeting With DSP | 1 day | Wed 2/26/25 | Wed 2/26/25 | 57 | 6
67 | Yes | Auto Scheduled | Assess Integration Readiness | 3 days | Thu 2/27/25 | Mon 3/03/25 | 66 | 6
68 | Yes | Auto Scheduled | Build / Unit Test Interfaces | 20 days | Tue 3/04/25 | Mon 3/31/25 | 67 | 6
69 | Yes | Auto Scheduled | Perform Integrated Testing With Data Source | 5 days | Tue 4/01/25 | Mon 4/07/25 | 68 | 6
70 | Yes | Auto Scheduled | Data Source Readiness Sign-off | 2 days | Tue 4/08/25 | Wed 4/09/25 | 69 | 6
71 | Yes | Auto Scheduled | Data Source Integration Complete | 0 days | Wed 4/09/25 | Wed 4/09/25 | 70 | 6
72 | Yes | Auto Scheduled | End Integration | 0 days | Wed 4/09/25 | Wed 4/09/25 | 71 | 5
73 | Yes | Auto Scheduled | Functional Development | 126 days | Tue 8/06/24 | Tue 1/28/25 |  | 2
74 | Yes | Auto Scheduled | Data Quality & Reporting Services | 37 days | Tue 8/06/24 | Wed 9/25/24 |  | 3
75 | Yes | Auto Scheduled | Define | 10 days | Tue 8/06/24 | Mon 8/19/24 |  | 4
76 | Yes | Auto Scheduled | Develop Functional specifications | 3 days | Tue 8/06/24 | Thu 8/08/24 | 3 | 5
77 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Fri 8/09/24 | Mon 8/12/24 | 76 | 5
78 | Yes | Auto Scheduled | Develop Technical design document | 3 days | Tue 8/13/24 | Thu 8/15/24 | 77 | 5
79 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Fri 8/16/24 | Mon 8/19/24 | 78 | 5
80 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Mon 8/19/24 | Mon 8/19/24 | 79 | 5
81 | Yes | Auto Scheduled | Develop | 22 days | Tue 8/20/24 | Wed 9/18/24 |  | 4
82 | Yes | Auto Scheduled | Perform initial development | 15 days | Tue 8/20/24 | Mon 9/09/24 | 80 | 5
83 | Yes | Auto Scheduled | Peer Review Code | 2 days | Tue 9/10/24 | Wed 9/11/24 | 82 | 5
84 | Yes | Auto Scheduled | Unit Test Code | 3 days | Thu 9/12/24 | Mon 9/16/24 | 83 | 5
85 | Yes | Auto Scheduled | Remediate Issues | 2 days | Tue 9/17/24 | Wed 9/18/24 | 84 | 5
86 | Yes | Auto Scheduled | Development Complete | 0 days | Wed 9/18/24 | Wed 9/18/24 | 85 | 5
87 | Yes | Auto Scheduled | Test | 5 days | Thu 9/19/24 | Wed 9/25/24 |  | 4
88 | Yes | Auto Scheduled | Perform Integrated Testing | 3 days | Thu 9/19/24 | Mon 9/23/24 | 86 | 5
89 | Yes | Auto Scheduled | Remediate Issues | 2 days | Tue 9/24/24 | Wed 9/25/24 | 88 | 5
90 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Wed 9/25/24 | Wed 9/25/24 | 89 | 5
91 | Yes | Auto Scheduled | Care Coordination Services | 45 days | Tue 8/06/24 | Mon 10/07/24 |  | 3
92 | Yes | Auto Scheduled | HealthShare Provider Portal | 45 days | Tue 8/06/24 | Mon 10/07/24 |  | 4
93 | Yes | Auto Scheduled | Define | 13 days | Tue 8/06/24 | Thu 8/22/24 |  | 5
94 | Yes | Auto Scheduled | Develop Functional specifications | 5 days | Tue 8/06/24 | Mon 8/12/24 | 3 | 6
95 | Yes | Auto Scheduled | Specification Review and Approval | 3 days | Tue 8/13/24 | Thu 8/15/24 | 94 | 6
96 | Yes | Auto Scheduled | Develop Technical design document | 3 days | Fri 8/16/24 | Tue 8/20/24 | 95 | 6
97 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Wed 8/21/24 | Thu 8/22/24 | 96 | 6
98 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Thu 8/22/24 | Thu 8/22/24 | 97 | 6
99 | Yes | Auto Scheduled | Develop | 27 days | Fri 8/23/24 | Mon 9/30/24 |  | 5
100 | Yes | Auto Scheduled | Perform initial development | 20 days | Fri 8/23/24 | Thu 9/19/24 | 98 | 6
101 | Yes | Auto Scheduled | Peer Review Code | 2 days | Fri 9/20/24 | Mon 9/23/24 | 100 | 6
102 | Yes | Auto Scheduled | Unit Test Code | 3 days | Tue 9/24/24 | Thu 9/26/24 | 101 | 6
103 | Yes | Auto Scheduled | Remediate Issues | 2 days | Fri 9/27/24 | Mon 9/30/24 | 102 | 6
104 | Yes | Auto Scheduled | Development Complete | 0 days | Mon 9/30/24 | Mon 9/30/24 | 103 | 6
105 | Yes | Auto Scheduled | Test | 5 days | Tue 10/01/24 | Mon 10/07/24 |  | 5
106 | Yes | Auto Scheduled | Perform Integrated Testing | 3 days | Tue 10/01/24 | Thu 10/03/24 | 104 | 6
107 | Yes | Auto Scheduled | Remediate Issues | 2 days | Fri 10/04/24 | Mon 10/07/24 | 106 | 6
108 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Mon 10/07/24 | Mon 10/07/24 | 107 | 6
109 | Yes | Auto Scheduled | API Services | 23 days | Tue 8/06/24 | Thu 9/05/24 |  | 3
110 | Yes | Auto Scheduled | IHE APIs (PIX/PDQ & XDS Query and Retrieve) | 23 days | Tue 8/06/24 | Thu 9/05/24 |  | 4
111 | Yes | Auto Scheduled | Define | 4 days | Tue 8/06/24 | Fri 8/09/24 |  | 5
112 | Yes | Auto Scheduled | Develop Functional specifications | 1 day | Tue 8/06/24 | Tue 8/06/24 | 3 | 6
113 | Yes | Auto Scheduled | Specification Review and Approval | 1 day | Wed 8/07/24 | Wed 8/07/24 | 112 | 6
114 | Yes | Auto Scheduled | Develop Technical design document | 1 day | Thu 8/08/24 | Thu 8/08/24 | 113 | 6
115 | Yes | Auto Scheduled | Specification Review and Approval | 1 day | Fri 8/09/24 | Fri 8/09/24 | 114 | 6
116 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Fri 8/09/24 | Fri 8/09/24 | 115 | 6
117 | Yes | Auto Scheduled | Develop | 16 days | Mon 8/12/24 | Mon 9/02/24 |  | 5
118 | Yes | Auto Scheduled | Perform initial development | 10 days | Mon 8/12/24 | Fri 8/23/24 | 116 | 6
119 | Yes | Auto Scheduled | Peer Review Code | 1 day | Mon 8/26/24 | Mon 8/26/24 | 118 | 6
120 | Yes | Auto Scheduled | Unit Test Code | 3 days | Tue 8/27/24 | Thu 8/29/24 | 119 | 6
121 | Yes | Auto Scheduled | Remediate Issues | 2 days | Fri 8/30/24 | Mon 9/02/24 | 120 | 6
122 | Yes | Auto Scheduled | Development Complete | 0 days | Mon 9/02/24 | Mon 9/02/24 | 121 | 6
123 | Yes | Auto Scheduled | Test | 3 days | Tue 9/03/24 | Thu 9/05/24 |  | 5
124 | Yes | Auto Scheduled | Perform Integrated Testing | 2 days | Tue 9/03/24 | Wed 9/04/24 | 122 | 6
125 | Yes | Auto Scheduled | Remediate Issues | 1 day | Thu 9/05/24 | Thu 9/05/24 | 124 | 6
126 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Thu 9/05/24 | Thu 9/05/24 | 125 | 6
127 | Yes | Auto Scheduled | Medicaid Data Services | 45 days | Thu 9/26/24 | Wed 11/27/24 |  | 3
128 | Yes | Auto Scheduled | Health Insight Development | 20 days | Thu 9/26/24 | Wed 10/23/24 |  | 4
129 | Yes | Auto Scheduled | Define | 4 days | Thu 9/26/24 | Tue 10/01/24 |  | 5
130 | Yes | Auto Scheduled | Develop Functional specifications | 1 day | Thu 9/26/24 | Thu 9/26/24 | 74 | 6
131 | Yes | Auto Scheduled | Specification Review and Approval | 1 day | Fri 9/27/24 | Fri 9/27/24 | 130 | 6
132 | Yes | Auto Scheduled | Develop Technical design document | 1 day | Mon 9/30/24 | Mon 9/30/24 | 131 | 6
133 | Yes | Auto Scheduled | Specification Review and Approval | 1 day | Tue 10/01/24 | Tue 10/01/24 | 132 | 6
134 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Tue 10/01/24 | Tue 10/01/24 | 133 | 6
135 | Yes | Auto Scheduled | Develop | 13 days | Wed 10/02/24 | Fri 10/18/24 |  | 5
136 | Yes | Auto Scheduled | Perform initial development | 10 days | Wed 10/02/24 | Tue 10/15/24 | 134 | 6
137 | Yes | Auto Scheduled | Peer Review Code | 1 day | Wed 10/16/24 | Wed 10/16/24 | 136 | 6
138 | Yes | Auto Scheduled | Unit Test Code | 1 day | Thu 10/17/24 | Thu 10/17/24 | 137 | 6
139 | Yes | Auto Scheduled | Remediate Issues | 1 day | Fri 10/18/24 | Fri 10/18/24 | 138 | 6
140 | Yes | Auto Scheduled | Development Complete | 0 days | Fri 10/18/24 | Fri 10/18/24 | 139 | 6
141 | Yes | Auto Scheduled | Test | 3 days | Mon 10/21/24 | Wed 10/23/24 |  | 5
142 | Yes | Auto Scheduled | Perform Integrated Testing | 2 days | Mon 10/21/24 | Tue 10/22/24 | 140 | 6
143 | Yes | Auto Scheduled | Remediate Issues | 1 day | Wed 10/23/24 | Wed 10/23/24 | 142 | 6
144 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Wed 10/23/24 | Wed 10/23/24 | 143 | 6
145 | Yes | Auto Scheduled | PRMP Data warehouse Nightly Export | 25 days | Thu 10/24/24 | Wed 11/27/24 |  | 4
146 | Yes | Auto Scheduled | Define | 6 days | Thu 10/24/24 | Thu 10/31/24 |  | 5
147 | Yes | Auto Scheduled | Develop Functional specifications | 2 days | Thu 10/24/24 | Fri 10/25/24 | 128 | 6
148 | Yes | Auto Scheduled | Specification Review and Approval | 1 day | Mon 10/28/24 | Mon 10/28/24 | 147 | 6
149 | Yes | Auto Scheduled | Develop Technical design document | 2 days | Tue 10/29/24 | Wed 10/30/24 | 148 | 6
150 | Yes | Auto Scheduled | Specification Review and Approval | 1 day | Thu 10/31/24 | Thu 10/31/24 | 149 | 6
151 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Thu 10/31/24 | Thu 10/31/24 | 150 | 6
152 | Yes | Auto Scheduled | Develop | 14 days | Fri 11/01/24 | Wed 11/20/24 |  | 5
153 | Yes | Auto Scheduled | Perform initial development | 10 days | Fri 11/01/24 | Thu 11/14/24 | 151 | 6
154 | Yes | Auto Scheduled | Peer Review Code | 1 day | Fri 11/15/24 | Fri 11/15/24 | 153 | 6
155 | Yes | Auto Scheduled | Unit Test Code | 2 days | Mon 11/18/24 | Tue 11/19/24 | 154 | 6
156 | Yes | Auto Scheduled | Remediate Issues | 1 day | Wed 11/20/24 | Wed 11/20/24 | 155 | 6
157 | Yes | Auto Scheduled | Development Complete | 0 days | Wed 11/20/24 | Wed 11/20/24 | 156 | 6
158 | Yes | Auto Scheduled | Test | 5 days | Thu 11/21/24 | Wed 11/27/24 |  | 5
159 | Yes | Auto Scheduled | Perform Integrated Testing | 3 days | Thu 11/21/24 | Mon 11/25/24 | 157 | 6
160 | Yes | Auto Scheduled | Remediate Issues | 2 days | Tue 11/26/24 | Wed 11/27/24 | 159 | 6
161 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Wed 11/27/24 | Wed 11/27/24 | 160 | 6
162 | Yes | Auto Scheduled | Electronic Notification Services | 37 days | Tue 10/08/24 | Wed 11/27/24 |  | 3
163 | Yes | Auto Scheduled | Define | 10 days | Tue 10/08/24 | Mon 10/21/24 |  | 4
164 | Yes | Auto Scheduled | Develop Functional specifications | 3 days | Tue 10/08/24 | Thu 10/10/24 | 91 | 5
165 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Fri 10/11/24 | Mon 10/14/24 | 164 | 5
166 | Yes | Auto Scheduled | Develop Technical design document | 3 days | Tue 10/15/24 | Thu 10/17/24 | 165 | 5
167 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Fri 10/18/24 | Mon 10/21/24 | 166 | 5
168 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Mon 10/21/24 | Mon 10/21/24 | 167 | 5
169 | Yes | Auto Scheduled | Develop | 22 days | Tue 10/22/24 | Wed 11/20/24 | 163 | 4
170 | Yes | Auto Scheduled | Perform initial development | 15 days | Tue 10/22/24 | Mon 11/11/24 | 168 | 5
171 | Yes | Auto Scheduled | Peer Review Code | 2 days | Tue 11/12/24 | Wed 11/13/24 | 170 | 5
172 | Yes | Auto Scheduled | Unit Test Code | 3 days | Thu 11/14/24 | Mon 11/18/24 | 171 | 5
173 | Yes | Auto Scheduled | Remediate Issues | 2 days | Tue 11/19/24 | Wed 11/20/24 | 172 | 5
174 | Yes | Auto Scheduled | Development Complete | 0 days | Wed 11/20/24 | Wed 11/20/24 | 173 | 5
175 | Yes | Auto Scheduled | Test | 5 days | Thu 11/21/24 | Wed 11/27/24 |  | 4
176 | Yes | Auto Scheduled | Perform Integrated Testing | 3 days | Thu 11/21/24 | Mon 11/25/24 | 174 | 5
177 | Yes | Auto Scheduled | Remediate Issues | 2 days | Tue 11/26/24 | Wed 11/27/24 | 176 | 5
178 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Wed 11/27/24 | Wed 11/27/24 | 177 | 5
179 | Yes | Auto Scheduled | Emergency Response Services | 35 days | Fri 9/06/24 | Thu 10/24/24 |  | 3
180 | Yes | Auto Scheduled | EHX Integration | 35 days | Fri 9/06/24 | Thu 10/24/24 |  | 4
181 | Yes | Auto Scheduled | Define | 6 days | Fri 9/06/24 | Fri 9/13/24 |  | 5
182 | Yes | Auto Scheduled | Develop Functional specifications | 2 days | Fri 9/06/24 | Mon 9/09/24 | 109 | 6
183 | Yes | Auto Scheduled | Specification Review and Approval | 1 day | Tue 9/10/24 | Tue 9/10/24 | 182 | 6
184 | Yes | Auto Scheduled | Develop Technical design document | 2 days | Wed 9/11/24 | Thu 9/12/24 | 183 | 6
185 | Yes | Auto Scheduled | Specification Review and Approval | 1 day | Fri 9/13/24 | Fri 9/13/24 | 184 | 6
186 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Fri 9/13/24 | Fri 9/13/24 | 185 | 6
187 | Yes | Auto Scheduled | Develop | 22 days | Mon 9/16/24 | Tue 10/15/24 | 181 | 5
188 | Yes | Auto Scheduled | Perform initial development | 15 days | Mon 9/16/24 | Fri 10/04/24 | 186 | 6
189 | Yes | Auto Scheduled | Peer Review Code | 2 days | Mon 10/07/24 | Tue 10/08/24 | 188 | 6
190 | Yes | Auto Scheduled | Unit Test Code | 3 days | Wed 10/09/24 | Fri 10/11/24 | 189 | 6
191 | Yes | Auto Scheduled | Remediate Issues | 2 days | Mon 10/14/24 | Tue 10/15/24 | 190 | 6
192 | Yes | Auto Scheduled | Development Complete | 0 days | Tue 10/15/24 | Tue 10/15/24 | 191 | 6
193 | Yes | Auto Scheduled | Test | 7 days | Wed 10/16/24 | Thu 10/24/24 |  | 5
194 | Yes | Auto Scheduled | Perform Integrated Testing | 5 days | Wed 10/16/24 | Tue 10/22/24 | 192 | 6
195 | Yes | Auto Scheduled | Remediate Issues | 2 days | Wed 10/23/24 | Thu 10/24/24 | 194 | 6
196 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Thu 10/24/24 | Thu 10/24/24 | 195 | 6
197 | Yes | Auto Scheduled | Consent Management Configuration | 29 days | Thu 11/28/24 | Tue 1/07/25 |  | 3
198 | Yes | Auto Scheduled | Define | 10 days | Thu 11/28/24 | Wed 12/11/24 |  | 4
199 | Yes | Auto Scheduled | Develop Functional specifications | 3 days | Thu 11/28/24 | Mon 12/02/24 | 162 | 5
200 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Tue 12/03/24 | Wed 12/04/24 | 199 | 5
201 | Yes | Auto Scheduled | Develop Technical design document | 3 days | Thu 12/05/24 | Mon 12/09/24 | 200 | 5
202 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Tue 12/10/24 | Wed 12/11/24 | 201 | 5
203 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Wed 12/11/24 | Wed 12/11/24 | 202 | 5
204 | Yes | Auto Scheduled | Develop | 14 days | Thu 12/12/24 | Tue 12/31/24 | 198 | 4
205 | Yes | Auto Scheduled | Perform initial development | 10 days | Thu 12/12/24 | Wed 12/25/24 | 203 | 5
206 | Yes | Auto Scheduled | Peer Review Code | 1 day | Thu 12/26/24 | Thu 12/26/24 | 205 | 5
207 | Yes | Auto Scheduled | Unit Test Code | 2 days | Fri 12/27/24 | Mon 12/30/24 | 206 | 5
208 | Yes | Auto Scheduled | Remediate Issues | 1 day | Tue 12/31/24 | Tue 12/31/24 | 207 | 5
209 | Yes | Auto Scheduled | Development Complete | 0 days | Tue 12/31/24 | Tue 12/31/24 | 208 | 5
210 | Yes | Auto Scheduled | Test | 5 days | Wed 1/01/25 | Tue 1/07/25 |  | 4
211 | Yes | Auto Scheduled | Perform Integrated Testing | 3 days | Wed 1/01/25 | Fri 1/03/25 | 209 | 5
212 | Yes | Auto Scheduled | Remediate Issues | 2 days | Mon 1/06/25 | Tue 1/07/25 | 211 | 5
213 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Tue 1/07/25 | Tue 1/07/25 | 212 | 5
214 | Yes | Auto Scheduled | Operational Reporting & Key Metrics | 44 days | Thu 11/28/24 | Tue 1/28/25 |  | 3
215 | Yes | Auto Scheduled | Define | 10 days | Thu 11/28/24 | Wed 12/11/24 |  | 4
216 | Yes | Auto Scheduled | Develop Functional specifications | 3 days | Thu 11/28/24 | Mon 12/02/24 | 127 | 5
217 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Tue 12/03/24 | Wed 12/04/24 | 216 | 5
218 | Yes | Auto Scheduled | Develop Technical design document | 3 days | Thu 12/05/24 | Mon 12/09/24 | 217 | 5
219 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Tue 12/10/24 | Wed 12/11/24 | 218 | 5
220 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Wed 12/11/24 | Wed 12/11/24 | 219 | 5
221 | Yes | Auto Scheduled | Develop | 29 days | Thu 12/12/24 | Tue 1/21/25 | 215 | 4
222 | Yes | Auto Scheduled | Perform initial development | 20 days | Thu 12/12/24 | Wed 1/08/25 | 220 | 5
223 | Yes | Auto Scheduled | Peer Review Code | 2 days | Thu 1/09/25 | Fri 1/10/25 | 222 | 5
224 | Yes | Auto Scheduled | Unit Test Code | 5 days | Mon 1/13/25 | Fri 1/17/25 | 223 | 5
225 | Yes | Auto Scheduled | Remediate Issues | 2 days | Mon 1/20/25 | Tue 1/21/25 | 224 | 5
226 | Yes | Auto Scheduled | Development Complete | 0 days | Tue 1/21/25 | Tue 1/21/25 | 225 | 5
227 | Yes | Auto Scheduled | Test | 5 days | Wed 1/22/25 | Tue 1/28/25 |  | 4
228 | Yes | Auto Scheduled | Perform Integrated Testing | 3 days | Wed 1/22/25 | Fri 1/24/25 | 226 | 5
229 | Yes | Auto Scheduled | Remediate Issues | 2 days | Mon 1/27/25 | Tue 1/28/25 | 228 | 5
230 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Tue 1/28/25 | Tue 1/28/25 | 229 | 5
231 | Yes | Auto Scheduled | Enterprise Identity Services | 35 days | Fri 10/25/24 | Thu 12/12/24 |  | 3
232 | Yes | Auto Scheduled | Define Requirements | 5 days | Fri 10/25/24 | Thu 10/31/24 | 179 | 4
233 | Yes | Auto Scheduled | HSPI Initial Configuration | 7 days | Fri 11/01/24 | Mon 11/11/24 | 232 | 4
234 | Yes | Auto Scheduled | Perform Tuning Round 1 | 9 days | Tue 11/12/24 | Fri 11/22/24 |  | 4
235 | Yes | Auto Scheduled | Load Initial Patient Extracts From Data Sources | 1 day | Tue 11/12/24 | Tue 11/12/24 | 233 | 5
236 | Yes | Auto Scheduled | Review Results | 5 days | Wed 11/13/24 | Tue 11/19/24 | 235 | 5
237 | Yes | Auto Scheduled | Modify Parameters | 3 days | Wed 11/20/24 | Fri 11/22/24 | 236 | 5
238 | Yes | Auto Scheduled | Perform Tuning Round 2 | 9 days | Mon 11/25/24 | Thu 12/05/24 |  | 4
239 | Yes | Auto Scheduled | Load Initial Patient Extracts From Data Sources | 1 day | Mon 11/25/24 | Mon 11/25/24 | 237 | 5
240 | Yes | Auto Scheduled | Review Results | 5 days | Tue 11/26/24 | Mon 12/02/24 | 239 | 5
241 | Yes | Auto Scheduled | Modify Parameters | 3 days | Tue 12/03/24 | Thu 12/05/24 | 240 | 5
242 | Yes | Auto Scheduled | Test | 5 days | Fri 12/06/24 | Thu 12/12/24 |  | 4
243 | Yes | Auto Scheduled | Perform Integrated Testing | 3 days | Fri 12/06/24 | Tue 12/10/24 | 241 | 5
244 | Yes | Auto Scheduled | Remediate Issues | 2 days | Wed 12/11/24 | Thu 12/12/24 | 243 | 5
245 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Thu 12/12/24 | Thu 12/12/24 | 244 | 5
246 | Yes | Auto Scheduled | Direct Secure Messaging | 37 days | Tue 8/06/24 | Wed 9/25/24 |  | 2
247 | Yes | Auto Scheduled | SES Direct HISP Deployment | 37 days | Tue 8/06/24 | Wed 9/25/24 |  | 3
248 | Yes | Auto Scheduled | Define | 10 days | Tue 8/06/24 | Mon 8/19/24 |  | 4
249 | Yes | Auto Scheduled | Develop Functional specifications | 3 days | Tue 8/06/24 | Thu 8/08/24 | 3 | 5
250 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Fri 8/09/24 | Mon 8/12/24 | 249 | 5
251 | Yes | Auto Scheduled | Develop Technical design document | 3 days | Tue 8/13/24 | Thu 8/15/24 | 250 | 5
252 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Fri 8/16/24 | Mon 8/19/24 | 251 | 5
253 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Mon 8/19/24 | Mon 8/19/24 | 252 | 5
254 | Yes | Auto Scheduled | Develop | 22 days | Tue 8/20/24 | Wed 9/18/24 |  | 4
255 | Yes | Auto Scheduled | Perform initial development | 15 days | Tue 8/20/24 | Mon 9/09/24 | 253 | 5
256 | Yes | Auto Scheduled | Peer Review Code | 2 days | Tue 9/10/24 | Wed 9/11/24 | 255 | 5
257 | Yes | Auto Scheduled | Unit Test Code | 3 days | Thu 9/12/24 | Mon 9/16/24 | 256 | 5
258 | Yes | Auto Scheduled | Remediate Issues | 2 days | Tue 9/17/24 | Wed 9/18/24 | 257 | 5
259 | Yes | Auto Scheduled | Development Complete | 0 days | Wed 9/18/24 | Wed 9/18/24 | 258 | 5
260 | Yes | Auto Scheduled | Test | 5 days | Thu 9/19/24 | Wed 9/25/24 |  | 4
261 | Yes | Auto Scheduled | Perform Integrated Testing | 3 days | Thu 9/19/24 | Mon 9/23/24 | 259 | 5
262 | Yes | Auto Scheduled | Remediate Issues | 2 days | Tue 9/24/24 | Wed 9/25/24 | 261 | 5
263 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Wed 9/25/24 | Wed 9/25/24 | 262 | 5
264 | Yes | Auto Scheduled | Historical Data Migration From HG Platform | 180 days | Tue 8/06/24 | Mon 4/14/25 |  | 2
265 | Yes | Auto Scheduled | Define | 32 days | Tue 8/06/24 | Wed 9/18/24 |  | 3
266 | Yes | Auto Scheduled | Define Migration Process & Integration Requirements | 2 days | Tue 8/06/24 | Wed 8/07/24 | 3 | 4
267 | Yes | Auto Scheduled | Receive Sample Data Extract 1 to Analyze | 5 days | Thu 8/08/24 | Wed 8/14/24 | 266 | 4
268 | Yes | Auto Scheduled | Analyze Sample Extract 1 | 5 days | Thu 8/15/24 | Wed 8/21/24 | 267 | 4
269 | Yes | Auto Scheduled | Review Issues and Perform Remediation | 5 days | Thu 8/22/24 | Wed 8/28/24 | 268 | 4
270 | Yes | Auto Scheduled | Receive Sample Data Extract 2 to Analyze | 5 days | Thu 8/29/24 | Wed 9/04/24 | 269 | 4
271 | Yes | Auto Scheduled | Analyze Sample Extract 2 | 5 days | Thu 9/05/24 | Wed 9/11/24 | 270 | 4
272 | Yes | Auto Scheduled | Review Issues and Perform Remediation | 5 days | Thu 9/12/24 | Wed 9/18/24 | 271 | 4
273 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Wed 9/11/24 | Wed 9/11/24 | 271 | 4
274 | Yes | Auto Scheduled | Develop | 39 days | Thu 9/12/24 | Tue 11/05/24 |  | 3
275 | Yes | Auto Scheduled | Perform initial development | 30 days | Thu 9/12/24 | Wed 10/23/24 | 273 | 4
276 | Yes | Auto Scheduled | Peer Review Code | 2 days | Thu 10/24/24 | Fri 10/25/24 | 275 | 4
277 | Yes | Auto Scheduled | Unit Test Code | 5 days | Mon 10/28/24 | Fri 11/01/24 | 276 | 4
278 | Yes | Auto Scheduled | Remediate Issues | 2 days | Mon 11/04/24 | Tue 11/05/24 | 277 | 4
279 | Yes | Auto Scheduled | Development Complete | 0 days | Tue 11/05/24 | Tue 11/05/24 | 278 | 4
280 | Yes | Auto Scheduled | Test | 21 days | Wed 11/06/24 | Wed 12/04/24 |  | 3
281 | Yes | Auto Scheduled | Perform Integrated Testing | 5 days | Wed 11/06/24 | Tue 11/12/24 | 279 | 4
282 | Yes | Auto Scheduled | Remediate Issues | 5 days | Wed 11/13/24 | Tue 11/19/24 | 281 | 4
283 | Yes | Auto Scheduled | Perform UAT Testing | 10 days | Wed 11/20/24 | Tue 12/03/24 | 282 | 4
284 | Yes | Auto Scheduled | Go Live Decision | 1 day | Wed 12/04/24 | Wed 12/04/24 | 283 | 4
285 | Yes | Auto Scheduled | Migration Load | 34 days | Wed 2/26/25 | Mon 4/14/25 |  | 3
286 | Yes | Auto Scheduled | Receive Full Set of Export Data from HG | 7 days | Wed 2/26/25 | Thu 3/06/25 | 34;284 | 4
287 | Yes | Auto Scheduled | Smoke Test Data | 3 days | Fri 3/07/25 | Tue 3/11/25 | 286 | 4
288 | Yes | Auto Scheduled | Perform Historical Data Load | 20 days | Wed 3/12/25 | Tue 4/08/25 | 287 | 4
289 | Yes | Auto Scheduled | Review Load Results | 3 days | Wed 4/09/25 | Fri 4/11/25 | 288 | 4
290 | Yes | Auto Scheduled | Declare Live | 1 day | Mon 4/14/25 | Mon 4/14/25 | 289 | 4
291 | Yes | Auto Scheduled | User Acceptance Testing | 41 days | Tue 4/15/25 | Tue 6/10/25 |  | 2
292 | Yes | Auto Scheduled | Finalize Test Plan | 5 days | Tue 4/15/25 | Mon 4/21/25 | 26;74;91;109;127;162;179;197;214;231;246;290 | 3
293 | Yes | Auto Scheduled | Execute Test Plan | 15 days | Tue 4/22/25 | Mon 5/12/25 | 292 | 3
294 | Yes | Auto Scheduled | Review Test Plan | 5 days | Tue 5/13/25 | Mon 5/19/25 | 293 | 3
295 | Yes | Auto Scheduled | Remediate Issues | 10 days | Tue 5/20/25 | Mon 6/02/25 | 294 | 3
296 | Yes | Auto Scheduled | Retest | 3 days | Tue 6/03/25 | Thu 6/05/25 | 295 | 3
297 | Yes | Auto Scheduled | Review Retest Results | 2 days | Fri 6/06/25 | Mon 6/09/25 | 296 | 3
298 | Yes | Auto Scheduled | Go Live Decision | 1 day | Tue 6/10/25 | Tue 6/10/25 | 297 | 3
299 | Yes | Auto Scheduled | Go-Live | 5 days | Wed 6/11/25 | Tue 6/17/25 |  | 2
300 | Yes | Auto Scheduled | Deploy Code | 2 days | Wed 6/11/25 | Thu 6/12/25 | 22;298 | 3
301 | Yes | Auto Scheduled | Perform Smoke Test | 3 days | Fri 6/13/25 | Tue 6/17/25 | 300 | 3
302 | Yes | Auto Scheduled | Declare System Live | 0 days | Tue 6/17/25 | Tue 6/17/25 | 301 | 3
303 | Yes | Auto Scheduled | End User Training | 20 days | Wed 6/18/25 | Tue 7/15/25 | 302 | 1
304 | Yes | Auto Scheduled | Post Go-Live Support | 270 days | Wed 6/18/25 | Tue 6/30/26 | 302 | 1
305 | Yes | Auto Scheduled | Phase 2 | 262 days | Wed 6/18/25 | Thu 6/18/26 |  | 1
306 | Yes | Auto Scheduled | Requirements Discovery | 11 days | Wed 6/18/25 | Wed 7/02/25 |  | 2
307 | Yes | Auto Scheduled | Review Phase Scope | 1 day | Wed 6/18/25 | Wed 6/18/25 | 299 | 3
308 | Yes | Auto Scheduled | Identify New Data Sources | 5 days | Thu 6/19/25 | Wed 6/25/25 | 307 | 3
309 | Yes | Auto Scheduled | Review Functional Requirements | 5 days | Thu 6/19/25 | Wed 6/25/25 | 307 | 3
310 | Yes | Auto Scheduled | Update Project and Resource Plan | 5 days | Thu 6/26/25 | Wed 7/02/25 | 309;308 | 3
311 | Yes | Auto Scheduled | Integration | 217 days | Thu 7/03/25 | Fri 5/01/26 |  | 2
312 | Yes | Auto Scheduled | Interface Specification & Configuration | 26 days | Thu 7/03/25 | Thu 8/07/25 |  | 3
313 | Yes | Auto Scheduled | Review existing interface standard | 5 days | Thu 7/03/25 | Wed 7/09/25 | 306 | 4
314 | Yes | Auto Scheduled | Develop new interface specifications (VXU, MCO, FHIR) | 10 days | Thu 7/10/25 | Wed 7/23/25 | 313 | 4
315 | Yes | Auto Scheduled | Undertake document review with client | 5 days | Thu 7/24/25 | Wed 7/30/25 | 314 | 4
316 | Yes | Auto Scheduled | Publish new specifications | 1 day | Thu 7/31/25 | Thu 7/31/25 | 315 | 4
317 | Yes | Auto Scheduled | Configure base ADT interface in all environments | 5 days | Fri 8/01/25 | Thu 8/07/25 | 316 | 4
318 | Yes | Auto Scheduled | Configure base ELR interface in all environments | 5 days | Fri 8/01/25 | Thu 8/07/25 | 316 | 4
319 | Yes | Auto Scheduled | Configure base VXU interface in all environments | 5 days | Fri 8/01/25 | Thu 8/07/25 | 316 | 4
320 | Yes | Auto Scheduled | Inbound Interfaces | 186 days | Thu 7/03/25 | Thu 3/19/26 |  | 3
321 | Yes | Auto Scheduled | ADT Interfaces (New) | 186 days | Thu 7/03/25 | Thu 3/19/26 |  | 4
322 | Yes | Auto Scheduled | Start Integration | 0 days | Thu 8/07/25 | Thu 8/07/25 | 317 | 5
323 | Yes | Auto Scheduled | Per Data Source (repeats 24 times) | 36 days | Thu 7/03/25 | Thu 8/21/25 |  | 5
324 | Yes | Auto Scheduled | Integration Kickoff Meeting With DSP | 1 day | Thu 7/03/25 | Thu 7/03/25 | 306 | 6
325 | Yes | Auto Scheduled | Assess Integration Readiness | 3 days | Fri 7/04/25 | Tue 7/08/25 | 324 | 6
326 | Yes | Auto Scheduled | Build / Unit Test Interfaces | 20 days | Wed 7/09/25 | Tue 8/05/25 | 325 | 6
327 | Yes | Auto Scheduled | Perform Integrated Testing With Data Source | 10 days | Wed 8/06/25 | Tue 8/19/25 | 326 | 6
328 | Yes | Auto Scheduled | Data Source Readiness Sign-off | 2 days | Wed 8/20/25 | Thu 8/21/25 | 327 | 6
329 | Yes | Auto Scheduled | Data Source Integration Complete | 0 days | Thu 8/21/25 | Thu 8/21/25 | 328 | 6
330 | Yes | Auto Scheduled | End Integration | 0 days | Thu 3/19/26 | Thu 3/19/26 | 322FF+160 days | 5
331 | Yes | Auto Scheduled | ELR Interfaces (New) | 186 days | Thu 7/03/25 | Thu 3/19/26 |  | 4
332 | Yes | Auto Scheduled | Start Integration | 0 days | Thu 8/07/25 | Thu 8/07/25 | 318 | 5
333 | Yes | Auto Scheduled | Per Data Source (repeats 24 times) | 36 days | Thu 7/03/25 | Thu 8/21/25 |  | 5
334 | Yes | Auto Scheduled | Integration Kickoff Meeting With DSP | 1 day | Thu 7/03/25 | Thu 7/03/25 | 306 | 6
335 | Yes | Auto Scheduled | Assess Integration Readiness | 3 days | Fri 7/04/25 | Tue 7/08/25 | 334 | 6
336 | Yes | Auto Scheduled | Build / Unit Test Interfaces | 20 days | Wed 7/09/25 | Tue 8/05/25 | 335 | 6
337 | Yes | Auto Scheduled | Perform Integrated Testing With Data Source | 10 days | Wed 8/06/25 | Tue 8/19/25 | 336 | 6
338 | Yes | Auto Scheduled | Data Source Readiness Sign-off | 2 days | Wed 8/20/25 | Thu 8/21/25 | 337 | 6
339 | Yes | Auto Scheduled | Data Source Integration Complete | 0 days | Thu 8/21/25 | Thu 8/21/25 | 338 | 6
340 | Yes | Auto Scheduled | End ELR Integration | 44 days | Mon 1/19/26 | Thu 3/19/26 | 332FF+160 days | 5
341 | Yes | Auto Scheduled | VXU Interfaces | 186 days | Thu 7/03/25 | Thu 3/19/26 |  | 4
342 | Yes | Auto Scheduled | Start Integration | 0 days | Thu 8/07/25 | Thu 8/07/25 | 319 | 5
343 | Yes | Auto Scheduled | Per Data Source (repeats 52 times) | 36 days | Thu 7/03/25 | Thu 8/21/25 |  | 5
344 | Yes | Auto Scheduled | Integration Kickoff Meeting With DSP | 1 day | Thu 7/03/25 | Thu 7/03/25 | 306 | 6
345 | Yes | Auto Scheduled | Assess Integration Readiness | 3 days | Fri 7/04/25 | Tue 7/08/25 | 344 | 6
346 | Yes | Auto Scheduled | Build / Unit Test Interfaces | 20 days | Wed 7/09/25 | Tue 8/05/25 | 345 | 6
347 | Yes | Auto Scheduled | Perform Integrated Testing With Data Source | 10 days | Wed 8/06/25 | Tue 8/19/25 | 346 | 6
348 | Yes | Auto Scheduled | Data Source Readiness Sign-off | 2 days | Wed 8/20/25 | Thu 8/21/25 | 347 | 6
349 | Yes | Auto Scheduled | Data Source Integration Complete | 0 days | Thu 8/21/25 | Thu 8/21/25 | 348 | 6
350 | Yes | Auto Scheduled | End ELR Integration | 44 days | Mon 1/19/26 | Thu 3/19/26 | 342FF+160 days | 5
351 | Yes | Auto Scheduled | Outbound Interfaces | 191 days | Fri 8/08/25 | Fri 5/01/26 |  | 3
352 | Yes | Auto Scheduled | Public Health Reporting - VXU Interface | 31 days | Fri 3/20/26 | Fri 5/01/26 |  | 4
353 | Yes | Auto Scheduled | Immunization Registry | 31 days | Fri 3/20/26 | Fri 5/01/26 |  | 5
354 | Yes | Auto Scheduled | Integration Kickoff Meeting With DSP | 1 day | Fri 3/20/26 | Fri 3/20/26 | 341 | 6
355 | Yes | Auto Scheduled | Assess Integration Readiness | 3 days | Mon 3/23/26 | Wed 3/25/26 | 354 | 6
356 | Yes | Auto Scheduled | Build / Unit Test Interfaces | 20 days | Thu 3/26/26 | Wed 4/22/26 | 355 | 6
357 | Yes | Auto Scheduled | Perform Integrated Testing With Data Source | 5 days | Thu 4/23/26 | Wed 4/29/26 | 356 | 6
358 | Yes | Auto Scheduled | Data Source Readiness Sign-off | 2 days | Thu 4/30/26 | Fri 5/01/26 | 357 | 6
359 | Yes | Auto Scheduled | Data Source Integration Complete | 0 days | Fri 5/01/26 | Fri 5/01/26 | 358 | 6
360 | Yes | Auto Scheduled | Emergency Response Services - ADT Interface | 31 days | Fri 8/08/25 | Fri 9/19/25 |  | 4
361 | Yes | Auto Scheduled | Integration Kickoff Meeting With DSP | 1 day | Fri 8/08/25 | Fri 8/08/25 | 312 | 5
362 | Yes | Auto Scheduled | Assess Integration Readiness | 3 days | Mon 8/11/25 | Wed 8/13/25 | 361 | 5
363 | Yes | Auto Scheduled | Build / Unit Test Interfaces | 20 days | Thu 8/14/25 | Wed 9/10/25 | 362 | 5
364 | Yes | Auto Scheduled | Perform Integrated Testing With Data Source | 5 days | Thu 9/11/25 | Wed 9/17/25 | 363 | 5
365 | Yes | Auto Scheduled | Data Source Readiness Sign-off | 2 days | Thu 9/18/25 | Fri 9/19/25 | 364 | 5
366 | Yes | Auto Scheduled | Data Source Integration Complete | 0 days | Fri 9/19/25 | Fri 9/19/25 | 365 | 5
367 | Yes | Auto Scheduled | Functional Development | 101 days | Thu 7/03/25 | Thu 11/20/25 |  | 2
368 | Yes | Auto Scheduled | Data Quality & Reporting Services | 37 days | Thu 7/03/25 | Fri 8/22/25 |  | 3
369 | Yes | Auto Scheduled | Define | 10 days | Thu 7/03/25 | Wed 7/16/25 |  | 4
370 | Yes | Auto Scheduled | Develop Functional specifications | 3 days | Thu 7/03/25 | Mon 7/07/25 | 306 | 5
371 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Tue 7/08/25 | Wed 7/09/25 | 370 | 5
372 | Yes | Auto Scheduled | Develop Technical design document | 3 days | Thu 7/10/25 | Mon 7/14/25 | 371 | 5
373 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Tue 7/15/25 | Wed 7/16/25 | 372 | 5
374 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Wed 7/16/25 | Wed 7/16/25 | 373 | 5
375 | Yes | Auto Scheduled | Develop | 22 days | Thu 7/17/25 | Fri 8/15/25 |  | 4
376 | Yes | Auto Scheduled | Perform initial development | 15 days | Thu 7/17/25 | Wed 8/06/25 | 374 | 5
377 | Yes | Auto Scheduled | Peer Review Code | 2 days | Thu 8/07/25 | Fri 8/08/25 | 376 | 5
378 | Yes | Auto Scheduled | Unit Test Code | 3 days | Mon 8/11/25 | Wed 8/13/25 | 377 | 5
379 | Yes | Auto Scheduled | Remediate Issues | 2 days | Thu 8/14/25 | Fri 8/15/25 | 378 | 5
380 | Yes | Auto Scheduled | Development Complete | 0 days | Fri 8/15/25 | Fri 8/15/25 | 379 | 5
381 | Yes | Auto Scheduled | Test | 5 days | Mon 8/18/25 | Fri 8/22/25 |  | 4
382 | Yes | Auto Scheduled | Perform Integrated Testing | 3 days | Mon 8/18/25 | Wed 8/20/25 | 380 | 5
383 | Yes | Auto Scheduled | Remediate Issues | 2 days | Thu 8/21/25 | Fri 8/22/25 | 382 | 5
384 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Fri 8/22/25 | Fri 8/22/25 | 383 | 5
385 | Yes | Auto Scheduled | API Services | 34 days | Thu 7/03/25 | Tue 8/19/25 |  | 3
386 | Yes | Auto Scheduled | FHIR APIs (Query Only) | 34 days | Thu 7/03/25 | Tue 8/19/25 |  | 4
387 | Yes | Auto Scheduled | Define | 10 days | Thu 7/03/25 | Wed 7/16/25 |  | 5
388 | Yes | Auto Scheduled | Develop Functional specifications | 3 days | Thu 7/03/25 | Mon 7/07/25 | 306 | 6
389 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Tue 7/08/25 | Wed 7/09/25 | 388 | 6
390 | Yes | Auto Scheduled | Develop Technical design document | 3 days | Thu 7/10/25 | Mon 7/14/25 | 389 | 6
391 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Tue 7/15/25 | Wed 7/16/25 | 390 | 6
392 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Wed 7/16/25 | Wed 7/16/25 | 391 | 6
393 | Yes | Auto Scheduled | Develop | 21 days | Thu 7/17/25 | Thu 8/14/25 |  | 5
394 | Yes | Auto Scheduled | Perform initial development | 15 days | Thu 7/17/25 | Wed 8/06/25 | 392 | 6
395 | Yes | Auto Scheduled | Peer Review Code | 1 day | Thu 8/07/25 | Thu 8/07/25 | 394 | 6
396 | Yes | Auto Scheduled | Unit Test Code | 3 days | Fri 8/08/25 | Tue 8/12/25 | 395 | 6
397 | Yes | Auto Scheduled | Remediate Issues | 2 days | Wed 8/13/25 | Thu 8/14/25 | 396 | 6
398 | Yes | Auto Scheduled | Development Complete | 0 days | Thu 8/14/25 | Thu 8/14/25 | 397 | 6
399 | Yes | Auto Scheduled | Test | 3 days | Fri 8/15/25 | Tue 8/19/25 |  | 5
400 | Yes | Auto Scheduled | Perform Integrated Testing | 2 days | Fri 8/15/25 | Mon 8/18/25 | 398 | 6
401 | Yes | Auto Scheduled | Remediate Issues | 1 day | Tue 8/19/25 | Tue 8/19/25 | 400 | 6
402 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Tue 8/19/25 | Tue 8/19/25 | 401 | 6
403 | Yes | Auto Scheduled | Medicaid Data Services | 101 days | Thu 7/03/25 | Thu 11/20/25 |  | 3
404 | Yes | Auto Scheduled | Report and Dashboard Development | 101 days | Thu 7/03/25 | Thu 11/20/25 |  | 4
405 | Yes | Auto Scheduled | Define | 16 days | Thu 7/03/25 | Thu 7/24/25 |  | 5
406 | Yes | Auto Scheduled | Develop Functional specifications | 5 days | Thu 7/03/25 | Wed 7/09/25 | 306 | 6
407 | Yes | Auto Scheduled | Specification Review and Approval | 3 days | Thu 7/10/25 | Mon 7/14/25 | 406 | 6
408 | Yes | Auto Scheduled | Develop Technical design document | 5 days | Tue 7/15/25 | Mon 7/21/25 | 407 | 6
409 | Yes | Auto Scheduled | Specification Review and Approval | 3 days | Tue 7/22/25 | Thu 7/24/25 | 408 | 6
410 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Thu 7/24/25 | Thu 7/24/25 | 409 | 6
411 | Yes | Auto Scheduled | Develop | 75 days | Fri 7/25/25 | Thu 11/06/25 |  | 5
412 | Yes | Auto Scheduled | Perform initial development | 60 days | Fri 7/25/25 | Thu 10/16/25 | 410 | 6
413 | Yes | Auto Scheduled | Peer Review Code | 5 days | Fri 10/17/25 | Thu 10/23/25 | 412 | 6
414 | Yes | Auto Scheduled | Unit Test Code | 5 days | Fri 10/24/25 | Thu 10/30/25 | 413 | 6
415 | Yes | Auto Scheduled | Remediate Issues | 5 days | Fri 10/31/25 | Thu 11/06/25 | 414 | 6
416 | Yes | Auto Scheduled | Development Complete | 0 days | Thu 11/06/25 | Thu 11/06/25 | 415 | 6
417 | Yes | Auto Scheduled | Test | 10 days | Fri 11/07/25 | Thu 11/20/25 |  | 5
418 | Yes | Auto Scheduled | Perform Integrated Testing | 5 days | Fri 11/07/25 | Thu 11/13/25 | 416 | 6
419 | Yes | Auto Scheduled | Remediate Issues | 5 days | Fri 11/14/25 | Thu 11/20/25 | 418 | 6
420 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Thu 11/20/25 | Thu 11/20/25 | 419 | 6
421 | Yes | Auto Scheduled | Electronic Notification Services (Enhancements) | 28 days | Thu 7/03/25 | Mon 8/11/25 |  | 3
422 | Yes | Auto Scheduled | Define | 8 days | Thu 7/03/25 | Mon 7/14/25 |  | 4
423 | Yes | Auto Scheduled | Develop Functional specifications | 3 days | Thu 7/03/25 | Mon 7/07/25 | 306 | 5
424 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Tue 7/08/25 | Wed 7/09/25 | 423 | 5
425 | Yes | Auto Scheduled | Develop Technical design document | 2 days | Thu 7/10/25 | Fri 7/11/25 | 424 | 5
426 | Yes | Auto Scheduled | Specification Review and Approval | 1 day | Mon 7/14/25 | Mon 7/14/25 | 425 | 5
427 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Mon 7/14/25 | Mon 7/14/25 | 426 | 5
428 | Yes | Auto Scheduled | Develop | 15 days | Tue 7/15/25 | Mon 8/04/25 | 422 | 4
429 | Yes | Auto Scheduled | Perform initial development | 10 days | Tue 7/15/25 | Mon 7/28/25 | 427 | 5
430 | Yes | Auto Scheduled | Peer Review Code | 1 day | Tue 7/29/25 | Tue 7/29/25 | 429 | 5
431 | Yes | Auto Scheduled | Unit Test Code | 2 days | Wed 7/30/25 | Thu 7/31/25 | 430 | 5
432 | Yes | Auto Scheduled | Remediate Issues | 2 days | Fri 8/01/25 | Mon 8/04/25 | 431 | 5
433 | Yes | Auto Scheduled | Development Complete | 0 days | Mon 8/04/25 | Mon 8/04/25 | 432 | 5
434 | Yes | Auto Scheduled | Test | 5 days | Tue 8/05/25 | Mon 8/11/25 |  | 4
435 | Yes | Auto Scheduled | Perform Integrated Testing | 3 days | Tue 8/05/25 | Thu 8/07/25 | 433 | 5
436 | Yes | Auto Scheduled | Remediate Issues | 2 days | Fri 8/08/25 | Mon 8/11/25 | 435 | 5
437 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Mon 8/11/25 | Mon 8/11/25 | 436 | 5
438 | Yes | Auto Scheduled | Emergency Response Services | 23 days | Mon 9/22/25 | Wed 10/22/25 |  | 3
439 | Yes | Auto Scheduled | ADT Event Routing to Emergency Response Vendor | 23 days | Mon 9/22/25 | Wed 10/22/25 |  | 4
440 | Yes | Auto Scheduled | Define | 6 days | Mon 9/22/25 | Mon 9/29/25 |  | 5
441 | Yes | Auto Scheduled | Develop Functional specifications | 2 days | Mon 9/22/25 | Tue 9/23/25 | 360 | 6
442 | Yes | Auto Scheduled | Specification Review and Approval | 1 day | Wed 9/24/25 | Wed 9/24/25 | 441 | 6
443 | Yes | Auto Scheduled | Develop Technical design document | 2 days | Thu 9/25/25 | Fri 9/26/25 | 442 | 6
444 | Yes | Auto Scheduled | Specification Review and Approval | 1 day | Mon 9/29/25 | Mon 9/29/25 | 443 | 6
445 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Mon 9/29/25 | Mon 9/29/25 | 444 | 6
446 | Yes | Auto Scheduled | Develop | 14 days | Tue 9/30/25 | Fri 10/17/25 |  | 5
447 | Yes | Auto Scheduled | Perform initial development | 10 days | Tue 9/30/25 | Mon 10/13/25 | 445 | 6
448 | Yes | Auto Scheduled | Peer Review Code | 1 day | Tue 10/14/25 | Tue 10/14/25 | 447 | 6
449 | Yes | Auto Scheduled | Unit Test Code | 2 days | Wed 10/15/25 | Thu 10/16/25 | 448 | 6
450 | Yes | Auto Scheduled | Remediate Issues | 1 day | Fri 10/17/25 | Fri 10/17/25 | 449 | 6
451 | Yes | Auto Scheduled | Development Complete | 0 days | Fri 10/17/25 | Fri 10/17/25 | 450 | 6
452 | Yes | Auto Scheduled | Test | 3 days | Mon 10/20/25 | Wed 10/22/25 |  | 5
453 | Yes | Auto Scheduled | Perform Integrated Testing | 2 days | Mon 10/20/25 | Tue 10/21/25 | 451 | 6
454 | Yes | Auto Scheduled | Remediate Issues | 1 day | Wed 10/22/25 | Wed 10/22/25 | 453 | 6
455 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Wed 10/22/25 | Wed 10/22/25 | 454 | 6
456 | Yes | Auto Scheduled | Operational Reporting & Key Metrics | 44 days | Thu 7/03/25 | Tue 9/02/25 |  | 3
457 | Yes | Auto Scheduled | Define | 10 days | Thu 7/03/25 | Wed 7/16/25 |  | 4
458 | Yes | Auto Scheduled | Develop Functional specifications | 3 days | Thu 7/03/25 | Mon 7/07/25 | 306 | 5
459 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Tue 7/08/25 | Wed 7/09/25 | 458 | 5
460 | Yes | Auto Scheduled | Develop Technical design document | 3 days | Thu 7/10/25 | Mon 7/14/25 | 459 | 5
461 | Yes | Auto Scheduled | Specification Review and Approval | 2 days | Tue 7/15/25 | Wed 7/16/25 | 460 | 5
462 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Wed 7/16/25 | Wed 7/16/25 | 461 | 5
463 | Yes | Auto Scheduled | Develop | 29 days | Thu 7/17/25 | Tue 8/26/25 | 457 | 4
464 | Yes | Auto Scheduled | Perform initial development | 20 days | Thu 7/17/25 | Wed 8/13/25 | 462 | 5
465 | Yes | Auto Scheduled | Peer Review Code | 2 days | Thu 8/14/25 | Fri 8/15/25 | 464 | 5
466 | Yes | Auto Scheduled | Unit Test Code | 5 days | Mon 8/18/25 | Fri 8/22/25 | 465 | 5
467 | Yes | Auto Scheduled | Remediate Issues | 2 days | Mon 8/25/25 | Tue 8/26/25 | 466 | 5
468 | Yes | Auto Scheduled | Development Complete | 0 days | Tue 8/26/25 | Tue 8/26/25 | 467 | 5
469 | Yes | Auto Scheduled | Test | 5 days | Wed 8/27/25 | Tue 9/02/25 |  | 4
470 | Yes | Auto Scheduled | Perform Integrated Testing | 3 days | Wed 8/27/25 | Fri 8/29/25 | 468 | 5
471 | Yes | Auto Scheduled | Remediate Issues | 2 days | Mon 9/01/25 | Tue 9/02/25 | 470 | 5
472 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Tue 9/02/25 | Tue 9/02/25 | 471 | 5
473 | Yes | Auto Scheduled | Enterprise Identity Services | 15 days | Thu 7/03/25 | Wed 7/23/25 |  | 3
474 | Yes | Auto Scheduled | Define Requirements | 3 days | Thu 7/03/25 | Mon 7/07/25 | 306 | 4
475 | Yes | Auto Scheduled | Perform Tuning Round 3 | 9 days | Tue 7/08/25 | Fri 7/18/25 |  | 4
476 | Yes | Auto Scheduled | Load Initial Patient Extracts From Data Sources | 1 day | Tue 7/08/25 | Tue 7/08/25 | 474 | 5
477 | Yes | Auto Scheduled | Review Results | 5 days | Wed 7/09/25 | Tue 7/15/25 | 476 | 5
478 | Yes | Auto Scheduled | Modify Parameters | 3 days | Wed 7/16/25 | Fri 7/18/25 | 477 | 5
479 | Yes | Auto Scheduled | Test | 3 days | Mon 7/21/25 | Wed 7/23/25 |  | 4
480 | Yes | Auto Scheduled | Perform Integrated Testing | 2 days | Mon 7/21/25 | Tue 7/22/25 | 478 | 5
481 | Yes | Auto Scheduled | Remediate Issues | 1 day | Wed 7/23/25 | Wed 7/23/25 | 480 | 5
482 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Wed 7/23/25 | Wed 7/23/25 | 481 | 5
483 | Yes | Auto Scheduled | Medicaid Services - MCO Pilot | 47 days | Thu 7/03/25 | Fri 9/05/25 |  | 2
484 | Yes | Auto Scheduled | Define | 16 days | Thu 7/03/25 | Thu 7/24/25 |  | 3
485 | Yes | Auto Scheduled | Develop Functional specifications | 5 days | Thu 7/03/25 | Wed 7/09/25 | 306 | 4
486 | Yes | Auto Scheduled | Specification Review and Approval | 3 days | Thu 7/10/25 | Mon 7/14/25 | 485 | 4
487 | Yes | Auto Scheduled | Develop Technical design document | 5 days | Tue 7/15/25 | Mon 7/21/25 | 486 | 4
488 | Yes | Auto Scheduled | Specification Review and Approval | 3 days | Tue 7/22/25 | Thu 7/24/25 | 487 | 4
489 | Yes | Auto Scheduled | Publish Specifications and start Development | 0 days | Thu 7/24/25 | Thu 7/24/25 | 488 | 4
490 | Yes | Auto Scheduled | Develop | 29 days | Thu 7/17/25 | Tue 8/26/25 | 457 | 3
491 | Yes | Auto Scheduled | Perform initial development | 20 days | Thu 7/17/25 | Wed 8/13/25 | 462 | 4
492 | Yes | Auto Scheduled | Peer Review Code | 2 days | Thu 8/14/25 | Fri 8/15/25 | 491 | 4
493 | Yes | Auto Scheduled | Unit Test Code | 5 days | Mon 8/18/25 | Fri 8/22/25 | 492 | 4
494 | Yes | Auto Scheduled | Remediate Issues | 2 days | Mon 8/25/25 | Tue 8/26/25 | 493 | 4
495 | Yes | Auto Scheduled | Development Complete | 0 days | Tue 8/26/25 | Tue 8/26/25 | 494 | 4
496 | Yes | Auto Scheduled | Test | 8 days | Wed 8/27/25 | Fri 9/05/25 |  | 3
497 | Yes | Auto Scheduled | Perform Integrated Testing | 5 days | Wed 8/27/25 | Tue 9/02/25 | 495 | 4
498 | Yes | Auto Scheduled | Remediate Issues | 3 days | Wed 9/03/25 | Fri 9/05/25 | 497 | 4
499 | Yes | Auto Scheduled | Ready for UAT Testing | 0 days | Fri 9/05/25 | Fri 9/05/25 | 498 | 4
500 | Yes | Auto Scheduled | User Acceptance Testing | 29 days | Mon 5/04/26 | Thu 6/11/26 |  | 2
501 | Yes | Auto Scheduled | Finalize Test Plan | 3 days | Mon 5/04/26 | Wed 5/06/26 | 311;367;483 | 3
502 | Yes | Auto Scheduled | Execute Test Plan | 10 days | Thu 5/07/26 | Wed 5/20/26 | 501 | 3
503 | Yes | Auto Scheduled | Review Test Plan | 5 days | Thu 5/21/26 | Wed 5/27/26 | 502 | 3
504 | Yes | Auto Scheduled | Remediate Issues | 5 days | Thu 5/28/26 | Wed 6/03/26 | 503 | 3
505 | Yes | Auto Scheduled | Retest | 3 days | Thu 6/04/26 | Mon 6/08/26 | 504 | 3
506 | Yes | Auto Scheduled | Review Retest Results | 2 days | Tue 6/09/26 | Wed 6/10/26 | 505 | 3
507 | Yes | Auto Scheduled | Go Live Decision | 1 day | Thu 6/11/26 | Thu 6/11/26 | 506 | 3
508 | Yes | Auto Scheduled | Go-Live | 5 days | Fri 6/12/26 | Thu 6/18/26 |  | 2
509 | Yes | Auto Scheduled | Deploy Code | 2 days | Fri 6/12/26 | Mon 6/15/26 | 22;507 | 3
510 | Yes | Auto Scheduled | Perform Smoke Test | 3 days | Tue 6/16/26 | Thu 6/18/26 | 509 | 3
511 | Yes | Auto Scheduled | Declare System Live | 0 days | Thu 6/18/26 | Thu 6/18/26 | 510 | 3

## Resource_Table
ID | Indicators | Resource name | Type | Material label | Initials | Group | Max.Units | Std.Rate | Ovt.Rate | Cost/Use | Accrue At | Base Calendar | Code

## Assignment_Table
ID | Task name | Resource name | Work | Duration