## Project tasks
Project name | Attachment H: Initial Project Schedule
Project manager | Teresita Santiago
Project start date | 2024-06-03 09:00
Project finish date | 2027-05-05 17:00
Duration | 763 days
% complete | 0%
Exported on | 2024-03-13 16:10
Task number | Outline number | Name | HIE Assigned | PRPM Assign | Start | Finish | Deliverables | Depends on | % complete | Bucket | Dependents (after) | Effort | Effort completed | Effort remaining | Duration | Assigned to | Milestone | Notes | Completed | Checklist Items | Labels | Priority | Sprint | Goal | Duration hrs
1 | 1 | 1.0 Project Orientation and Planning | Project Manager |  | 2024-06-03 09:00 | 2024-06-28 17:00 |  |  | 0% | [5 empty] | 20 days |  | No |  |  |  |  | Medium
2 | 1.1 | 1.1 Kick-Off Meeting with PRMP | Project Manager |  | 2024-06-03 09:00 | 2024-06-12 17:00 | Kick-Off Meeting Summary |  | 0% | [5 empty] | 8 days |  | No |  |  |  |  | Medium
3 | 1.1.1 | 1.1.1 Plan Kick-Off Meeting | Project Manager | PRMP Coordinator | 2024-06-03 09:00 | 2024-06-03 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 1 day |  | No |  |  |  |  | Medium | Backlog
4 | 1.1.2 | 1.1.2 Conduct Kick-Off Meeting | Project Manager | PRMP Team | 2024-06-11 09:00 | 2024-06-11 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 1 day |  | No |  |  |  |  | Medium | Backlog
5 | 1.1.3 | 1.1.3 Document Meeting Summary | Project Manager |  | 2024-06-12 09:00 | 2024-06-12 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 1 day |  | No |  |  |  |  | Medium | Backlog
6 | 1.2 | 1.2 Develop Detailed Project Plan and WBS | Project Manager |  | 2024-06-17 09:00 | 2024-06-28 17:00 |  |  | 0% | [5 empty] | 10 days |  | No |  |  |  |  | Medium
7 | 1.2.1 | 1.2.1 Create Detailed Project Plan | Project Manager |  | 2024-06-17 09:00 | 2024-06-24 17:00 | Detailed Project Plan |  | 0% | Bucket 1 |  |  |  |  | 6 days |  | No |  |  |  |  | Medium | Backlog
8 | 1.2.2 | 1.2.2 Develop Work Breakdown Structure (WBS) | Project Manager |  | 2024-06-24 09:00 | 2024-06-26 17:00 | Work Breakdown Structure (WBS) |  | 0% | Bucket 1 |  |  |  |  | 3 days |  | No |  |  |  |  | Medium | Backlog
9 | 1.2.3 | 1.2.3 Review and Refine Project Plan | Project Manager |  | 2024-06-27 09:00 | 2024-06-28 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 2 days |  | No |  |  |  |  | Medium | Backlog
10 | 2 | 2.0 Data Migration Coordination | Project Manager |  | 2024-07-01 09:00 | 2024-08-09 17:00 | Data Migration Coordination Plan |  | 0% | [5 empty] | 30 days |  | No |  |  |  |  | Medium
11 | 2.1 | 2.1 Coordinate with Existing Vendors | Project Manager |  | 2024-07-01 09:00 | 2024-07-02 17:00 | Plan for Migration |  | 0% | Bucket 1 |  |  |  |  | 2 days |  | No |  |  |  |  | Medium | Backlog
12 | 2.2 | 2.2 Design and Implement Test Data Transfer | Integration Engineer |  | 2024-07-03 09:00 | 2024-07-05 17:00 | Test Scripts to validate transfer |  | 0% | Bucket 1 |  |  |  |  | 3 days |  | No |  |  |  |  | Medium | Backlog
13 | 2.3 | 2.3 Data Transfer | Technical Lead |  | 2024-07-08 09:00 | 2024-07-26 17:00 | Successfully transmit data |  | 0% | Bucket 1 |  |  |  |  | 15 days |  | No |  |  |  |  | Medium | Backlog
14 | 2.4 | 2.3 Data Transfer validation (Test) | Data Analyst |  | 2024-07-29 09:00 | 2024-08-09 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 10 days |  | No |  |  |  |  | Medium | Backlog
15 | 3 | 3.0 Team Training and Onboarding | Project Manager |  | 2024-08-09 09:00 | 2024-11-29 17:00 |  |  | 0% | [5 empty] | 81 days |  | No |  |  |  |  | Medium
16 | 3.1 | 3.1 Coordinate Onboarding Meeting | Project Manager |  | 2024-08-09 09:00 | 2024-08-09 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 1 day |  | No |  |  |  |  | Medium | Backlog
17 | 3.2 | 3.2 Onboarding Meeting | Project Manager | PRMP Coordinator | 2024-08-12 09:00 | 2024-08-12 17:00 | Coordinate Trainings |  | 0% | Bucket 1 |  |  |  |  | 1 day |  | No |  |  |  |  | Medium | Backlog
18 | 3.3 | 3.3 Training Material Creation | Project Manager |  | 2024-08-13 09:00 | 2024-08-23 17:00 | Training Material of HIE |  | 0% | Bucket 1 |  |  |  |  | 9 days |  | No |  |  |  |  | Medium | Backlog
19 | 3.4 | 3.3 Review of Training Materials |  | PRMP Coordinator | 2024-08-26 09:00 | 2024-08-30 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 5 days |  | No |  |  |  |  | Medium | Backlog
20 | 3.5 | 3.4 Coordinate Training Schedule |  |  | 2024-09-02 09:00 | 2024-09-06 17:00 | Schedule for Training Sessions |  | 0% | Bucket 1 |  |  |  |  | 5 days |  | No |  |  |  |  | Medium | Backlog
21 | 3.6 | 3.5 Begin Training Sessions for Project Team | Project Manager | Project Coordinator | 2024-09-09 09:00 | 2024-11-29 17:00 | Training Materials, Completion Reports |  | 0% | Bucket 1 |  |  |  |  | 60 days |  | No |  |  |  |  | Medium | Backlog
22 | 4 | 4.0 Pilot Data Access and Reporting Services | Project Manager |  | 2024-11-29 09:00 | 2025-07-18 17:00 |  |  | 0% | [5 empty] | 166 days |  | No |  |  |  |  | Medium
23 | 4.1 | 4.1 Users Access and Credentials | Operations Lead | PRMP Team | 2024-11-29 09:00 | 2024-12-12 17:00 | All users have access to HIE |  | 0% | Bucket 1 |  |  |  |  | 10 days |  | No |  |  |  |  | Medium | Backlog
24 | 4.2 | 4.2 Begin Accumulating Metrics Data for Outcomes | Network and Information Systems Management Lead |  | 2025-01-01 09:00 | 2025-06-30 17:00 | All data accumulation |  | 0% | Bucket 1 |  |  |  |  | 129 days |  | No |  |  |  |  | Medium | Backlog
25 | 4.3 | 4.3 Metrics Data Review | Data Analyst |  | 2025-07-01 09:00 | 2025-07-15 17:00 | Data collected and transmitted correctly |  | 0% | Bucket 1 |  |  |  |  | 11 days |  | No |  |  |  |  | Medium | Backlog
26 | 4.4 | 4.4 Metrics Data Report | Project Manager | PRPM Coordinator | 2025-07-16 09:00 | 2025-07-18 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 3 days |  | No |  |  |  |  | Medium | Backlog
27 | 5 | 5.0 Data Collection for CMS Certification | Project Manager |  | 2026-01-01 09:00 | 2026-04-15 17:00 |  |  | 0% | [5 empty] | 75 days |  | No |  |  |  |  | Medium
28 | 5.1 | 5.1 Accumulate Metrics Data for Outcomes | Network and Information Systems Management Lead |  | 2026-01-01 09:00 | 2026-03-31 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 64 days |  | No |  |  |  |  | Medium | Backlog
29 | 5.2 | 5.2 Data Review for Certification |  | PRMP Coordinator | 2026-04-01 09:00 | 2026-04-10 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 8 days |  | No |  |  |  |  | Medium | Backlog
30 | 5.3 | 5.3Certification Kick Off | Project Manager | PRMP Coordinator | 2026-04-13 09:00 | 2026-04-15 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 3 days |  | No |  |  |  |  | Medium | Backlog
31 | 6 | 6.0 HIE Operations Certification | Project Manager |  | 2026-04-01 09:00 | 2027-05-05 17:00 | Approval of OAPD |  | 0% | [5 empty] | 286 days |  | No |  |  |  |  | Medium
32 | 6.1 | 6.1 Assist on OAPD Submission to CMS | Project Manager | PRMP Coordinator | 2026-04-01 09:00 | 2026-04-17 17:00 | Gaining Access to Maintenance Funds |  | 0% | Bucket 1 |  |  |  |  | 13 days |  | No |  |  |  |  | Medium | Backlog
33 | 6.2 | 6.2 OAPD Subimission |  | PRMP Coordinator | 2026-04-20 09:00 | 2026-04-22 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 3 days |  | No |  |  |  |  | Medium | Backlog
34 | 6.3 | 6.2 OAPD Review |  | CMS | 2026-04-23 09:00 | 2027-05-05 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 270 days |  | No |  |  |  |  | Medium | Backlog
35 | 6.4 | 6.3 OAPD Approval |  | CMS | 2026-05-05 09:00 | 2026-05-08 17:00 | Certification Approval |  | 0% | Bucket 1 |  |  |  |  | 4 days |  | No |  |  |  |  | Medium | Backlog
36 | 7 | 7.0 OAPD Document Submission | Project Manager |  | 2026-04-01 09:00 | 2026-05-29 17:00 |  |  | 0% | [5 empty] | 43 days |  | No |  |  |  |  | Medium
37 | 7.1 | 7.1 Preparation of OAPD Documentation | Project Manager | PRPM Coordinator | 2026-04-01 09:00 | 2026-04-28 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 20 days |  | No |  |  |  |  | Medium | Backlog
38 | 7.2 | 7.2 Review of OAPD Document with PRPM |  | PRMP Team | 2026-04-29 09:00 | 2026-05-06 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 6 days |  | No |  |  |  |  | Medium | Backlog
39 | 7.3 | 7.3 Submission of OAPD Documents to CMS |  | PRMP Coordinator | 2026-05-07 09:00 | 2026-05-08 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 2 days |  | No |  |  |  |  | Medium | Backlog
40 | 7.4 | 7.4 CMS Reviews of OAPD Documents |  | CMS | 2026-05-11 09:00 | 2026-05-22 17:00 |  |  | 0% | Bucket 1 |  |  |  |  | 10 days |  | No |  |  |  |  | Medium | Backlog
41 | 7.5 | 7.4 CMS Approval of OAPD Documents |  | CMS | 2026-05-25 09:00 | 2026-05-29 17:00 | OAPD Documentation Approval |  | 0% | Bucket 1 |  |  |  |  | 5 days |  | No |  |  |  |  | Medium | Backlog