## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | PRHIE Project vNoRedv3 | 539.88 days | Mon 7/01/24 | Fri 7/24/26 |  | 0
1 | Yes | Auto Scheduled | Phase 1 - Post Award Development | 146.31 days | Mon 7/01/24 | Tue 1/21/25 |  | 1
2 | Yes | Auto Scheduled | Kick Off In-Person Meetings 1 (D03) | 134.25 days | Mon 7/01/24 | Fri 1/03/25 |  | 2 | Welcome and Introductions Acknowledgement of RFP Award Review of Contract Terms Project Kick-Off Communication Plan
3 | Yes | Auto Scheduled | Kick Off In-Person Meetings 2 (D03) | 2 days | Wed 7/03/24 | Fri 1/03/25 |  | 2 | Risk Management Project Scope and Deliverables Timeline and Milestones Monthly Status Report Exisiting Policy and Agreement Review Invoicing Next Steps and Closing Remarks
4 | Yes | Auto Scheduled | Project Initiation | 133.31 days | Thu 7/18/24 | Tue 1/21/25 | 2 | 2
5 | Yes | Auto Scheduled | Finalize Centralis Health Agreement with PRMP | 1.56 days | Fri 1/03/25 | Mon 1/06/25 |  | 3
6 | Yes | Auto Scheduled | Obtain and Review Final Contract from PRMP | 4 hrs | Fri 1/03/25 | Fri 1/03/25 |  | 4
7 | Yes | Auto Scheduled | Centralis Exectutive Review | 4 hrs | Fri 1/03/25 | Mon 1/06/25 | 6 | 4
8 | Yes | Auto Scheduled | Centralis Legal Review | 4 hrs | Mon 1/06/25 | Mon 1/06/25 | 7 | 4
9 | Yes | Auto Scheduled | Execute and Save Final Contract | 30 mins | Mon 1/06/25 | Mon 1/06/25 | 8 | 4
10 | Yes | Auto Scheduled | Invoicing | 0.5 days | Mon 1/06/25 | Tue 1/07/25 | 5 | 3
11 | Yes | Auto Scheduled | Add Approved Invoice Template to Quickbooks | 4 hrs | Mon 1/06/25 | Tue 1/07/25 |  | 4
12 | Yes | Auto Scheduled | Plans & Charter | 131.31 days | Mon 7/22/24 | Tue 1/21/25 | 10 | 3
13 | Yes | Auto Scheduled | D02: PRHIE Work Plan | 40 hrs | Tue 1/07/25 | Tue 1/14/25 |  | 4
14 | Yes | Manually Scheduled | D04 Implementation Plan | 20 hrs | Mon 7/22/24 | Wed 7/24/24 | 13 | 4
15 | Yes | Auto Scheduled | D01 Monthly Status Report | 40 hrs | Tue 1/14/25 | Tue 1/21/25 | 13;14 | 4
16 | Yes | Manually Scheduled | DIO: Training Management Plan | 20 hrs | Mon 8/05/24 | Wed 8/07/24 | 15 | 4
17 | Yes | Manually Scheduled | D08 Staffing Management Plan | 10 hrs | Wed 8/07/24 | Thu 8/08/24 | 16 | 4
18 | Yes | Auto Scheduled | D12: Disaster Recovery and Business Continuity Plan | 5 hrs | Tue 1/07/25 | Tue 1/07/25 | 17 | 4
19 | Yes | Auto Scheduled | Dll: Data Management Plan | 20 hrs | Wed 1/08/25 | Mon 1/13/25 | 18 | 4
20 | Yes | Auto Scheduled | D13: Public Health Systems Plan | 5 hrs | Mon 1/13/25 | Tue 1/14/25 | 19 | 4
21 | Yes | Manually Scheduled | D14: Pilot Implementation and Management Plan(s) | 10 hrs | Mon 8/12/24 | Tue 8/13/24 |  | 4
22 | Yes | Manually Scheduled | D15: Data Transition Plan | 20 hrs | Tue 7/30/24 | Thu 8/01/24 |  | 4
23 | Yes | Manually Scheduled | D06 Operations Management Plan | 40 hrs | Mon 8/05/24 | Fri 8/09/24 |  | 4
24 | Yes | Auto Scheduled | Finalize and Adopt Polices and Agreements | 132.5 days | Thu 7/18/24 | Mon 1/20/25 |  | 3
25 | Yes | Auto Scheduled | Healthcare Providers User Agreement | 1 day | Mon 1/13/25 | Mon 1/13/25 |  | 4
26 | Yes | Auto Scheduled | Statement of HIPAA Compliance | 1 day | Tue 1/14/25 | Tue 1/14/25 | 25 | 4
27 | Yes | Auto Scheduled | Privacy Policy | 1 day | Wed 1/15/25 | Wed 1/15/25 | 26 | 4
28 | Yes | Auto Scheduled | Terms of Use | 1 day | Thu 1/16/25 | Thu 1/16/25 | 27 | 4
29 | Yes | Auto Scheduled | ENS FEE Schedule | 0.5 days | Fri 1/17/25 | Fri 1/17/25 | 28 | 4 | 7,500 Patient panel sponsored by PRMP
30 | Yes | Auto Scheduled | HIE Participant Agreement | 1 day | Fri 1/17/25 | Mon 1/20/25 | 29 | 4
31 | Yes | Manually Scheduled | D07: Security, Privacy, and Confidentiality Plan | 10 days | Thu 7/18/24 | Wed 7/31/24 |  | 4
32 | Yes | Manually Scheduled | D09: Incident Management Plan | 3 days | Mon 8/12/24 | Wed 8/14/24 |  | 4
33 | Yes | Auto Scheduled | Existing Participant Engagment | 3.75 days | Mon 8/12/24 | Thu 8/15/24 | 4 | 2
34 | Yes | Manually Scheduled | D05: HIE Participant Engagement and Technical Assistance Plan | 30 hrs | Mon 8/12/24 | Thu 8/15/24 |  | 3
35 | Yes | Auto Scheduled | Update Participant Agreements | 18.5 days | Tue 8/13/24 | Fri 9/06/24 | 33 | 2
36 | Yes | Auto Scheduled | Hospital/Clinic 1 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 |  | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
37 | Yes | Auto Scheduled | Hospital/Clinic 2 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 36 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
38 | Yes | Auto Scheduled | Hospital/Clinic 3 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 37 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
39 | Yes | Auto Scheduled | Hospital/Clinic 4 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 38 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
40 | Yes | Auto Scheduled | Hospital/Clinic 5 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 39 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
41 | Yes | Auto Scheduled | Hospital/Clinic 6 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 40 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
42 | Yes | Auto Scheduled | Hospital/Clinic 7 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 41 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
43 | Yes | Auto Scheduled | Hospital/Clinic 8 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 42 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
44 | Yes | Auto Scheduled | Hospital/Clinic 9 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 43 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
45 | Yes | Auto Scheduled | Hospital/Clinic 10 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 44 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
46 | Yes | Auto Scheduled | Hospital/Clinic 11 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 45 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
47 | Yes | Auto Scheduled | Hospital/Clinic 12 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 46 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
48 | Yes | Auto Scheduled | Hospital/Clinic 13 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 47 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
49 | Yes | Auto Scheduled | Hospital/Clinic 14 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 48 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
50 | Yes | Auto Scheduled | Hospital/Clinic 15 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 49 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
51 | Yes | Auto Scheduled | Hospital/Clinic 16 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 50 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
52 | Yes | Auto Scheduled | Hospital/Clinic 17 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 51 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
53 | Yes | Auto Scheduled | Hospital/Clinic 18 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 52 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
54 | Yes | Auto Scheduled | Hospital/Clinic 19 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 53 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
55 | Yes | Auto Scheduled | Hospital/Clinic 20 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 54 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
56 | Yes | Auto Scheduled | Hospital/Clinic 21 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 55 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
57 | Yes | Auto Scheduled | Hospital/Clinic 22 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 56 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
58 | Yes | Auto Scheduled | Hospital/Clinic 23 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 57 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
59 | Yes | Auto Scheduled | Hospital/Clinic 24 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 58 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
60 | Yes | Auto Scheduled | Hospital/Clinic 25 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 59 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
61 | Yes | Auto Scheduled | Hospital/Clinic 26 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 60 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
62 | Yes | Auto Scheduled | Hospital/Clinic 27 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 61 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
63 | Yes | Auto Scheduled | Hospital/Clinic 28 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 62 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
64 | Yes | Auto Scheduled | Hospital/Clinic 29 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 63 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
65 | Yes | Auto Scheduled | Hospital/Clinic 30 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 64 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
66 | Yes | Auto Scheduled | Hospital/Clinic 31 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 65 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
67 | Yes | Auto Scheduled | Hospital/Clinic 32 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 66 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
68 | Yes | Auto Scheduled | Hospital/Clinic 33 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 67 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
69 | Yes | Auto Scheduled | Hospital/Clinic 34 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 68 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
70 | Yes | Auto Scheduled | Hospital/Clinic 35 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 69 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
71 | Yes | Auto Scheduled | Hospital/Clinic 36 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 70 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
72 | Yes | Auto Scheduled | Hospital/Clinic 37 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 71 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
73 | Yes | Auto Scheduled | Hospital/Clinic 38 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 72 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
74 | Yes | Auto Scheduled | Hospital/Clinic 39 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 73 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
75 | Yes | Auto Scheduled | Hospital/Clinic 40 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 74 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
76 | Yes | Auto Scheduled | Hospital/Clinic 41 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 75 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
77 | Yes | Auto Scheduled | Hospital/Clinic 42 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 76 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
78 | Yes | Auto Scheduled | Hospital/Clinic 43 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 77 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
79 | Yes | Auto Scheduled | Hospital/Clinic 44 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 78 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
80 | Yes | Auto Scheduled | Hospital/Clinic 45 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 79 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
81 | Yes | Auto Scheduled | Hospital/Clinic 46 | 0 hrs | Thu 8/15/24 | Thu 8/15/24 | 80 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
82 | Yes | Manually Scheduled | Hospital/Clinic 47 | 3 hrs | Tue 8/13/24 | Tue 8/13/24 |  | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
83 | Yes | Auto Scheduled | Hospital/Clinic 48 | 3 hrs | Thu 8/15/24 | Fri 8/16/24 | 82 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
84 | Yes | Auto Scheduled | Hospital/Clinic 49 | 3 hrs | Fri 8/16/24 | Fri 8/16/24 | 83 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
85 | Yes | Auto Scheduled | Hospital/Clinic 50 | 3 hrs | Fri 8/16/24 | Fri 8/16/24 | 84 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
86 | Yes | Auto Scheduled | Hospital/Clinic 51 | 3 hrs | Fri 8/16/24 | Mon 8/19/24 | 85 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
87 | Yes | Auto Scheduled | Hospital/Clinic 52 | 3 hrs | Mon 8/19/24 | Mon 8/19/24 | 86 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
88 | Yes | Auto Scheduled | Hospital/Clinic 53 | 3 hrs | Mon 8/19/24 | Mon 8/19/24 | 87 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
89 | Yes | Auto Scheduled | Hospital/Clinic 54 | 3 hrs | Tue 8/20/24 | Tue 8/20/24 | 88 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
90 | Yes | Auto Scheduled | Hospital/Clinic 55 | 3 hrs | Tue 8/20/24 | Tue 8/20/24 | 89 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
91 | Yes | Auto Scheduled | Hospital/Clinic 56 | 3 hrs | Tue 8/20/24 | Wed 8/21/24 | 90 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
92 | Yes | Auto Scheduled | Hospital/Clinic 57 | 3 hrs | Wed 8/21/24 | Wed 8/21/24 | 91 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
93 | Yes | Auto Scheduled | Hospital/Clinic 58 | 3 hrs | Wed 8/21/24 | Wed 8/21/24 | 92 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
94 | Yes | Auto Scheduled | Hospital/Clinic 59 | 3 hrs | Wed 8/21/24 | Thu 8/22/24 | 93 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
95 | Yes | Auto Scheduled | Hospital/Clinic 60 | 3 hrs | Thu 8/22/24 | Thu 8/22/24 | 94 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
96 | Yes | Auto Scheduled | Hospital/Clinic 61 | 3 hrs | Thu 8/22/24 | Thu 8/22/24 | 95 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
97 | Yes | Auto Scheduled | Hospital/Clinic 62 | 3 hrs | Fri 8/23/24 | Fri 8/23/24 | 96 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
98 | Yes | Auto Scheduled | Hospital/Clinic 63 | 3 hrs | Fri 8/23/24 | Fri 8/23/24 | 97 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
99 | Yes | Auto Scheduled | Centros 330_FQHC 1 | 3 hrs | Fri 8/23/24 | Mon 8/26/24 | 98 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
100 | Yes | Auto Scheduled | Centros 330_FQHC 2 | 3 hrs | Mon 8/26/24 | Mon 8/26/24 | 99 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
101 | Yes | Auto Scheduled | Centros 330_FQHC 3 | 3 hrs | Mon 8/26/24 | Mon 8/26/24 | 100 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
102 | Yes | Auto Scheduled | Centros 330_FQHC 4 | 3 hrs | Mon 8/26/24 | Tue 8/27/24 | 101 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
103 | Yes | Auto Scheduled | Centros 330_FQHC 5 | 3 hrs | Tue 8/27/24 | Tue 8/27/24 | 102 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
104 | Yes | Auto Scheduled | Centros 330_FQHC 6 | 3 hrs | Tue 8/27/24 | Tue 8/27/24 | 103 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
105 | Yes | Auto Scheduled | Centros 330_FQHC 7 | 3 hrs | Wed 8/28/24 | Wed 8/28/24 | 104 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
106 | Yes | Auto Scheduled | Centros 330_FQHC 8 | 3 hrs | Wed 8/28/24 | Wed 8/28/24 | 105 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
107 | Yes | Auto Scheduled | Centros 330_FQHC 9 | 3 hrs | Wed 8/28/24 | Thu 8/29/24 | 106 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
108 | Yes | Auto Scheduled | Centros 330_FQHC 10 | 3 hrs | Thu 8/29/24 | Thu 8/29/24 | 107 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
109 | Yes | Auto Scheduled | Centros 330_FQHC 11 | 3 hrs | Thu 8/29/24 | Thu 8/29/24 | 108 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
110 | Yes | Auto Scheduled | Centros 330_FQHC 12 | 3 hrs | Thu 8/29/24 | Fri 8/30/24 | 109 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
111 | Yes | Auto Scheduled | Centros 330_FQHC 13 | 3 hrs | Fri 8/30/24 | Fri 8/30/24 | 110 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
112 | Yes | Auto Scheduled | Centros 330_FQHC 14 | 3 hrs | Fri 8/30/24 | Fri 8/30/24 | 111 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
113 | Yes | Auto Scheduled | Centros 330_FQHC 15 | 3 hrs | Mon 9/02/24 | Mon 9/02/24 | 112 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
114 | Yes | Auto Scheduled | Centros 330_FQHC 16 | 3 hrs | Mon 9/02/24 | Mon 9/02/24 | 113 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
115 | Yes | Auto Scheduled | Centros 330_FQHC 17 | 3 hrs | Mon 9/02/24 | Tue 9/03/24 | 114 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
116 | Yes | Auto Scheduled | LIMS 1 | 3 hrs | Tue 9/03/24 | Tue 9/03/24 | 115 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
117 | Yes | Auto Scheduled | LIMS 2 | 3 hrs | Tue 9/03/24 | Tue 9/03/24 | 116 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
118 | Yes | Auto Scheduled | LIMS 3 | 3 hrs | Tue 9/03/24 | Wed 9/04/24 | 117 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
119 | Yes | Auto Scheduled | LIMS 4 | 3 hrs | Wed 9/04/24 | Wed 9/04/24 | 118 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
120 | Yes | Auto Scheduled | LIMS 5 | 3 hrs | Wed 9/04/24 | Wed 9/04/24 | 119 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
121 | Yes | Auto Scheduled | LIMS 6 | 3 hrs | Thu 9/05/24 | Thu 9/05/24 | 120 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
122 | Yes | Auto Scheduled | LIMS 7 | 3 hrs | Thu 9/05/24 | Thu 9/05/24 | 121 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
123 | Yes | Auto Scheduled | LIMS 8 | 3 hrs | Thu 9/05/24 | Fri 9/06/24 | 122 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
124 | Yes | Auto Scheduled | Radiology Facility | 3 hrs | Fri 9/06/24 | Fri 9/06/24 | 123 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
125 | Yes | Manually Scheduled | Existing Participant Engagement Complete | 0 days | Fri 9/06/24 | Fri 9/06/24 |  | 3
126 | Yes | Auto Scheduled | Phase 2 - Hisorical Data/Interface Transition, MCO Pilot, MES | 177.31 days | Fri 8/02/24 | Tue 4/08/25 | 1 | 1
127 | Yes | Auto Scheduled | Historical Data Transfer (D15) | 60 days | Fri 8/02/24 | Fri 10/25/24 |  | 2
128 | Yes | Manually Scheduled | Introductions to Health Gorilla | 0.5 days | Mon 8/12/24 | Mon 8/12/24 |  | 3
129 | Yes | Manually Scheduled | Establish Technical Contact with Health Gorilla | 1 day | Fri 8/02/24 | Fri 8/02/24 |  | 3
130 | Yes | Manually Scheduled | Data Transfer Test | 3 days | Mon 8/05/24 | Wed 8/07/24 | 128;129 | 3
131 | Yes | Manually Scheduled | Validate Data | 3 days | Tue 8/13/24 | Thu 8/15/24 | 130 | 3
132 | Yes | Manually Scheduled | Commense Historical Data Transfer and Integration | 49 days | Mon 8/19/24 | Thu 10/24/24 | 131 | 3
133 | Yes | Manually Scheduled | Histroical Data Transfer and Intifigraton | 0 days | Fri 10/25/24 | Fri 10/25/24 |  | 3 | Historical data transferred from Health Gorilla is now available within the Centralis Health web portal to be viewed in the HIE
134 | Yes | Manually Scheduled | MES HIE Certification - Kick Off | 76.38 days | Mon 9/02/24 | Tue 12/17/24 |  | 2
135 | Yes | Auto Scheduled | Medicaid Benefitciary Roster | 11 days | Mon 9/02/24 | Mon 9/16/24 |  | 3
136 | Yes | Auto Scheduled | Establish process to obtain active MCO monthly beneficiary roster(Centralis Health Gateway or SFTP) | 0.25 days | Mon 9/02/24 | Mon 9/02/24 |  | 4
137 | Yes | Auto Scheduled | Build PRMP Medicaid Beneficiary Respository | 0.25 days | Mon 9/02/24 | Mon 9/02/24 | 136 | 4 | This step builds the shell of the PRMP Medicaid Beneficiary Respository, allowing for the flow of data and population of records
138 | Yes | Auto Scheduled | Test File Upload, Receipt, and Load to Repository | 0.5 days | Mon 9/02/24 | Mon 9/02/24 | 137 | 4 | This phase will test the upload process from PRMP, Centralis Health to confirm Receipt and load of beneficiary data into repository.
139 | Yes | Auto Scheduled | Generate Unique Patient ID for Medicaid Beneficiares | 3 days | Tue 9/03/24 | Thu 9/05/24 | 138 | 4 | This phase will start the process of filling out the PRMP Medicaid Beneficiary repository.
140 | Yes | Auto Scheduled | PRMP to Review and Approve Load | 0.5 days | Fri 9/06/24 | Fri 9/06/24 | 139 | 4 | During this phase PRMP designess, with the help of Centralis Health, will log into Centralis Health web portal to view the display of the loaded data in the HIE. Once approved scheduled loads can be established
141 | Yes | Auto Scheduled | Establish Beneficiary Roster Upload Schedule | 0.5 days | Fri 9/06/24 | Fri 9/06/24 | 140 | 4 | Establish day of the monthy PRMP will upload roster to Centralis Health for repository population
142 | Yes | Auto Scheduled | Population of PRMP Beneficiary Repository Logitudinal Records with Historical Data | 5 days | Tue 9/10/24 | Mon 9/16/24 | 141 | 4 | This will begin the process of expanding PRMP Medicaid Beneficiatry Respository from only PRMP roster data to patient records matched from PRHIE larger patient repositories. -This is done by leveraging PRHIE MPI to match patients in PRHIE Clinical Reporistories and duplicating records for PRMP use in the PRMP Medicaid Beneficiary Respository
143 | Yes | Auto Scheduled | MES User Initiation | 50 days | Mon 9/16/24 | Tue 11/26/24 | 135 | 3
144 | Yes | Auto Scheduled | User Credentialing and Setup | 0 days | Mon 9/16/24 | Mon 9/16/24 |  | 4
145 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0 days | Mon 9/16/24 | Mon 9/16/24 |  | 5 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
146 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 0 days | Mon 9/16/24 | Mon 9/16/24 | 145 | 5 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
147 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 0 days | Mon 9/16/24 | Mon 9/16/24 | 146 | 5
148 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 0 days | Mon 9/16/24 | Mon 9/16/24 | 147 | 5
149 | Yes | Auto Scheduled | System Training, Testing, and Validation | 17 days | Fri 11/01/24 | Tue 11/26/24 | 144 | 4
150 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Fri 11/01/24 | Fri 11/01/24 |  | 5
151 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Fri 11/01/24 | Fri 11/01/24 | 150 | 5
152 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Fri 11/01/24 | Fri 11/01/24 | 151 | 5
153 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Fri 11/01/24 | Fri 11/01/24 | 152 | 5
154 | Yes | Manually Scheduled | MES Kickoff Complete | 0 days | Tue 11/26/24 | Tue 11/26/24 |  | 5 | By this point in the contract we have established a process to tramit montly Active Medicaid Beneficiary Rosters leveraging the Centralis Health Gateway application. Leveraging those lists have begun populating the PRMP Medicaid Repository. By 11 one the historical data transferred from Health Gorilla to Centralis Health is no avilable for PRMP staff to view in the web portal, staff has been onboarded and trained to access accordingly.
155 | Yes | Auto Scheduled | Begin Interface Transition | 84.56 days | Mon 10/07/24 | Fri 1/31/25 |  | 2 | Re-establish interfaces with all currently connected data sources (ie, Hospitals, clinics, lab, etc). This maybe require new VPNS and active participation for the data source and/or EMR vendor. We assumed 198 feeds based on Health Gorillas-Integration Overview_PRHIE 2023 from the HIE Procurement Libary.
156 | Yes | Auto Scheduled | ADT 1 | 5 hrs | Tue 1/21/25 | Wed 1/22/25 |  | 3
157 | Yes | Auto Scheduled | ADT 2 | 5 hrs | Wed 1/22/25 | Thu 1/23/25 | 156 | 3
158 | Yes | Auto Scheduled | ADT 3 | 5 hrs | Thu 1/23/25 | Thu 1/23/25 | 157 | 3
159 | Yes | Auto Scheduled | ADT 4 | 5 hrs | Thu 1/23/25 | Fri 1/24/25 | 158 | 3
160 | Yes | Auto Scheduled | ADT 5 | 5 hrs | Fri 1/24/25 | Mon 1/27/25 | 159 | 3
161 | Yes | Auto Scheduled | ADT 6 | 5 hrs | Mon 1/27/25 | Tue 1/28/25 | 160 | 3
162 | Yes | Auto Scheduled | ADT 7 | 5 hrs | Tue 1/28/25 | Wed 1/29/25 | 161 | 3
163 | Yes | Auto Scheduled | ADT 8 | 5 hrs | Wed 1/29/25 | Thu 1/30/25 | 162 | 3
164 | Yes | Auto Scheduled | ADT 9 | 5 hrs | Thu 1/30/25 | Thu 1/30/25 | 163 | 3
165 | Yes | Auto Scheduled | ADT 10 | 5 hrs | Thu 1/30/25 | Fri 1/31/25 | 164 | 3
166 | Yes | Auto Scheduled | ADT 11 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 165 | 3
167 | Yes | Auto Scheduled | ADT 12 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 166 | 3
168 | Yes | Auto Scheduled | ADT 13 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 167 | 3
169 | Yes | Auto Scheduled | ADT 14 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 168 | 3
170 | Yes | Auto Scheduled | ADT 15 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 169 | 3
171 | Yes | Auto Scheduled | ADT 16 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 170 | 3
172 | Yes | Auto Scheduled | ADT 17 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 171 | 3
173 | Yes | Auto Scheduled | ADT 18 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 172 | 3
174 | Yes | Auto Scheduled | ADT 19 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 173 | 3
175 | Yes | Auto Scheduled | ADT 20 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 174 | 3
176 | Yes | Auto Scheduled | ADT 21 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 175 | 3
177 | Yes | Auto Scheduled | ADT 22 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 176 | 3
178 | Yes | Auto Scheduled | ADT 23 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 177 | 3
179 | Yes | Auto Scheduled | ADT 24 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 178 | 3
180 | Yes | Auto Scheduled | ADT 25 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 179 | 3
181 | Yes | Auto Scheduled | ADT 26 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 180 | 3
182 | Yes | Auto Scheduled | ADT 27 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 181 | 3
183 | Yes | Auto Scheduled | ADT 28 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 182 | 3
184 | Yes | Auto Scheduled | ADT 29 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 183 | 3
185 | Yes | Auto Scheduled | ADT 30 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 184 | 3
186 | Yes | Auto Scheduled | ADT 31 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 185 | 3
187 | Yes | Auto Scheduled | ADT 32 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 186 | 3
188 | Yes | Auto Scheduled | ADT 33 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 187 | 3
189 | Yes | Auto Scheduled | ADT 34 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 188 | 3
190 | Yes | Auto Scheduled | ADT 35 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 189 | 3
191 | Yes | Auto Scheduled | ADT 36 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 190 | 3
192 | Yes | Auto Scheduled | ADT 37 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 191 | 3
193 | Yes | Auto Scheduled | ADT 38 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 192 | 3
194 | Yes | Auto Scheduled | ADT 39 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 193 | 3
195 | Yes | Auto Scheduled | ADT 40 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 194 | 3
196 | Yes | Auto Scheduled | ADT 41 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 195 | 3
197 | Yes | Auto Scheduled | ADT 42 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 196 | 3
198 | Yes | Auto Scheduled | ADT 43 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 197 | 3
199 | Yes | Auto Scheduled | ADT 44 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 198 | 3
200 | Yes | Auto Scheduled | ADT 45 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 199 | 3
201 | Yes | Auto Scheduled | ADT 46 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 200 | 3
202 | Yes | Auto Scheduled | ADT 47 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 201 | 3
203 | Yes | Auto Scheduled | ADT 48 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 202 | 3
204 | Yes | Auto Scheduled | ADT 49 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 203 | 3
205 | Yes | Auto Scheduled | ADT 50 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 204 | 3
206 | Yes | Auto Scheduled | ADT 51 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 205 | 3
207 | Yes | Auto Scheduled | ADT 52 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 206 | 3
208 | Yes | Auto Scheduled | CCDA 1 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 207 | 3
209 | Yes | Auto Scheduled | CCDA 2 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 208 | 3
210 | Yes | Auto Scheduled | CCDA 3 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 209 | 3
211 | Yes | Auto Scheduled | CCDA 4 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 210 | 3
212 | Yes | Auto Scheduled | CCDA 5 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 211 | 3
213 | Yes | Auto Scheduled | CCDA 6 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 212 | 3
214 | Yes | Auto Scheduled | CCDA 7 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 213 | 3
215 | Yes | Auto Scheduled | CCDA 8 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 214 | 3
216 | Yes | Auto Scheduled | CCDA 9 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 215 | 3
217 | Yes | Auto Scheduled | CCDA 10 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 216 | 3
218 | Yes | Auto Scheduled | CCDA 11 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 217 | 3
219 | Yes | Auto Scheduled | CCDA 12 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 218 | 3
220 | Yes | Auto Scheduled | CCDA 13 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 219 | 3
221 | Yes | Auto Scheduled | CCDA 14 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 220 | 3
222 | Yes | Auto Scheduled | CCDA 15 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 221 | 3
223 | Yes | Auto Scheduled | CCDA 16 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 222 | 3
224 | Yes | Auto Scheduled | CCDA 17 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 223 | 3
225 | Yes | Auto Scheduled | CCDA 18 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 224 | 3
226 | Yes | Auto Scheduled | CCDA 19 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 225 | 3
227 | Yes | Auto Scheduled | CCDA 20 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 226 | 3
228 | Yes | Auto Scheduled | CCDA 21 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 227 | 3
229 | Yes | Auto Scheduled | CCDA 22 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 228 | 3
230 | Yes | Auto Scheduled | CCDA 23 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 229 | 3
231 | Yes | Auto Scheduled | CCDA 24 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 230 | 3
232 | Yes | Auto Scheduled | CCDA 25 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 231 | 3
233 | Yes | Auto Scheduled | CCDA 26 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 232 | 3
234 | Yes | Auto Scheduled | CCDA 27 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 233 | 3
235 | Yes | Auto Scheduled | CCDA 28 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 234 | 3
236 | Yes | Auto Scheduled | CCDA 29 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 235 | 3
237 | Yes | Auto Scheduled | CCDA 30 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 236 | 3
238 | Yes | Auto Scheduled | CCDA 31 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 237 | 3
239 | Yes | Auto Scheduled | CCDA 32 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 238 | 3
240 | Yes | Auto Scheduled | CCDA 33 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 239 | 3
241 | Yes | Auto Scheduled | CCDA 34 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 240 | 3
242 | Yes | Auto Scheduled | CCDA 35 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 241 | 3
243 | Yes | Auto Scheduled | CCDA 36 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 242 | 3
244 | Yes | Auto Scheduled | CCDA 37 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 243 | 3
245 | Yes | Auto Scheduled | CCDA 38 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 244 | 3
246 | Yes | Auto Scheduled | CCDA 39 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 245 | 3
247 | Yes | Auto Scheduled | CCDA 40 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 246 | 3
248 | Yes | Auto Scheduled | CCDA 41 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 247 | 3
249 | Yes | Auto Scheduled | CCDA 42 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 248 | 3
250 | Yes | Auto Scheduled | CCDA 43 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 249 | 3
251 | Yes | Auto Scheduled | CCDA 44 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 250 | 3
252 | Yes | Auto Scheduled | CCDA 45 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 251 | 3
253 | Yes | Manually Scheduled | CCDA 46 | 5 hrs | Mon 10/07/24 | Mon 10/07/24 |  | 3
254 | Yes | Auto Scheduled | CCDA 47 | 5 hrs | Tue 1/21/25 | Wed 1/22/25 | 253 | 3
255 | Yes | Auto Scheduled | CCDA 48 | 5 hrs | Wed 1/22/25 | Thu 1/23/25 | 254 | 3
256 | Yes | Auto Scheduled | CCDA 49 | 5 hrs | Thu 1/23/25 | Thu 1/23/25 | 255 | 3
257 | Yes | Auto Scheduled | CCDA 50 | 5 hrs | Thu 1/23/25 | Fri 1/24/25 | 256 | 3
258 | Yes | Auto Scheduled | CCDA 51 | 5 hrs | Fri 1/24/25 | Mon 1/27/25 | 257 | 3
259 | Yes | Auto Scheduled | CCDA 52 | 5 hrs | Mon 1/27/25 | Tue 1/28/25 | 258 | 3
260 | Yes | Auto Scheduled | CCDA 53 | 5 hrs | Tue 1/28/25 | Wed 1/29/25 | 259 | 3
261 | Yes | Auto Scheduled | Lab 1 | 5 hrs | Wed 1/29/25 | Thu 1/30/25 | 260 | 3
262 | Yes | Auto Scheduled | Lab 2 | 5 hrs | Thu 1/30/25 | Thu 1/30/25 | 261 | 3
263 | Yes | Auto Scheduled | Lab 3 | 5 hrs | Thu 1/30/25 | Fri 1/31/25 | 262 | 3
264 | Yes | Auto Scheduled | Lab 4 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 263 | 3
265 | Yes | Auto Scheduled | Lab 5 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 264 | 3
266 | Yes | Auto Scheduled | Lab 6 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 265 | 3
267 | Yes | Auto Scheduled | Lab 7 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 266 | 3
268 | Yes | Auto Scheduled | Lab 8 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 267 | 3
269 | Yes | Auto Scheduled | Lab 9 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 268 | 3
270 | Yes | Auto Scheduled | Lab 10 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 269 | 3
271 | Yes | Auto Scheduled | Lab 11 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 270 | 3
272 | Yes | Auto Scheduled | Lab 12 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 271 | 3
273 | Yes | Auto Scheduled | Lab 13 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 272 | 3
274 | Yes | Auto Scheduled | Lab 14 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 273 | 3
275 | Yes | Auto Scheduled | Lab 15 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 274 | 3
276 | Yes | Auto Scheduled | Lab 16 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 275 | 3
277 | Yes | Auto Scheduled | Lab 17 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 276 | 3
278 | Yes | Auto Scheduled | Lab 18 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 277 | 3
279 | Yes | Auto Scheduled | Lab 19 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 278 | 3
280 | Yes | Auto Scheduled | Lab 20 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 279 | 3
281 | Yes | Auto Scheduled | Lab 21 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 280 | 3
282 | Yes | Auto Scheduled | Lab 22 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 281 | 3
283 | Yes | Auto Scheduled | Lab 23 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 282 | 3
284 | Yes | Auto Scheduled | Lab 24 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 283 | 3
285 | Yes | Auto Scheduled | Lab 25 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 284 | 3
286 | Yes | Auto Scheduled | Lab 26 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 285 | 3
287 | Yes | Auto Scheduled | Lab 27 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 286 | 3
288 | Yes | Auto Scheduled | Lab 28 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 287 | 3
289 | Yes | Auto Scheduled | Lab 29 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 288 | 3
290 | Yes | Auto Scheduled | Lab 30 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 289 | 3
291 | Yes | Auto Scheduled | Lab 31 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 290 | 3
292 | Yes | Auto Scheduled | Lab 32 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 291 | 3
293 | Yes | Auto Scheduled | Lab 33 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 292 | 3
294 | Yes | Auto Scheduled | Lab 34 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 293 | 3
295 | Yes | Auto Scheduled | Lab 35 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 294 | 3
296 | Yes | Auto Scheduled | Lab 36 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 295 | 3
297 | Yes | Auto Scheduled | Lab 37 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 296 | 3
298 | Yes | Auto Scheduled | Lab 38 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 297 | 3
299 | Yes | Auto Scheduled | Lab 39 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 298 | 3
300 | Yes | Auto Scheduled | Lab 40 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 299 | 3
301 | Yes | Auto Scheduled | Lab 41 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 300 | 3
302 | Yes | Auto Scheduled | Lab 42 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 301 | 3
303 | Yes | Auto Scheduled | Lab 43 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 302 | 3
304 | Yes | Auto Scheduled | Lab 44 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 303 | 3
305 | Yes | Auto Scheduled | Lab 45 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 304 | 3
306 | Yes | Auto Scheduled | Lab 46 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 305 | 3
307 | Yes | Auto Scheduled | Lab 47 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 306 | 3
308 | Yes | Auto Scheduled | Lab 48 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 307 | 3
309 | Yes | Auto Scheduled | Lab 49 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 308 | 3
310 | Yes | Auto Scheduled | Lab 50 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 309 | 3
311 | Yes | Auto Scheduled | Lab 51 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 310 | 3
312 | Yes | Auto Scheduled | Lab 52 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 311 | 3
313 | Yes | Auto Scheduled | Lab 53 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 312 | 3
314 | Yes | Auto Scheduled | Lab 54 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 313 | 3
315 | Yes | Auto Scheduled | Lab 55 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 314 | 3
316 | Yes | Auto Scheduled | Lab 56 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 315 | 3
317 | Yes | Auto Scheduled | Lab 57 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 316 | 3
318 | Yes | Auto Scheduled | Lab 58 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 317 | 3
319 | Yes | Auto Scheduled | Lab 59 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 318 | 3
320 | Yes | Auto Scheduled | Rad 1 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 319 | 3
321 | Yes | Auto Scheduled | Rad 2 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 320 | 3
322 | Yes | Auto Scheduled | Rad 3 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 321 | 3
323 | Yes | Auto Scheduled | Rad 4 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 322 | 3
324 | Yes | Auto Scheduled | Rad 5 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 323 | 3
325 | Yes | Auto Scheduled | Rad 6 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 324 | 3
326 | Yes | Auto Scheduled | Rad 7 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 325 | 3
327 | Yes | Auto Scheduled | Rad 8 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 326 | 3
328 | Yes | Auto Scheduled | Rad 9 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 327 | 3
329 | Yes | Auto Scheduled | Rad 10 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 328 | 3
330 | Yes | Auto Scheduled | Rad 11 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 329 | 3
331 | Yes | Auto Scheduled | Rad 12 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 330 | 3
332 | Yes | Auto Scheduled | Rad 13 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 331 | 3
333 | Yes | Auto Scheduled | Rad 14 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 332 | 3
334 | Yes | Auto Scheduled | Rad 15 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 333 | 3
335 | Yes | Auto Scheduled | Rad 16 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 334 | 3
336 | Yes | Auto Scheduled | Rad 17 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 335 | 3
337 | Yes | Auto Scheduled | Rad 18 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 336 | 3
338 | Yes | Auto Scheduled | Rad 19 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 337 | 3
339 | Yes | Auto Scheduled | Rad 20 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 338 | 3
340 | Yes | Auto Scheduled | Rad 21 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 339 | 3
341 | Yes | Auto Scheduled | Rad 22 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 340 | 3
342 | Yes | Auto Scheduled | Rad 23 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 341 | 3
343 | Yes | Auto Scheduled | Rad 24 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 342 | 3
344 | Yes | Auto Scheduled | Rad 25 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 343 | 3
345 | Yes | Auto Scheduled | Rad 26 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 344 | 3
346 | Yes | Auto Scheduled | Rad 27 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 345 | 3
347 | Yes | Auto Scheduled | Rad 28 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 346 | 3
348 | Yes | Auto Scheduled | Rad 29 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 347 | 3
349 | Yes | Auto Scheduled | Rad 30 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 348 | 3
350 | Yes | Auto Scheduled | Rad 31 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 349 | 3
351 | Yes | Auto Scheduled | Rad 32 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 350 | 3
352 | Yes | Auto Scheduled | Rad 33 | 0 hrs | Fri 1/31/25 | Fri 1/31/25 | 351 | 3
353 | Yes | Auto Scheduled | Aggregate and Normalize (D11) | 116.31 days | Mon 10/28/24 | Tue 4/08/25 |  | 2
354 | Yes | Auto Scheduled | ADT 1 | 5 hrs | Tue 1/21/25 | Wed 1/22/25 |  | 3
355 | Yes | Auto Scheduled | ADT 2 | 5 hrs | Wed 1/22/25 | Thu 1/23/25 | 354 | 3
356 | Yes | Auto Scheduled | ADT 3 | 5 hrs | Thu 1/23/25 | Thu 1/23/25 | 355 | 3
357 | Yes | Auto Scheduled | ADT 4 | 5 hrs | Thu 1/23/25 | Fri 1/24/25 | 356 | 3
358 | Yes | Auto Scheduled | ADT 5 | 5 hrs | Fri 1/24/25 | Mon 1/27/25 | 357 | 3
359 | Yes | Auto Scheduled | ADT 6 | 5 hrs | Mon 1/27/25 | Tue 1/28/25 | 358 | 3
360 | Yes | Auto Scheduled | ADT 7 | 5 hrs | Tue 1/28/25 | Wed 1/29/25 | 359 | 3
361 | Yes | Auto Scheduled | ADT 8 | 5 hrs | Wed 1/29/25 | Thu 1/30/25 | 360 | 3
362 | Yes | Auto Scheduled | ADT 9 | 5 hrs | Thu 1/30/25 | Thu 1/30/25 | 361 | 3
363 | Yes | Auto Scheduled | ADT 10 | 5 hrs | Thu 1/30/25 | Fri 1/31/25 | 362 | 3
364 | Yes | Auto Scheduled | ADT 11 | 5 hrs | Fri 1/31/25 | Mon 2/03/25 | 363 | 3
365 | Yes | Auto Scheduled | ADT 12 | 5 hrs | Mon 2/03/25 | Tue 2/04/25 | 364 | 3
366 | Yes | Auto Scheduled | ADT 13 | 5 hrs | Tue 2/04/25 | Wed 2/05/25 | 365 | 3
367 | Yes | Auto Scheduled | ADT 14 | 5 hrs | Wed 2/05/25 | Thu 2/06/25 | 366 | 3
368 | Yes | Auto Scheduled | ADT 15 | 5 hrs | Thu 2/06/25 | Thu 2/06/25 | 367 | 3
369 | Yes | Auto Scheduled | ADT 16 | 5 hrs | Thu 2/06/25 | Fri 2/07/25 | 368 | 3
370 | Yes | Auto Scheduled | ADT 17 | 5 hrs | Fri 2/07/25 | Mon 2/10/25 | 369 | 3
371 | Yes | Auto Scheduled | ADT 18 | 5 hrs | Mon 2/10/25 | Tue 2/11/25 | 370 | 3
372 | Yes | Auto Scheduled | ADT 19 | 5 hrs | Tue 2/11/25 | Wed 2/12/25 | 371 | 3
373 | Yes | Auto Scheduled | ADT 20 | 5 hrs | Wed 2/12/25 | Thu 2/13/25 | 372 | 3
374 | Yes | Auto Scheduled | ADT 21 | 5 hrs | Thu 2/13/25 | Thu 2/13/25 | 373 | 3
375 | Yes | Auto Scheduled | ADT 22 | 5 hrs | Thu 2/13/25 | Fri 2/14/25 | 374 | 3
376 | Yes | Auto Scheduled | ADT 23 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 375 | 3
377 | Yes | Auto Scheduled | ADT 24 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 376 | 3
378 | Yes | Auto Scheduled | ADT 25 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 377 | 3
379 | Yes | Auto Scheduled | ADT 26 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 378 | 3
380 | Yes | Auto Scheduled | ADT 27 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 379 | 3
381 | Yes | Auto Scheduled | ADT 28 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 380 | 3
382 | Yes | Auto Scheduled | ADT 29 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 381 | 3
383 | Yes | Auto Scheduled | ADT 30 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 382 | 3
384 | Yes | Auto Scheduled | ADT 31 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 383 | 3
385 | Yes | Auto Scheduled | ADT 32 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 384 | 3
386 | Yes | Auto Scheduled | ADT 33 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 385 | 3
387 | Yes | Auto Scheduled | ADT 34 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 386 | 3
388 | Yes | Auto Scheduled | ADT 35 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 387 | 3
389 | Yes | Auto Scheduled | ADT 36 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 388 | 3
390 | Yes | Auto Scheduled | ADT 37 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 389 | 3
391 | Yes | Auto Scheduled | ADT 38 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 390 | 3
392 | Yes | Auto Scheduled | ADT 39 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 391 | 3
393 | Yes | Auto Scheduled | ADT 40 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 392 | 3
394 | Yes | Auto Scheduled | ADT 41 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 393 | 3
395 | Yes | Auto Scheduled | ADT 42 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 394 | 3
396 | Yes | Auto Scheduled | ADT 43 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 395 | 3
397 | Yes | Auto Scheduled | ADT 44 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 396 | 3
398 | Yes | Auto Scheduled | ADT 45 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 397 | 3
399 | Yes | Auto Scheduled | ADT 46 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 398 | 3
400 | Yes | Auto Scheduled | ADT 47 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 399 | 3
401 | Yes | Auto Scheduled | ADT 48 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 400 | 3
402 | Yes | Auto Scheduled | ADT 49 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 401 | 3
403 | Yes | Auto Scheduled | ADT 50 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 402 | 3
404 | Yes | Manually Scheduled | 50% of Existing PHRIE Participant Reconnected via Interface & Data Integrated | 0 days | Mon 12/23/24 | Mon 12/23/24 |  | 3 | 25% of the initial PRHIE intefaces are now reconnected via interface, and data has been integrated into the Centralis Health web portal for viewing in the HIE
405 | Yes | Auto Scheduled | ADT 51 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 403 | 3
406 | Yes | Auto Scheduled | ADT 52 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 405 | 3
407 | Yes | Auto Scheduled | CCDA 1 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 406 | 3
408 | Yes | Auto Scheduled | CCDA 2 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 407 | 3
409 | Yes | Auto Scheduled | CCDA 3 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 408 | 3
410 | Yes | Auto Scheduled | CCDA 4 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 409 | 3
411 | Yes | Auto Scheduled | CCDA 5 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 410 | 3
412 | Yes | Auto Scheduled | CCDA 6 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 411 | 3
413 | Yes | Auto Scheduled | CCDA 7 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 412 | 3
414 | Yes | Auto Scheduled | CCDA 8 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 413 | 3
415 | Yes | Auto Scheduled | CCDA 9 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 414 | 3
416 | Yes | Auto Scheduled | CCDA 10 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 415 | 3
417 | Yes | Auto Scheduled | CCDA 11 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 416 | 3
418 | Yes | Auto Scheduled | CCDA 12 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 417 | 3
419 | Yes | Auto Scheduled | CCDA 13 | 0 hrs | Fri 2/14/25 | Fri 2/14/25 | 418 | 3
420 | Yes | Manually Scheduled | CCDA 14 | 5 hrs | Mon 10/28/24 | Mon 10/28/24 | 419 | 3
421 | Yes | Auto Scheduled | CCDA 15 | 5 hrs | Tue 1/21/25 | Tue 1/21/25 | 420 | 3
422 | Yes | Auto Scheduled | CCDA 16 | 5 hrs | Tue 1/21/25 | Wed 1/22/25 | 421 | 3
423 | Yes | Auto Scheduled | CCDA 17 | 5 hrs | Wed 1/22/25 | Thu 1/23/25 | 422 | 3
424 | Yes | Auto Scheduled | CCDA 18 | 5 hrs | Thu 1/23/25 | Thu 1/23/25 | 423 | 3
425 | Yes | Auto Scheduled | CCDA 19 | 5 hrs | Thu 1/23/25 | Fri 1/24/25 | 424 | 3
426 | Yes | Auto Scheduled | CCDA 20 | 5 hrs | Fri 1/24/25 | Mon 1/27/25 | 425 | 3
427 | Yes | Auto Scheduled | CCDA 21 | 5 hrs | Mon 1/27/25 | Mon 1/27/25 | 426 | 3
428 | Yes | Auto Scheduled | CCDA 22 | 5 hrs | Mon 1/27/25 | Tue 1/28/25 | 427 | 3
429 | Yes | Auto Scheduled | CCDA 23 | 5 hrs | Tue 1/28/25 | Tue 1/28/25 | 428 | 3
430 | Yes | Auto Scheduled | CCDA 24 | 5 hrs | Tue 1/28/25 | Wed 1/29/25 | 429 | 3
431 | Yes | Auto Scheduled | CCDA 25 | 5 hrs | Wed 1/29/25 | Thu 1/30/25 | 430 | 3
432 | Yes | Auto Scheduled | CCDA 26 | 5 hrs | Thu 1/30/25 | Thu 1/30/25 | 431 | 3
433 | Yes | Auto Scheduled | CCDA 27 | 5 hrs | Thu 1/30/25 | Fri 1/31/25 | 432 | 3
434 | Yes | Auto Scheduled | CCDA 28 | 5 hrs | Fri 1/31/25 | Mon 2/03/25 | 433 | 3
435 | Yes | Auto Scheduled | CCDA 29 | 5 hrs | Mon 2/03/25 | Mon 2/03/25 | 434 | 3
436 | Yes | Auto Scheduled | CCDA 30 | 5 hrs | Mon 2/03/25 | Tue 2/04/25 | 435 | 3
437 | Yes | Auto Scheduled | CCDA 31 | 5 hrs | Tue 2/04/25 | Tue 2/04/25 | 436 | 3
438 | Yes | Auto Scheduled | CCDA 32 | 5 hrs | Tue 2/04/25 | Wed 2/05/25 | 437 | 3
439 | Yes | Auto Scheduled | CCDA 33 | 5 hrs | Wed 2/05/25 | Thu 2/06/25 | 438 | 3
440 | Yes | Auto Scheduled | CCDA 34 | 5 hrs | Thu 2/06/25 | Thu 2/06/25 | 439 | 3
441 | Yes | Auto Scheduled | CCDA 35 | 5 hrs | Thu 2/06/25 | Fri 2/07/25 | 440 | 3
442 | Yes | Auto Scheduled | CCDA 36 | 5 hrs | Fri 2/07/25 | Mon 2/10/25 | 441 | 3
443 | Yes | Auto Scheduled | CCDA 37 | 5 hrs | Mon 2/10/25 | Mon 2/10/25 | 442 | 3
444 | Yes | Auto Scheduled | CCDA 38 | 5 hrs | Mon 2/10/25 | Tue 2/11/25 | 443 | 3
445 | Yes | Auto Scheduled | CCDA 39 | 5 hrs | Tue 2/11/25 | Tue 2/11/25 | 444 | 3
446 | Yes | Auto Scheduled | CCDA 40 | 5 hrs | Tue 2/11/25 | Wed 2/12/25 | 445 | 3
447 | Yes | Auto Scheduled | CCDA 41 | 5 hrs | Wed 2/12/25 | Thu 2/13/25 | 446 | 3
448 | Yes | Auto Scheduled | CCDA 42 | 5 hrs | Thu 2/13/25 | Thu 2/13/25 | 447 | 3
449 | Yes | Auto Scheduled | CCDA 43 | 5 hrs | Thu 2/13/25 | Fri 2/14/25 | 448 | 3
450 | Yes | Auto Scheduled | CCDA 44 | 5 hrs | Fri 2/14/25 | Mon 2/17/25 | 449 | 3
451 | Yes | Auto Scheduled | CCDA 45 | 5 hrs | Mon 2/17/25 | Mon 2/17/25 | 450 | 3
452 | Yes | Auto Scheduled | CCDA 46 | 5 hrs | Mon 2/17/25 | Tue 2/18/25 | 451 | 3
453 | Yes | Auto Scheduled | CCDA 47 | 5 hrs | Tue 2/18/25 | Tue 2/18/25 | 452 | 3
454 | Yes | Auto Scheduled | CCDA 48 | 5 hrs | Tue 2/18/25 | Wed 2/19/25 | 453 | 3
455 | Yes | Manually Scheduled | 100% of Existing PHRIE Participant Reconnected via Interface & Data Integrated | 0 days | Fri 1/03/25 | Fri 1/03/25 |  | 3 | 100% of the initial PRHIE intefaces are now reconnected via interface, and data has been integrated into the Centralis Health web portal for viewing in the HIE
456 | Yes | Auto Scheduled | CCDA 49 | 5 hrs | Wed 2/19/25 | Thu 2/20/25 | 454 | 3
457 | Yes | Auto Scheduled | CCDA 50 | 5 hrs | Thu 2/20/25 | Thu 2/20/25 | 456 | 3
458 | Yes | Auto Scheduled | CCDA 51 | 5 hrs | Thu 2/20/25 | Fri 2/21/25 | 457 | 3
459 | Yes | Auto Scheduled | CCDA 52 | 5 hrs | Fri 2/21/25 | Mon 2/24/25 | 458 | 3
460 | Yes | Auto Scheduled | CCDA 53 | 5 hrs | Mon 2/24/25 | Mon 2/24/25 | 459 | 3
461 | Yes | Auto Scheduled | Lab 1 | 5 hrs | Mon 2/24/25 | Tue 2/25/25 | 460 | 3
462 | Yes | Auto Scheduled | Lab 2 | 5 hrs | Tue 2/25/25 | Tue 2/25/25 | 461 | 3
463 | Yes | Auto Scheduled | Lab 3 | 5 hrs | Tue 2/25/25 | Wed 2/26/25 | 462 | 3
464 | Yes | Auto Scheduled | Lab 4 | 5 hrs | Wed 2/26/25 | Thu 2/27/25 | 463 | 3
465 | Yes | Auto Scheduled | Lab 5 | 5 hrs | Thu 2/27/25 | Thu 2/27/25 | 464 | 3
466 | Yes | Auto Scheduled | Lab 6 | 5 hrs | Thu 2/27/25 | Fri 2/28/25 | 465 | 3
467 | Yes | Auto Scheduled | Lab 7 | 5 hrs | Fri 2/28/25 | Mon 3/03/25 | 466 | 3
468 | Yes | Auto Scheduled | Lab 8 | 5 hrs | Mon 3/03/25 | Mon 3/03/25 | 467 | 3
469 | Yes | Auto Scheduled | Lab 9 | 5 hrs | Mon 3/03/25 | Tue 3/04/25 | 468 | 3
470 | Yes | Auto Scheduled | Lab 10 | 5 hrs | Tue 3/04/25 | Tue 3/04/25 | 469 | 3
471 | Yes | Auto Scheduled | Lab 11 | 5 hrs | Tue 3/04/25 | Wed 3/05/25 | 470 | 3
472 | Yes | Auto Scheduled | Lab 12 | 5 hrs | Wed 3/05/25 | Thu 3/06/25 | 471 | 3
473 | Yes | Auto Scheduled | Lab 13 | 5 hrs | Thu 3/06/25 | Thu 3/06/25 | 472 | 3
474 | Yes | Auto Scheduled | Lab 14 | 5 hrs | Thu 3/06/25 | Fri 3/07/25 | 473 | 3
475 | Yes | Auto Scheduled | Lab 15 | 5 hrs | Fri 3/07/25 | Mon 3/10/25 | 474 | 3
476 | Yes | Auto Scheduled | Lab 16 | 5 hrs | Mon 3/10/25 | Mon 3/10/25 | 475 | 3
477 | Yes | Auto Scheduled | Lab 17 | 5 hrs | Mon 3/10/25 | Tue 3/11/25 | 476 | 3
478 | Yes | Auto Scheduled | Lab 18 | 5 hrs | Tue 3/11/25 | Tue 3/11/25 | 477 | 3
479 | Yes | Auto Scheduled | Lab 19 | 5 hrs | Tue 3/11/25 | Wed 3/12/25 | 478 | 3
480 | Yes | Auto Scheduled | Lab 20 | 5 hrs | Wed 3/12/25 | Thu 3/13/25 | 479 | 3
481 | Yes | Auto Scheduled | Lab 21 | 5 hrs | Thu 3/13/25 | Thu 3/13/25 | 480 | 3
482 | Yes | Auto Scheduled | Lab 22 | 5 hrs | Thu 3/13/25 | Fri 3/14/25 | 481 | 3
483 | Yes | Auto Scheduled | Lab 23 | 5 hrs | Fri 3/14/25 | Mon 3/17/25 | 482 | 3
484 | Yes | Auto Scheduled | Lab 24 | 5 hrs | Mon 3/17/25 | Mon 3/17/25 | 483 | 3
485 | Yes | Auto Scheduled | Lab 25 | 5 hrs | Mon 3/17/25 | Tue 3/18/25 | 484 | 3
486 | Yes | Manually Scheduled | Lab 26 | 5 hrs | Mon 10/28/24 | Mon 10/28/24 | 485 | 3
487 | Yes | Auto Scheduled | Lab 27 | 5 hrs | Tue 1/21/25 | Wed 1/22/25 | 486 | 3
488 | Yes | Auto Scheduled | Lab 28 | 5 hrs | Wed 1/22/25 | Thu 1/23/25 | 487 | 3
489 | Yes | Auto Scheduled | Lab 29 | 5 hrs | Thu 1/23/25 | Thu 1/23/25 | 488 | 3
490 | Yes | Auto Scheduled | Lab 30 | 5 hrs | Thu 1/23/25 | Fri 1/24/25 | 489 | 3
491 | Yes | Auto Scheduled | Lab 31 | 5 hrs | Fri 1/24/25 | Mon 1/27/25 | 490 | 3
492 | Yes | Auto Scheduled | Lab 32 | 5 hrs | Mon 1/27/25 | Tue 1/28/25 | 491 | 3
493 | Yes | Auto Scheduled | Lab 33 | 5 hrs | Tue 1/28/25 | Wed 1/29/25 | 492 | 3
494 | Yes | Auto Scheduled | Lab 34 | 5 hrs | Wed 1/29/25 | Thu 1/30/25 | 493 | 3
495 | Yes | Auto Scheduled | Lab 35 | 5 hrs | Thu 1/30/25 | Thu 1/30/25 | 494 | 3
496 | Yes | Auto Scheduled | Lab 36 | 5 hrs | Thu 1/30/25 | Fri 1/31/25 | 495 | 3
497 | Yes | Auto Scheduled | Lab 37 | 5 hrs | Fri 1/31/25 | Mon 2/03/25 | 496 | 3
498 | Yes | Auto Scheduled | Lab 38 | 5 hrs | Mon 2/03/25 | Tue 2/04/25 | 497 | 3
499 | Yes | Auto Scheduled | Lab 39 | 5 hrs | Tue 2/04/25 | Wed 2/05/25 | 498 | 3
500 | Yes | Auto Scheduled | Lab 40 | 5 hrs | Wed 2/05/25 | Thu 2/06/25 | 499 | 3
501 | Yes | Auto Scheduled | Lab 41 | 5 hrs | Thu 2/06/25 | Thu 2/06/25 | 500 | 3
502 | Yes | Auto Scheduled | Lab 42 | 5 hrs | Thu 2/06/25 | Fri 2/07/25 | 501 | 3
503 | Yes | Auto Scheduled | Lab 43 | 5 hrs | Fri 2/07/25 | Mon 2/10/25 | 502 | 3
504 | Yes | Auto Scheduled | Lab 44 | 5 hrs | Mon 2/10/25 | Tue 2/11/25 | 503 | 3
505 | Yes | Auto Scheduled | Lab 45 | 5 hrs | Tue 2/11/25 | Wed 2/12/25 | 504 | 3
506 | Yes | Manually Scheduled | 25% of Existing PHRIE Participant Reconnected via Interface & Data Integrated | 0 days | Wed 11/13/24 | Wed 11/13/24 |  | 3 | 25% of the initial PRHIE intefaces are now reconnected via interface, and data has been integrated into the Centralis Health web portal for viewing in the HIE
507 | Yes | Auto Scheduled | Lab 46 | 5 hrs | Wed 2/12/25 | Thu 2/13/25 | 505 | 3
508 | Yes | Auto Scheduled | Lab 47 | 5 hrs | Thu 2/13/25 | Thu 2/13/25 | 507 | 3
509 | Yes | Auto Scheduled | Lab 48 | 5 hrs | Thu 2/13/25 | Fri 2/14/25 | 508 | 3
510 | Yes | Auto Scheduled | Lab 49 | 5 hrs | Fri 2/14/25 | Mon 2/17/25 | 509 | 3
511 | Yes | Auto Scheduled | Lab 50 | 5 hrs | Mon 2/17/25 | Tue 2/18/25 | 510 | 3
512 | Yes | Auto Scheduled | Lab 51 | 5 hrs | Tue 2/18/25 | Wed 2/19/25 | 511 | 3
513 | Yes | Auto Scheduled | Lab 52 | 5 hrs | Wed 2/19/25 | Thu 2/20/25 | 512 | 3
514 | Yes | Auto Scheduled | Lab 53 | 5 hrs | Thu 2/20/25 | Thu 2/20/25 | 513 | 3
515 | Yes | Auto Scheduled | Lab 54 | 5 hrs | Thu 2/20/25 | Fri 2/21/25 | 514 | 3
516 | Yes | Auto Scheduled | Lab 55 | 5 hrs | Fri 2/21/25 | Mon 2/24/25 | 515 | 3
517 | Yes | Auto Scheduled | Lab 56 | 5 hrs | Mon 2/24/25 | Tue 2/25/25 | 516 | 3
518 | Yes | Auto Scheduled | Lab 57 | 5 hrs | Tue 2/25/25 | Wed 2/26/25 | 517 | 3
519 | Yes | Auto Scheduled | Lab 58 | 5 hrs | Wed 2/26/25 | Thu 2/27/25 | 518 | 3
520 | Yes | Auto Scheduled | Lab 59 | 5 hrs | Thu 2/27/25 | Thu 2/27/25 | 519 | 3
521 | Yes | Auto Scheduled | Rad 1 | 5 hrs | Thu 2/27/25 | Fri 2/28/25 | 520 | 3
522 | Yes | Auto Scheduled | Rad 2 | 5 hrs | Fri 2/28/25 | Mon 3/03/25 | 521 | 3
523 | Yes | Auto Scheduled | Rad 3 | 5 hrs | Mon 3/03/25 | Tue 3/04/25 | 522 | 3
524 | Yes | Auto Scheduled | Rad 4 | 5 hrs | Tue 3/04/25 | Wed 3/05/25 | 523 | 3
525 | Yes | Auto Scheduled | Rad 5 | 5 hrs | Wed 3/05/25 | Thu 3/06/25 | 524 | 3
526 | Yes | Auto Scheduled | Rad 6 | 5 hrs | Thu 3/06/25 | Thu 3/06/25 | 525 | 3
527 | Yes | Auto Scheduled | Rad 7 | 5 hrs | Thu 3/06/25 | Fri 3/07/25 | 526 | 3
528 | Yes | Auto Scheduled | Rad 8 | 5 hrs | Fri 3/07/25 | Mon 3/10/25 | 527 | 3
529 | Yes | Auto Scheduled | Rad 9 | 5 hrs | Mon 3/10/25 | Tue 3/11/25 | 528 | 3
530 | Yes | Auto Scheduled | Rad 10 | 5 hrs | Tue 3/11/25 | Wed 3/12/25 | 529 | 3
531 | Yes | Auto Scheduled | Rad 11 | 5 hrs | Wed 3/12/25 | Thu 3/13/25 | 530 | 3
532 | Yes | Auto Scheduled | Rad 12 | 5 hrs | Thu 3/13/25 | Thu 3/13/25 | 531 | 3
533 | Yes | Auto Scheduled | Rad 13 | 5 hrs | Thu 3/13/25 | Fri 3/14/25 | 532 | 3
534 | Yes | Auto Scheduled | Rad 14 | 5 hrs | Fri 3/14/25 | Mon 3/17/25 | 533 | 3
535 | Yes | Auto Scheduled | Rad 15 | 5 hrs | Mon 3/17/25 | Tue 3/18/25 | 534 | 3
536 | Yes | Auto Scheduled | Rad 16 | 5 hrs | Tue 3/18/25 | Wed 3/19/25 | 535 | 3
537 | Yes | Auto Scheduled | Rad 17 | 5 hrs | Wed 3/19/25 | Thu 3/20/25 | 536 | 3
538 | Yes | Auto Scheduled | Rad 18 | 5 hrs | Thu 3/20/25 | Thu 3/20/25 | 537 | 3
539 | Yes | Auto Scheduled | Rad 19 | 5 hrs | Thu 3/20/25 | Fri 3/21/25 | 538 | 3
540 | Yes | Auto Scheduled | Rad 20 | 5 hrs | Fri 3/21/25 | Mon 3/24/25 | 539 | 3
541 | Yes | Auto Scheduled | Rad 21 | 5 hrs | Mon 3/24/25 | Tue 3/25/25 | 540 | 3
542 | Yes | Auto Scheduled | Rad 22 | 5 hrs | Tue 3/25/25 | Wed 3/26/25 | 541 | 3
543 | Yes | Auto Scheduled | Rad 23 | 5 hrs | Wed 3/26/25 | Thu 3/27/25 | 542 | 3
544 | Yes | Auto Scheduled | Rad 24 | 5 hrs | Thu 3/27/25 | Thu 3/27/25 | 543 | 3
545 | Yes | Auto Scheduled | Rad 25 | 5 hrs | Thu 3/27/25 | Fri 3/28/25 | 544 | 3
546 | Yes | Auto Scheduled | Rad 26 | 5 hrs | Fri 3/28/25 | Mon 3/31/25 | 545 | 3
547 | Yes | Auto Scheduled | Rad 27 | 5 hrs | Mon 3/31/25 | Tue 4/01/25 | 546 | 3
548 | Yes | Auto Scheduled | Rad 28 | 5 hrs | Tue 4/01/25 | Wed 4/02/25 | 547 | 3
549 | Yes | Auto Scheduled | Rad 29 | 5 hrs | Wed 4/02/25 | Thu 4/03/25 | 548 | 3
550 | Yes | Auto Scheduled | Rad 30 | 5 hrs | Thu 4/03/25 | Thu 4/03/25 | 549 | 3
551 | Yes | Auto Scheduled | Rad 31 | 5 hrs | Thu 4/03/25 | Fri 4/04/25 | 550 | 3
552 | Yes | Auto Scheduled | Rad 32 | 5 hrs | Fri 4/04/25 | Mon 4/07/25 | 551 | 3
553 | Yes | Auto Scheduled | Rad 33 | 5 hrs | Mon 4/07/25 | Tue 4/08/25 | 552 | 3
554 | Yes | Manually Scheduled | 75% of Existing PHRIE Participant Reconnected via Interface & Data Integrated | 0 days | Tue 12/24/24 | Tue 12/24/24 |  | 3 | 75% of the initial PRHIE intefaces are now reconnected via interface, and data has been integrated into the Centralis Health web portal for viewing in the HIE
555 | Yes | Manually Scheduled | Recurring Fees for PRHIE Participants License Fee Start | 0 days | Wed 1/01/25 | Wed 1/01/25 |  | 3
556 | Yes | Auto Scheduled | MCO Pilot | 17.69 days | Tue 1/21/25 | Fri 2/14/25 |  | 2
557 | Yes | Auto Scheduled | Participant Creation & Project Charter | 0 days | Tue 1/21/25 | Tue 1/21/25 |  | 3
558 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 0 hrs | Tue 1/21/25 | Tue 1/21/25 |  | 4
559 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 0 hrs | Tue 1/21/25 | Tue 1/21/25 | 558 | 4
560 | Yes | Auto Scheduled | Enter Participant into the System | 0 hrs | Tue 1/21/25 | Tue 1/21/25 | 559 | 4 | Create Participant Profile Create ENS Work Queue
561 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 0 hrs | Tue 1/21/25 | Tue 1/21/25 | 560 | 4 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
562 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 9.69 days | Tue 1/21/25 | Mon 2/03/25 | 557 | 3
563 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 0 days | Tue 1/21/25 | Tue 1/21/25 |  | 4 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
564 | Yes | Auto Scheduled | Give Access to The Exchange | 0 days | Tue 1/21/25 | Tue 1/21/25 | 563 | 4 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
565 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 0 days | Tue 1/21/25 | Tue 1/21/25 | 564 | 4
566 | Yes | Auto Scheduled | Determine Patient Panel Size | 0 days | Tue 1/21/25 | Tue 1/21/25 | 565 | 4
567 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 0 days | Tue 1/21/25 | Tue 1/21/25 | 566 | 4
568 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Fri 1/31/25 | Fri 1/31/25 |  | 4
569 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Mon 2/03/25 | Mon 2/03/25 |  | 4
570 | Yes | Auto Scheduled | User Credentialing and Setup | 0 days | Mon 2/03/25 | Mon 2/03/25 |  | 3
571 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0 days | Mon 2/03/25 | Mon 2/03/25 |  | 4 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
572 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 0 days | Mon 2/03/25 | Mon 2/03/25 | 571 | 4 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
573 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 0 days | Mon 2/03/25 | Mon 2/03/25 | 572 | 4
574 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 0 days | Mon 2/03/25 | Mon 2/03/25 | 573 | 4
575 | Yes | Auto Scheduled | System Training, Testing, and Validation | 4 days | Mon 2/10/25 | Fri 2/14/25 |  | 3
576 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Mon 2/10/25 | Mon 2/10/25 |  | 4
577 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Mon 2/10/25 | Mon 2/10/25 | 576 | 4
578 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Mon 2/10/25 | Mon 2/10/25 | 577 | 4
579 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Mon 2/10/25 | Mon 2/10/25 | 578 | 4
580 | Yes | Manually Scheduled | MCO Pilot Complete | 0 days | Fri 2/14/25 | Fri 2/14/25 |  | 4 | At this point in the contract the pilot for MCO 1 has been completed and has been live for a month.
581 | Yes | Auto Scheduled | Plans & Charters | 15.5 days | Wed 1/01/25 | Wed 1/22/25 |  | 2
582 | Yes | Manually Scheduled | D16: Detailed System Design Document | 20 hrs | Wed 1/01/25 | Fri 1/03/25 |  | 3
583 | Yes | Auto Scheduled | D17 Independent, Third-Party Security, and Privacy Controls Assessment Report | 5 hrs | Tue 1/21/25 | Tue 1/21/25 |  | 3
584 | Yes | Manually Scheduled | D18: Outcomes Based Certification (OBC) Support Plan and Reporting | 20 hrs | Wed 1/15/25 | Fri 1/17/25 |  | 3
585 | Yes | Manually Scheduled | D19: Turnover and Closeout Management Plan | 20 hrs | Mon 1/20/25 | Wed 1/22/25 |  | 3
586 | Yes | Auto Scheduled | Emergency Response Services | 15.25 days | Tue 1/21/25 | Tue 2/11/25 |  | 2
587 | Yes | Auto Scheduled | PRMP Introduction | 1 day | Tue 1/21/25 | Wed 1/22/25 |  | 3
588 | Yes | Auto Scheduled | Establish Technical Point of Contact with Vendor | 1 day | Wed 1/22/25 | Thu 1/23/25 | 587 | 3
589 | Yes | Auto Scheduled | Establish Interface Connectivy | 5 days | Thu 1/23/25 | Mon 2/03/25 | 588 | 3
590 | Yes | Auto Scheduled | Replicate ADT feed from PRHIE to PRMP Emergency Services | 5 days | Mon 2/03/25 | Tue 2/11/25 | 589 | 3
591 | Yes | Manually Scheduled | Emergency Response Services Live | 0 days | Tue 1/28/25 | Tue 1/28/25 |  | 3
592 | Yes | Auto Scheduled | PRDOH Connections/ELR | 43.62 days | Mon 2/03/25 | Thu 4/03/25 |  | 2
593 | Yes | Manually Scheduled | PRMP Introduction to PRDOH | 0.5 days | Mon 2/03/25 | Mon 2/03/25 |  | 3
594 | Yes | Manually Scheduled | Establish PRDOH Technical POC | 0.5 days | Wed 2/05/25 | Wed 2/05/25 |  | 3
595 | Yes | Manually Scheduled | Determine and Agree on Spec | 3 days | Thu 2/06/25 | Mon 2/10/25 |  | 3
596 | Yes | Manually Scheduled | Establish and Test Connectivity btw Centralis Health and PRDOH | 1.5 days | Thu 2/13/25 | Fri 2/14/25 |  | 3
597 | Yes | Auto Scheduled | Hospital/Clinic 1 | 5 hrs | Fri 2/14/25 | Mon 2/17/25 | 596 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
598 | Yes | Auto Scheduled | Hospital/Clinic 2 | 3 hrs | Mon 2/17/25 | Mon 2/17/25 | 597 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
599 | Yes | Auto Scheduled | Hospital/Clinic 3 | 3 hrs | Mon 2/17/25 | Mon 2/17/25 | 598 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
600 | Yes | Auto Scheduled | Hospital/Clinic 4 | 3 hrs | Mon 2/17/25 | Tue 2/18/25 | 599 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
601 | Yes | Auto Scheduled | Hospital/Clinic 5 | 3 hrs | Tue 2/18/25 | Tue 2/18/25 | 600 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
602 | Yes | Auto Scheduled | Hospital/Clinic 6 | 3 hrs | Tue 2/18/25 | Tue 2/18/25 | 601 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
603 | Yes | Auto Scheduled | Hospital/Clinic 7 | 3 hrs | Wed 2/19/25 | Wed 2/19/25 | 602 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
604 | Yes | Auto Scheduled | Hospital/Clinic 8 | 3 hrs | Wed 2/19/25 | Wed 2/19/25 | 603 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
605 | Yes | Auto Scheduled | Hospital/Clinic 9 | 3 hrs | Wed 2/19/25 | Thu 2/20/25 | 604 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
606 | Yes | Auto Scheduled | Hospital/Clinic 10 | 3 hrs | Thu 2/20/25 | Thu 2/20/25 | 605 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
607 | Yes | Auto Scheduled | Hospital/Clinic 11 | 3 hrs | Thu 2/20/25 | Thu 2/20/25 | 606 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
608 | Yes | Auto Scheduled | Hospital/Clinic 12 | 3 hrs | Thu 2/20/25 | Fri 2/21/25 | 607 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
609 | Yes | Auto Scheduled | Hospital/Clinic 13 | 3 hrs | Fri 2/21/25 | Fri 2/21/25 | 608 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
610 | Yes | Auto Scheduled | Hospital/Clinic 14 | 3 hrs | Fri 2/21/25 | Fri 2/21/25 | 609 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
611 | Yes | Auto Scheduled | Hospital/Clinic 15 | 3 hrs | Mon 2/24/25 | Mon 2/24/25 | 610 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
612 | Yes | Auto Scheduled | Hospital/Clinic 16 | 3 hrs | Mon 2/24/25 | Mon 2/24/25 | 611 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
613 | Yes | Auto Scheduled | Hospital/Clinic 17 | 3 hrs | Mon 2/24/25 | Tue 2/25/25 | 612 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
614 | Yes | Auto Scheduled | Hospital/Clinic 18 | 3 hrs | Tue 2/25/25 | Tue 2/25/25 | 613 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
615 | Yes | Auto Scheduled | Hospital/Clinic 19 | 3 hrs | Tue 2/25/25 | Tue 2/25/25 | 614 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
616 | Yes | Auto Scheduled | Hospital/Clinic 20 | 3 hrs | Tue 2/25/25 | Wed 2/26/25 | 615 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
617 | Yes | Auto Scheduled | Hospital/Clinic 21 | 3 hrs | Wed 2/26/25 | Wed 2/26/25 | 616 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
618 | Yes | Auto Scheduled | Hospital/Clinic 22 | 3 hrs | Wed 2/26/25 | Wed 2/26/25 | 617 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
619 | Yes | Auto Scheduled | Hospital/Clinic 23 | 3 hrs | Thu 2/27/25 | Thu 2/27/25 | 618 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
620 | Yes | Auto Scheduled | Hospital/Clinic 24 | 3 hrs | Thu 2/27/25 | Thu 2/27/25 | 619 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
621 | Yes | Auto Scheduled | Hospital/Clinic 25 | 3 hrs | Thu 2/27/25 | Fri 2/28/25 | 620 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
622 | Yes | Auto Scheduled | Hospital/Clinic 26 | 3 hrs | Fri 2/28/25 | Fri 2/28/25 | 621 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
623 | Yes | Auto Scheduled | Hospital/Clinic 27 | 3 hrs | Fri 2/28/25 | Fri 2/28/25 | 622 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
624 | Yes | Auto Scheduled | Hospital/Clinic 28 | 3 hrs | Fri 2/28/25 | Mon 3/03/25 | 623 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
625 | Yes | Auto Scheduled | Hospital/Clinic 29 | 3 hrs | Mon 3/03/25 | Mon 3/03/25 | 624 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
626 | Yes | Auto Scheduled | Hospital/Clinic 30 | 3 hrs | Mon 3/03/25 | Mon 3/03/25 | 625 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
627 | Yes | Auto Scheduled | Hospital/Clinic 31 | 3 hrs | Tue 3/04/25 | Tue 3/04/25 | 626 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
628 | Yes | Auto Scheduled | Hospital/Clinic 32 | 3 hrs | Tue 3/04/25 | Tue 3/04/25 | 627 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
629 | Yes | Auto Scheduled | Hospital/Clinic 33 | 3 hrs | Tue 3/04/25 | Wed 3/05/25 | 628 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
630 | Yes | Auto Scheduled | Hospital/Clinic 34 | 3 hrs | Wed 3/05/25 | Wed 3/05/25 | 629 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
631 | Yes | Auto Scheduled | Hospital/Clinic 35 | 3 hrs | Wed 3/05/25 | Wed 3/05/25 | 630 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
632 | Yes | Auto Scheduled | Hospital/Clinic 36 | 3 hrs | Wed 3/05/25 | Thu 3/06/25 | 631 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
633 | Yes | Auto Scheduled | Hospital/Clinic 37 | 3 hrs | Thu 3/06/25 | Thu 3/06/25 | 632 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
634 | Yes | Auto Scheduled | Hospital/Clinic 38 | 3 hrs | Thu 3/06/25 | Thu 3/06/25 | 633 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
635 | Yes | Auto Scheduled | Hospital/Clinic 39 | 3 hrs | Fri 3/07/25 | Fri 3/07/25 | 634 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
636 | Yes | Auto Scheduled | Hospital/Clinic 40 | 3 hrs | Fri 3/07/25 | Fri 3/07/25 | 635 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
637 | Yes | Auto Scheduled | Hospital/Clinic 41 | 3 hrs | Fri 3/07/25 | Mon 3/10/25 | 636 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
638 | Yes | Auto Scheduled | Hospital/Clinic 42 | 3 hrs | Mon 3/10/25 | Mon 3/10/25 | 637 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
639 | Yes | Auto Scheduled | Hospital/Clinic 43 | 3 hrs | Mon 3/10/25 | Mon 3/10/25 | 638 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
640 | Yes | Auto Scheduled | Hospital/Clinic 44 | 3 hrs | Mon 3/10/25 | Tue 3/11/25 | 639 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
641 | Yes | Auto Scheduled | Hospital/Clinic 45 | 3 hrs | Tue 3/11/25 | Tue 3/11/25 | 640 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
642 | Yes | Auto Scheduled | Hospital/Clinic 46 | 3 hrs | Tue 3/11/25 | Tue 3/11/25 | 641 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
643 | Yes | Manually Scheduled | Hospital/Clinic 47 | 3 hrs | Wed 3/12/25 | Wed 3/12/25 | 642 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
644 | Yes | Auto Scheduled | Hospital/Clinic 48 | 3 hrs | Wed 3/12/25 | Thu 3/13/25 | 643 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
645 | Yes | Auto Scheduled | Hospital/Clinic 49 | 3 hrs | Thu 3/13/25 | Thu 3/13/25 | 644 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
646 | Yes | Auto Scheduled | Hospital/Clinic 50 | 3 hrs | Thu 3/13/25 | Thu 3/13/25 | 645 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
647 | Yes | Auto Scheduled | Hospital/Clinic 51 | 3 hrs | Fri 3/14/25 | Fri 3/14/25 | 646 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
648 | Yes | Auto Scheduled | Hospital/Clinic 52 | 3 hrs | Fri 3/14/25 | Fri 3/14/25 | 647 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
649 | Yes | Auto Scheduled | Hospital/Clinic 53 | 3 hrs | Fri 3/14/25 | Mon 3/17/25 | 648 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
650 | Yes | Auto Scheduled | Hospital/Clinic 54 | 3 hrs | Mon 3/17/25 | Mon 3/17/25 | 649 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
651 | Yes | Auto Scheduled | Hospital/Clinic 55 | 3 hrs | Mon 3/17/25 | Mon 3/17/25 | 650 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
652 | Yes | Auto Scheduled | Hospital/Clinic 56 | 3 hrs | Mon 3/17/25 | Tue 3/18/25 | 651 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
653 | Yes | Auto Scheduled | Hospital/Clinic 57 | 3 hrs | Tue 3/18/25 | Tue 3/18/25 | 652 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
654 | Yes | Auto Scheduled | Hospital/Clinic 58 | 3 hrs | Tue 3/18/25 | Tue 3/18/25 | 653 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
655 | Yes | Auto Scheduled | Hospital/Clinic 59 | 3 hrs | Wed 3/19/25 | Wed 3/19/25 | 654 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
656 | Yes | Auto Scheduled | Hospital/Clinic 60 | 3 hrs | Wed 3/19/25 | Wed 3/19/25 | 655 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
657 | Yes | Auto Scheduled | Hospital/Clinic 61 | 3 hrs | Wed 3/19/25 | Thu 3/20/25 | 656 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
658 | Yes | Auto Scheduled | Hospital/Clinic 62 | 3 hrs | Thu 3/20/25 | Thu 3/20/25 | 657 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
659 | Yes | Auto Scheduled | Hospital/Clinic 63 | 3 hrs | Thu 3/20/25 | Thu 3/20/25 | 658 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
660 | Yes | Auto Scheduled | Centros 330_FQHC 1 | 3 hrs | Thu 3/20/25 | Fri 3/21/25 | 659 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
661 | Yes | Auto Scheduled | Centros 330_FQHC 2 | 3 hrs | Fri 3/21/25 | Fri 3/21/25 | 660 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
662 | Yes | Auto Scheduled | Centros 330_FQHC 3 | 3 hrs | Fri 3/21/25 | Fri 3/21/25 | 661 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
663 | Yes | Auto Scheduled | Centros 330_FQHC 4 | 3 hrs | Mon 3/24/25 | Mon 3/24/25 | 662 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
664 | Yes | Auto Scheduled | Centros 330_FQHC 5 | 3 hrs | Mon 3/24/25 | Mon 3/24/25 | 663 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
665 | Yes | Auto Scheduled | Centros 330_FQHC 6 | 3 hrs | Mon 3/24/25 | Tue 3/25/25 | 664 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
666 | Yes | Auto Scheduled | Centros 330_FQHC 7 | 3 hrs | Tue 3/25/25 | Tue 3/25/25 | 665 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
667 | Yes | Auto Scheduled | Centros 330_FQHC 8 | 3 hrs | Tue 3/25/25 | Tue 3/25/25 | 666 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
668 | Yes | Auto Scheduled | Centros 330_FQHC 9 | 3 hrs | Tue 3/25/25 | Wed 3/26/25 | 667 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
669 | Yes | Auto Scheduled | Centros 330_FQHC 10 | 3 hrs | Wed 3/26/25 | Wed 3/26/25 | 668 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
670 | Yes | Auto Scheduled | Centros 330_FQHC 11 | 3 hrs | Wed 3/26/25 | Wed 3/26/25 | 669 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
671 | Yes | Auto Scheduled | Centros 330_FQHC 12 | 3 hrs | Thu 3/27/25 | Thu 3/27/25 | 670 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
672 | Yes | Auto Scheduled | Centros 330_FQHC 13 | 3 hrs | Thu 3/27/25 | Thu 3/27/25 | 671 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
673 | Yes | Auto Scheduled | Centros 330_FQHC 14 | 3 hrs | Thu 3/27/25 | Fri 3/28/25 | 672 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
674 | Yes | Auto Scheduled | Centros 330_FQHC 15 | 3 hrs | Fri 3/28/25 | Fri 3/28/25 | 673 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
675 | Yes | Auto Scheduled | Centros 330_FQHC 16 | 3 hrs | Fri 3/28/25 | Fri 3/28/25 | 674 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
676 | Yes | Auto Scheduled | Centros 330_FQHC 17 | 3 hrs | Fri 3/28/25 | Mon 3/31/25 | 675 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
677 | Yes | Auto Scheduled | LIMS 1 | 3 hrs | Mon 3/31/25 | Mon 3/31/25 | 676 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
678 | Yes | Auto Scheduled | LIMS 2 | 3 hrs | Mon 3/31/25 | Mon 3/31/25 | 677 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
679 | Yes | Auto Scheduled | LIMS 3 | 3 hrs | Tue 4/01/25 | Tue 4/01/25 | 678 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
680 | Yes | Auto Scheduled | LIMS 4 | 3 hrs | Tue 4/01/25 | Tue 4/01/25 | 679 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
681 | Yes | Auto Scheduled | LIMS 5 | 3 hrs | Tue 4/01/25 | Wed 4/02/25 | 680 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
682 | Yes | Auto Scheduled | LIMS 6 | 3 hrs | Wed 4/02/25 | Wed 4/02/25 | 681 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
683 | Yes | Auto Scheduled | LIMS 7 | 3 hrs | Wed 4/02/25 | Wed 4/02/25 | 682 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
684 | Yes | Auto Scheduled | LIMS 8 | 3 hrs | Wed 4/02/25 | Thu 4/03/25 | 683 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
685 | Yes | Auto Scheduled | Radiology Facility | 3 hrs | Thu 4/03/25 | Thu 4/03/25 | 684 | 3 | Centarlis Health team to followup on PRMP introductory email, with phone calls and email communications to initiate communications with existing PHRIE participants, and update agreements to align with Centralis Health as HIE vedor
686 | Yes | Manually Scheduled | PRDOH Reconnection Complete / ELR | 0 days | Thu 4/03/25 | Thu 4/03/25 |  | 3
687 | Yes | Auto Scheduled | Phase 3- Expand and Launch | 321.88 days | Thu 5/01/25 | Fri 7/24/26 |  | 1
688 | Yes | Auto Scheduled | Expanded Existing Data Feeds to PRHIE | 22.5 days | Mon 9/01/25 | Wed 10/01/25 |  | 2 | Work with data sources to fill the gaps in data on existing interfaces to PRHIE ie If only receiving ADT, expand data to include full clinical feeds (HL7, CDA, API, etc) Connected data sources (81) is based on the Health Gorilla - Integration Overview_PRHIE 2023 documents from the HIE Procurement Library.
689 | Yes | Auto Scheduled | Hospital/Clinics 1 | 5 hrs | Mon 9/01/25 | Mon 9/01/25 |  | 3
690 | Yes | Auto Scheduled | Hospital/Clinics 2 | 5 hrs | Mon 9/01/25 | Tue 9/02/25 | 689 | 3
691 | Yes | Auto Scheduled | Hospital/Clinics 3 | 5 hrs | Tue 9/02/25 | Tue 9/02/25 | 690 | 3
692 | Yes | Auto Scheduled | Hospital/Clinics 4 | 5 hrs | Tue 9/02/25 | Wed 9/03/25 | 691 | 3
693 | Yes | Auto Scheduled | Hospital/Clinics 5 | 5 hrs | Wed 9/03/25 | Thu 9/04/25 | 692 | 3
694 | Yes | Auto Scheduled | Hospital/Clinics 6 | 5 hrs | Thu 9/04/25 | Thu 9/04/25 | 693 | 3
695 | Yes | Auto Scheduled | Hospital/Clinics 7 | 5 hrs | Thu 9/04/25 | Fri 9/05/25 | 694 | 3
696 | Yes | Auto Scheduled | Hospital/Clinics 8 | 5 hrs | Fri 9/05/25 | Fri 9/05/25 | 695 | 3
697 | Yes | Auto Scheduled | Hospital/Clinics 9 | 5 hrs | Mon 9/08/25 | Mon 9/08/25 | 696 | 3
698 | Yes | Auto Scheduled | Hospital/Clinics 10 | 5 hrs | Mon 9/08/25 | Tue 9/09/25 | 697 | 3
699 | Yes | Auto Scheduled | Hospital/Clinics 11 | 5 hrs | Tue 9/09/25 | Tue 9/09/25 | 698 | 3
700 | Yes | Auto Scheduled | Hospital/Clinics 12 | 5 hrs | Tue 9/09/25 | Wed 9/10/25 | 699 | 3
701 | Yes | Auto Scheduled | Hospital/Clinics 13 | 5 hrs | Wed 9/10/25 | Thu 9/11/25 | 700 | 3
702 | Yes | Auto Scheduled | Hospital/Clinics 14 | 5 hrs | Thu 9/11/25 | Thu 9/11/25 | 701 | 3
703 | Yes | Auto Scheduled | Hospital/Clinics 15 | 5 hrs | Thu 9/11/25 | Fri 9/12/25 | 702 | 3
704 | Yes | Auto Scheduled | Hospital/Clinics 16 | 5 hrs | Fri 9/12/25 | Fri 9/12/25 | 703 | 3
705 | Yes | Auto Scheduled | Hospital/Clinics 17 | 5 hrs | Mon 9/15/25 | Mon 9/15/25 | 704 | 3
706 | Yes | Auto Scheduled | Hospital/Clinics 18 | 5 hrs | Mon 9/15/25 | Tue 9/16/25 | 705 | 3
707 | Yes | Auto Scheduled | Hospital/Clinics 19 | 5 hrs | Tue 9/16/25 | Tue 9/16/25 | 706 | 3
708 | Yes | Auto Scheduled | Hospital/Clinics 20 | 5 hrs | Tue 9/16/25 | Wed 9/17/25 | 707 | 3
709 | Yes | Auto Scheduled | Hospital/Clinics 21 | 5 hrs | Wed 9/17/25 | Thu 9/18/25 | 708 | 3
710 | Yes | Auto Scheduled | Hospital/Clinics 22 | 5 hrs | Thu 9/18/25 | Thu 9/18/25 | 709 | 3
711 | Yes | Auto Scheduled | Hospital/Clinics 23 | 5 hrs | Thu 9/18/25 | Fri 9/19/25 | 710 | 3
712 | Yes | Auto Scheduled | Hospital/Clinics 24 | 5 hrs | Fri 9/19/25 | Fri 9/19/25 | 711 | 3
713 | Yes | Auto Scheduled | Hospital/Clinics 25 | 5 hrs | Mon 9/22/25 | Mon 9/22/25 | 712 | 3
714 | Yes | Auto Scheduled | Hospital/Clinics 26 | 5 hrs | Mon 9/22/25 | Tue 9/23/25 | 713 | 3
715 | Yes | Auto Scheduled | Hospital/Clinics 27 | 5 hrs | Tue 9/23/25 | Tue 9/23/25 | 714 | 3
716 | Yes | Auto Scheduled | Hospital/Clinics 28 | 5 hrs | Tue 9/23/25 | Wed 9/24/25 | 715 | 3
717 | Yes | Auto Scheduled | Hospital/Clinics 29 | 5 hrs | Wed 9/24/25 | Thu 9/25/25 | 716 | 3
718 | Yes | Auto Scheduled | Hospital/Clinics 30 | 5 hrs | Thu 9/25/25 | Thu 9/25/25 | 717 | 3
719 | Yes | Auto Scheduled | Hospital/Clinics 31 | 5 hrs | Thu 9/25/25 | Fri 9/26/25 | 718 | 3
720 | Yes | Auto Scheduled | Hospital/Clinics 32 | 5 hrs | Fri 9/26/25 | Fri 9/26/25 | 719 | 3
721 | Yes | Auto Scheduled | Hospital/Clinics 33 | 5 hrs | Mon 9/29/25 | Mon 9/29/25 | 720 | 3
722 | Yes | Auto Scheduled | Hospital/Clinics 34 | 5 hrs | Mon 9/29/25 | Tue 9/30/25 | 721 | 3
723 | Yes | Auto Scheduled | Hospital/Clinics 35 | 5 hrs | Tue 9/30/25 | Tue 9/30/25 | 722 | 3
724 | Yes | Auto Scheduled | Hospital/Clinics 36 | 5 hrs | Tue 9/30/25 | Wed 10/01/25 | 723 | 3
725 | Yes | Manually Scheduled | Hospital/Clinics 37 | 5 hrs | Mon 9/01/25 | Mon 9/01/25 | 724 | 3
726 | Yes | Auto Scheduled | Hospital/Clinics 38 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 725 | 3
727 | Yes | Auto Scheduled | Hospital/Clinics 39 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 726 | 3
728 | Yes | Auto Scheduled | Hospital/Clinics 40 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 727 | 3
729 | Yes | Auto Scheduled | Hospital/Clinics 41 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 728 | 3
730 | Yes | Auto Scheduled | Hospital/Clinics 42 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 729 | 3
731 | Yes | Auto Scheduled | Hospital/Clinics 43 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 730 | 3
732 | Yes | Auto Scheduled | Hospital/Clinics 44 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 731 | 3
733 | Yes | Auto Scheduled | Hospital/Clinics 45 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 732 | 3
734 | Yes | Auto Scheduled | Hospital/Clinics 46 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 733 | 3
735 | Yes | Auto Scheduled | Hospital/Clinics 47 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 734 | 3
736 | Yes | Auto Scheduled | Hospital/Clinics 48 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 735 | 3
737 | Yes | Auto Scheduled | Hospital/Clinics 49 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 736 | 3
738 | Yes | Auto Scheduled | Hospital/Clinics 50 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 737 | 3
739 | Yes | Auto Scheduled | Hospital/Clinics 51 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 738 | 3
740 | Yes | Auto Scheduled | Hospital/Clinics 52 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 739 | 3
741 | Yes | Auto Scheduled | Hospital/Clinics 53 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 740 | 3
742 | Yes | Auto Scheduled | Hospital/Clinics 54 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 741 | 3
743 | Yes | Auto Scheduled | Hospital/Clinics 55 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 742 | 3
744 | Yes | Auto Scheduled | Hospital/Clinics 56 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 743 | 3
745 | Yes | Auto Scheduled | Hospital/Clinics 57 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 744 | 3
746 | Yes | Auto Scheduled | Hospital/Clinics 58 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 745 | 3
747 | Yes | Auto Scheduled | Hospital/Clinics 59 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 746 | 3
748 | Yes | Auto Scheduled | Hospital/Clinics 60 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 747 | 3
749 | Yes | Auto Scheduled | Hospital/Clinics 61 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 748 | 3
750 | Yes | Auto Scheduled | Hospital/Clinics 62 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 749 | 3
751 | Yes | Auto Scheduled | Hospital/Clinics 63 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 750 | 3
752 | Yes | Auto Scheduled | FQHC 1 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 751 | 3
753 | Yes | Auto Scheduled | FQHC 2 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 752 | 3
754 | Yes | Auto Scheduled | FQHC 3 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 753 | 3
755 | Yes | Auto Scheduled | FQHC 4 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 754 | 3
756 | Yes | Auto Scheduled | FQHC 5 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 755 | 3
757 | Yes | Auto Scheduled | FQHC 6 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 756 | 3
758 | Yes | Auto Scheduled | FQHC 7 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 757 | 3
759 | Yes | Auto Scheduled | FQHC 8 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 758 | 3
760 | Yes | Auto Scheduled | FQHC 9 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 759 | 3
761 | Yes | Auto Scheduled | LIMS 1 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 760 | 3
762 | Yes | Auto Scheduled | LIMS 2 | 0 hrs | Mon 9/01/25 | Mon 9/01/25 | 761 | 3
763 | Yes | Manually Scheduled | Expand Hospital Connectivity | 107.25 days | Mon 9/01/25 | Wed 1/28/26 |  | 2 | Establish connection and Connectivity to hospitals not previously connected to PRHIE with former HIE vendor
764 | Yes | Auto Scheduled | Identify Missing Data Sources | 0.5 days | Mon 9/01/25 | Mon 9/01/25 |  | 3 | Work with PRMP to identify hospital not previously connected
765 | Yes | Auto Scheduled | PRMP Introductory Email | 0.5 days | Mon 9/01/25 | Mon 9/01/25 | 764 | 3
766 | Yes | Auto Scheduled | On-board Remaining Hospital Data | 76.25 days | Tue 9/02/25 | Wed 12/17/25 | 765 | 3 | According to the RFP there are 54 hospitals in Puerto Rico. The PRHIE HIE roadmap states 72% of hospitals are already connected, leaving approximately 16 remaining hospitals
767 | Yes | Auto Scheduled | Hospital 1 | 0.44 days | Tue 9/02/25 | Tue 9/02/25 |  | 4
768 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Tue 9/02/25 | Tue 9/02/25 |  | 5
769 | Yes | Auto Scheduled | Obtain Contract | 3.5 hrs | Tue 9/02/25 | Tue 9/02/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
770 | Yes | Auto Scheduled | Interface Activity | 0 days | Tue 9/02/25 | Tue 9/02/25 | 769 | 5 | Build interfaces based on PRMP expected data sets
771 | Yes | Auto Scheduled | Hospital 2 | 4.81 days | Tue 9/02/25 | Tue 9/09/25 | 767 | 4
772 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Tue 9/09/25 | Tue 9/09/25 |  | 5
773 | Yes | Auto Scheduled | Obtain Contract | 3.5 hrs | Tue 9/02/25 | Tue 9/02/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
774 | Yes | Auto Scheduled | Interface Activity | 0 days | Tue 9/02/25 | Tue 9/02/25 | 773 | 5 | Build interfaces based on PRMP expected data sets
775 | Yes | Auto Scheduled | Hospital 3 | 5 days | Tue 9/09/25 | Tue 9/16/25 | 771 | 4
776 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Tue 9/16/25 | Tue 9/16/25 |  | 5
777 | Yes | Auto Scheduled | Obtain Contract | 3.5 hrs | Tue 9/09/25 | Tue 9/09/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
778 | Yes | Auto Scheduled | Interface Activity | 0 days | Tue 9/09/25 | Tue 9/09/25 | 777 | 5 | Build interfaces based on PRMP expected data sets
779 | Yes | Auto Scheduled | Hospital 4 | 6 days | Tue 9/16/25 | Wed 9/24/25 | 775 | 4
780 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Wed 9/24/25 | Wed 9/24/25 |  | 5
781 | Yes | Auto Scheduled | Obtain Contract | 3.5 hrs | Tue 9/16/25 | Tue 9/16/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
782 | Yes | Auto Scheduled | Interface Activity | 0 days | Tue 9/16/25 | Tue 9/16/25 | 781 | 5 | Build interfaces based on PRMP expected data sets
783 | Yes | Auto Scheduled | Hospital 5 | 3 days | Wed 9/24/25 | Mon 9/29/25 | 779 | 4
784 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Mon 9/29/25 | Mon 9/29/25 |  | 5
785 | Yes | Auto Scheduled | Obtain Contract | 3.5 hrs | Wed 9/24/25 | Wed 9/24/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
786 | Yes | Auto Scheduled | Interface Activity | 0 days | Wed 9/24/25 | Wed 9/24/25 | 785 | 5 | Build interfaces based on PRMP expected data sets
787 | Yes | Auto Scheduled | Hospital 6 | 8 days | Mon 9/29/25 | Thu 10/09/25 | 783 | 4
788 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Thu 10/09/25 | Thu 10/09/25 |  | 5
789 | Yes | Auto Scheduled | Obtain Contract | 3.5 hrs | Mon 9/29/25 | Mon 9/29/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
790 | Yes | Auto Scheduled | Interface Activity | 0 days | Mon 9/29/25 | Mon 9/29/25 | 789 | 5 | Build interfaces based on PRMP expected data sets
791 | Yes | Auto Scheduled | Hospital 7 | 5 days | Thu 10/09/25 | Thu 10/16/25 | 787 | 4
792 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Thu 10/16/25 | Thu 10/16/25 |  | 5
793 | Yes | Auto Scheduled | Obtain Contract | 3.5 hrs | Thu 10/09/25 | Thu 10/09/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
794 | Yes | Auto Scheduled | Interface Activity | 0 days | Thu 10/09/25 | Thu 10/09/25 | 793 | 5 | Build interfaces based on PRMP expected data sets
795 | Yes | Auto Scheduled | Hospital 8 | 6 days | Thu 10/16/25 | Fri 10/24/25 | 791 | 4
796 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Fri 10/24/25 | Fri 10/24/25 |  | 5
797 | Yes | Auto Scheduled | Obtain Contract | 0 hrs | Thu 10/16/25 | Thu 10/16/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
798 | Yes | Auto Scheduled | Interface Activity | 0 days | Thu 10/16/25 | Thu 10/16/25 | 797 | 5 | Build interfaces based on PRMP expected data sets
799 | Yes | Auto Scheduled | Hospital 9 | 5 days | Fri 10/24/25 | Fri 10/31/25 | 795 | 4
800 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Fri 10/31/25 | Fri 10/31/25 |  | 5
801 | Yes | Auto Scheduled | Obtain Contract | 3.5 hrs | Fri 10/24/25 | Fri 10/24/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
802 | Yes | Auto Scheduled | Interface Activity | 0 days | Fri 10/24/25 | Fri 10/24/25 | 801 | 5 | Build interfaces based on PRMP expected data sets
803 | Yes | Auto Scheduled | Hospital 10 | 5 days | Fri 10/31/25 | Fri 11/07/25 | 799 | 4
804 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Fri 11/07/25 | Fri 11/07/25 |  | 5
805 | Yes | Auto Scheduled | Obtain Contract | 3.5 hrs | Fri 10/31/25 | Fri 10/31/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
806 | Yes | Auto Scheduled | Interface Activity | 0 days | Fri 10/31/25 | Fri 10/31/25 | 805 | 5 | Build interfaces based on PRMP expected data sets
807 | Yes | Auto Scheduled | Hospital 11 | 15.25 days | Fri 10/17/25 | Fri 11/07/25 | 803 | 4
808 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Fri 10/17/25 | Fri 10/17/25 |  | 5
809 | Yes | Auto Scheduled | Obtain Contract | 0 hrs | Fri 11/07/25 | Fri 11/07/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
810 | Yes | Auto Scheduled | Interface Activity | 0 days | Fri 11/07/25 | Fri 11/07/25 | 809 | 5 | Build interfaces based on PRMP expected data sets
811 | Yes | Auto Scheduled | Hospital 12 | 11 days | Fri 11/07/25 | Mon 11/24/25 | 807 | 4
812 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Mon 11/24/25 | Mon 11/24/25 |  | 5
813 | Yes | Auto Scheduled | Obtain Contract | 3.5 hrs | Fri 11/07/25 | Fri 11/07/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
814 | Yes | Auto Scheduled | Interface Activity | 0 days | Fri 11/07/25 | Fri 11/07/25 | 813 | 5 | Build interfaces based on PRMP expected data sets
815 | Yes | Auto Scheduled | Hospital 13 | 6 days | Mon 11/24/25 | Tue 12/02/25 | 811 | 4
816 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Tue 12/02/25 | Tue 12/02/25 |  | 5
817 | Yes | Auto Scheduled | Obtain Contract | 3.5 hrs | Mon 11/24/25 | Mon 11/24/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
818 | Yes | Auto Scheduled | Interface Activity | 0 days | Mon 11/24/25 | Mon 11/24/25 | 817 | 5 | Build interfaces based on PRMP expected data sets
819 | Yes | Auto Scheduled | Hospital 14 | 0.44 days | Wed 12/10/25 | Wed 12/10/25 | 815 | 4
820 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Wed 12/10/25 | Wed 12/10/25 |  | 5
821 | Yes | Manually Scheduled | Obtain Contract | 3.5 hrs | Wed 12/10/25 | Wed 12/10/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
822 | Yes | Auto Scheduled | Interface Activity | 0 days | Wed 12/10/25 | Wed 12/10/25 | 821 | 5 | Build interfaces based on PRMP expected data sets
823 | Yes | Auto Scheduled | Hospital 15 | 4.81 days | Wed 12/10/25 | Wed 12/17/25 | 819 | 4
824 | Yes | Manually Scheduled | PRMP Introduction | 0.25 days | Wed 12/17/25 | Wed 12/17/25 |  | 5
825 | Yes | Auto Scheduled | Obtain Contract | 3.5 hrs | Wed 12/10/25 | Wed 12/10/25 |  | 5 | Based on communications following PRMP introdcutory email, agreements will be established prior to interface
826 | Yes | Auto Scheduled | Interface Activity | 0 days | Wed 12/10/25 | Wed 12/10/25 | 825 | 5 | Build interfaces based on PRMP expected data sets
827 | Yes | Auto Scheduled | Launch HIE Services w ENS (Centros 330/MCO Community) | 321.88 days | Thu 5/01/25 | Fri 7/24/26 | 586 | 2 | At this point in the contract all historical data from prior HIE vendor has been migrated to Centralis Health. Existing feeds are connected and provide current update to date clinical data based on the expectation of PRMP. MCO has piloted ENS and access to patient logitudinal records. We are ready to expand services to the provider and remaining MCO community . Our strategic approach is the launch this effort by providing each organization with a patient panel of 7500 (sponsored by PRMP). Once panels are uploaded to Centralis Health and notification are flowing to the organization via their Centralis Health web portal, they can access patient logitudinal records directly from the work queue item.
828 | Yes | Manually Scheduled | Establish Communication Plan with PRMP | 1 day | Wed 10/01/25 | Wed 10/01/25 |  | 3 | -PRMP to assist with introductions to remaining 4 MCOs -Align effors with ASPPR to gain direct access to the Centros 330 organizations
829 | Yes | Manually Scheduled | PRMP Introduction | 0 days | Thu 10/09/25 | Thu 10/09/25 |  | 3
830 | Yes | Auto Scheduled | MCO Launch | 194.38 days | Thu 5/01/25 | Wed 1/28/26 |  | 3
831 | Yes | Manually Scheduled | MMM Multi Health LLC | 29.88 days | Wed 10/15/25 | Tue 11/25/25 |  | 4
832 | Yes | Manually Scheduled | Participant Creation & Project Charter | 1.38 days | Wed 10/15/25 | Thu 10/16/25 |  | 5
833 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 0 hrs | Thu 5/01/25 | Thu 5/01/25 |  | 6
834 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 0 hrs | Wed 10/15/25 | Wed 10/15/25 | 833 | 6
835 | Yes | Auto Scheduled | Enter Participant into the System | 0 hrs | Wed 10/15/25 | Wed 10/15/25 | 834 | 6 | Create Participant Profile Create ENS Work Queue
836 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 0 hrs | Wed 10/15/25 | Wed 10/15/25 | 835 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
837 | Yes | Manually Scheduled | Community Patient Lookup & Notification Setup | 7 days | Thu 10/16/25 | Mon 10/27/25 | 832 | 5
838 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 0 days | Thu 10/16/25 | Thu 10/16/25 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
839 | Yes | Auto Scheduled | Give Access to The Exchange | 0 days | Thu 10/16/25 | Thu 10/16/25 | 838 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
840 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 0 days | Thu 10/16/25 | Thu 10/16/25 | 839 | 6
841 | Yes | Auto Scheduled | Determine Patient Panel Size | 0 days | Thu 10/16/25 | Thu 10/16/25 | 840 | 6
842 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 0 days | Thu 10/16/25 | Thu 10/16/25 | 841 | 6
843 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Thu 10/16/25 | Fri 10/17/25 | 842 | 6
844 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Fri 10/17/25 | Mon 10/20/25 | 843 | 6
845 | Yes | Manually Scheduled | User Credentialing and Setup | 3.5 days | Mon 10/27/25 | Thu 10/30/25 | 837 | 5
846 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0 days | Mon 10/27/25 | Mon 10/27/25 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
847 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 0 days | Mon 10/27/25 | Mon 10/27/25 | 846 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
848 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 0 days | Mon 10/27/25 | Mon 10/27/25 | 847 | 6
849 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 0 days | Mon 10/27/25 | Mon 10/27/25 | 848 | 6
850 | Yes | Manually Scheduled | System Training, Testing, and Validation | 5 days | Thu 10/30/25 | Thu 11/06/25 | 845 | 5
851 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Thu 10/30/25 | Thu 10/30/25 |  | 6
852 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Thu 10/30/25 | Thu 10/30/25 | 148;851 | 6
853 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Thu 10/30/25 | Thu 10/30/25 | 852 | 6
854 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Thu 10/30/25 | Thu 10/30/25 | 853 | 6
855 | Yes | Auto Scheduled | Molina Healthcare of Puerto Rico Inc. | 8.5 days | Tue 11/18/25 | Fri 11/28/25 | 831 | 4
856 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Tue 11/18/25 | Wed 11/19/25 |  | 5
857 | Yes | Manually Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Tue 11/18/25 | Tue 11/18/25 |  | 6
858 | Yes | Manually Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Tue 11/18/25 | Wed 11/19/25 | 857 | 6
859 | Yes | Manually Scheduled | Enter Participant into the System | 1 hr | Wed 11/19/25 | Wed 11/19/25 | 858 | 6 | Create Participant Profile Create ENS Work Queue
860 | Yes | Manually Scheduled | Establish Account Designee and Super Users | 1 hr | Wed 11/19/25 | Wed 11/19/25 | 859 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
861 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 4.62 days | Wed 11/19/25 | Tue 11/25/25 | 856 | 5
862 | Yes | Manually Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Wed 11/19/25 | Thu 11/20/25 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
863 | Yes | Manually Scheduled | Give Access to The Exchange | 1 day | Thu 11/20/25 | Fri 11/21/25 | 862 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
864 | Yes | Manually Scheduled | Identify desired ADT types needed by Participant | 1 day | Mon 11/24/25 | Mon 11/24/25 | 863 | 6
865 | Yes | Manually Scheduled | Determine Patient Panel Size | 1 day | Tue 11/25/25 | Tue 11/25/25 | 864 | 6
866 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 0 days | Tue 11/25/25 | Tue 11/25/25 | 865 | 6
867 | Yes | Auto Scheduled | Configure and test notifications in system | 0 days | Tue 11/25/25 | Tue 11/25/25 | 866 | 6
868 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 0 days | Tue 11/25/25 | Tue 11/25/25 |  | 6
869 | Yes | Auto Scheduled | User Credentialing and Setup | 0.5 days | Fri 11/28/25 | Fri 11/28/25 | 861 | 5
870 | Yes | Manually Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Fri 11/28/25 | Fri 11/28/25 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
871 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 0 days | Fri 11/28/25 | Fri 11/28/25 | 870 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
872 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 0 days | Fri 11/28/25 | Fri 11/28/25 | 871 | 6
873 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 0 days | Fri 11/28/25 | Fri 11/28/25 | 872 | 6
874 | Yes | Auto Scheduled | System Training, Testing, and Validation | 0 days | Fri 11/28/25 | Fri 11/28/25 | 869 | 5
875 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Fri 11/28/25 | Fri 11/28/25 |  | 6
876 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Fri 11/28/25 | Fri 11/28/25 | 148;875 | 6
877 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Fri 11/28/25 | Fri 11/28/25 | 876 | 6
878 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Fri 11/28/25 | Fri 11/28/25 | 877 | 6
879 | Yes | Auto Scheduled | Plan De Salud Menonita Inc. | 2 days | Fri 11/28/25 | Tue 12/02/25 | 855 | 4
880 | Yes | Auto Scheduled | Participant Creation & Project Charter | 0 days | Fri 11/28/25 | Fri 11/28/25 |  | 5
881 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 0 hrs | Fri 11/28/25 | Fri 11/28/25 |  | 6
882 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 0 hrs | Fri 11/28/25 | Fri 11/28/25 | 881 | 6
883 | Yes | Auto Scheduled | Enter Participant into the System | 0 hrs | Fri 11/28/25 | Fri 11/28/25 | 882 | 6 | Create Participant Profile Create ENS Work Queue
884 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 0 hrs | Fri 11/28/25 | Fri 11/28/25 | 883 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
885 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 2 days | Fri 11/28/25 | Tue 12/02/25 | 880 | 5
886 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 0 days | Fri 11/28/25 | Fri 11/28/25 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
887 | Yes | Auto Scheduled | Give Access to The Exchange | 0 days | Fri 11/28/25 | Fri 11/28/25 | 886 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
888 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 0 days | Fri 11/28/25 | Fri 11/28/25 | 887 | 6
889 | Yes | Auto Scheduled | Determine Patient Panel Size | 0 days | Fri 11/28/25 | Fri 11/28/25 | 888 | 6
890 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 0 days | Fri 11/28/25 | Fri 11/28/25 | 889 | 6
891 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Fri 11/28/25 | Mon 12/01/25 | 890 | 6
892 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Mon 12/01/25 | Tue 12/02/25 | 891 | 6
893 | Yes | Auto Scheduled | User Credentialing and Setup | 0 days | Tue 12/02/25 | Tue 12/02/25 | 885 | 5
894 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0 days | Tue 12/02/25 | Tue 12/02/25 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
895 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 0 days | Tue 12/02/25 | Tue 12/02/25 | 894 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
896 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 0 days | Tue 12/02/25 | Tue 12/02/25 | 895 | 6
897 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 0 days | Tue 12/02/25 | Tue 12/02/25 | 896 | 6
898 | Yes | Auto Scheduled | System Training, Testing, and Validation | 0 days | Tue 12/02/25 | Tue 12/02/25 | 893 | 5
899 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Tue 12/02/25 | Tue 12/02/25 |  | 6
900 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Tue 12/02/25 | Tue 12/02/25 | 148;899 | 6
901 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Tue 12/02/25 | Tue 12/02/25 | 900 | 6
902 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Tue 12/02/25 | Tue 12/02/25 | 901 | 6
903 | Yes | Auto Scheduled | Triple-S Salud Inc. | 40.88 days | Tue 12/02/25 | Wed 1/28/26 | 879 | 4
904 | Yes | Auto Scheduled | Participant Creation & Project Charter | 0 days | Tue 12/02/25 | Tue 12/02/25 |  | 5
905 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 0 hrs | Tue 12/02/25 | Tue 12/02/25 |  | 6
906 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 0 hrs | Tue 12/02/25 | Tue 12/02/25 | 905 | 6
907 | Yes | Auto Scheduled | Enter Participant into the System | 0 hrs | Tue 12/02/25 | Tue 12/02/25 | 906 | 6 | Create Participant Profile Create ENS Work Queue
908 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 0 hrs | Tue 12/02/25 | Tue 12/02/25 | 907 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
909 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 31.5 days | Tue 12/02/25 | Wed 1/14/26 | 904 | 5
910 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 0 days | Tue 12/02/25 | Tue 12/02/25 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
911 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Wed 1/07/26 | Wed 1/07/26 | 910 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
912 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Thu 1/08/26 | Thu 1/08/26 | 911 | 6
913 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Fri 1/09/26 | Fri 1/09/26 | 912 | 6
914 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Mon 1/12/26 | Mon 1/12/26 | 913 | 6
915 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Tue 1/13/26 | Tue 1/13/26 | 914 | 6
916 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Wed 1/14/26 | Wed 1/14/26 | 915 | 6
917 | Yes | Auto Scheduled | User Credentialing and Setup | 1.5 days | Thu 1/15/26 | Fri 1/16/26 | 909 | 5
918 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Thu 1/15/26 | Thu 1/15/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
919 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Thu 1/15/26 | Fri 1/16/26 | 918 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
920 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 0 days | Fri 1/16/26 | Fri 1/16/26 | 919 | 6
921 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 0 days | Fri 1/16/26 | Fri 1/16/26 | 920 | 6
922 | Yes | Auto Scheduled | System Training, Testing, and Validation | 7.88 days | Fri 1/16/26 | Wed 1/28/26 | 917 | 5
923 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Fri 1/16/26 | Fri 1/16/26 |  | 6
924 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Fri 1/16/26 | Fri 1/16/26 | 148;923 | 6
925 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Fri 1/16/26 | Fri 1/16/26 | 924 | 6
926 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Mon 1/26/26 | Wed 1/28/26 | 925 | 6
927 | Yes | Auto Scheduled | Centros 330 | 202.88 days | Wed 10/15/25 | Fri 7/24/26 |  | 3
928 | Yes | Auto Scheduled | ATLANTIC MEDICAL CENTER, INC. | 15.5 days | Wed 10/15/25 | Wed 11/05/25 |  | 4
929 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Wed 10/15/25 | Thu 10/16/25 |  | 5
930 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Wed 10/15/25 | Wed 10/15/25 |  | 6
931 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Wed 10/15/25 | Thu 10/16/25 | 930 | 6
932 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Thu 10/16/25 | Thu 10/16/25 | 931 | 6 | Create Participant Profile Create ENS Work Queue
933 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Thu 10/16/25 | Thu 10/16/25 | 932 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
934 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 5 days | Fri 10/17/25 | Thu 10/23/25 | 929 | 5
935 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Fri 10/17/25 | Fri 10/17/25 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
936 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Mon 10/20/25 | Mon 10/20/25 | 935 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
937 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Tue 10/21/25 | Tue 10/21/25 | 936 | 6
938 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Wed 10/22/25 | Wed 10/22/25 | 937 | 6
939 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Thu 10/23/25 | Thu 10/23/25 | 938 | 6
940 | Yes | Auto Scheduled | Configure and test notifications in system | 0 days | Thu 10/23/25 | Thu 10/23/25 | 939 | 6
941 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 0 days | Thu 10/23/25 | Thu 10/23/25 | 940 | 6
942 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Fri 10/24/25 | Wed 10/29/25 | 934 | 5
943 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Fri 10/24/25 | Fri 10/24/25 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
944 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Fri 10/24/25 | Mon 10/27/25 | 943 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
945 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Mon 10/27/25 | Tue 10/28/25 | 944 | 6
946 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Tue 10/28/25 | Wed 10/29/25 | 945 | 6
947 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Wed 10/29/25 | Wed 11/05/25 | 942 | 5
948 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Wed 10/29/25 | Wed 10/29/25 |  | 6
949 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Thu 10/30/25 | Thu 10/30/25 | 148;948 | 6
950 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Thu 10/30/25 | Mon 11/03/25 | 949 | 6
951 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Mon 11/03/25 | Wed 11/05/25 | 950 | 6
952 | Yes | Auto Scheduled | CAMUY HEALTH SERVICES, INC. | 14.88 days | Mon 11/03/25 | Fri 11/21/25 |  | 4
953 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Mon 11/03/25 | Tue 11/04/25 |  | 5
954 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Mon 11/03/25 | Mon 11/03/25 |  | 6
955 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Mon 11/03/25 | Tue 11/04/25 | 954 | 6
956 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Tue 11/04/25 | Tue 11/04/25 | 955 | 6 | Create Participant Profile Create ENS Work Queue
957 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Tue 11/04/25 | Tue 11/04/25 | 956 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
958 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 5 days | Tue 11/04/25 | Tue 11/11/25 | 953 | 5
959 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Tue 11/04/25 | Wed 11/05/25 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
960 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Wed 11/05/25 | Thu 11/06/25 | 959 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
961 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Thu 11/06/25 | Fri 11/07/25 | 960 | 6
962 | Yes | Auto Scheduled | Determine Patient Panel Size | 0 days | Fri 11/07/25 | Fri 11/07/25 | 961 | 6
963 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 0 days | Fri 11/07/25 | Fri 11/07/25 | 962 | 6
964 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Fri 11/07/25 | Mon 11/10/25 | 963 | 6
965 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Mon 11/10/25 | Tue 11/11/25 | 964 | 6
966 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Tue 11/11/25 | Fri 11/14/25 | 958 | 5
967 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Tue 11/11/25 | Tue 11/11/25 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
968 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Tue 11/11/25 | Wed 11/12/25 | 967 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
969 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Wed 11/12/25 | Thu 11/13/25 | 968 | 6
970 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Thu 11/13/25 | Fri 11/14/25 | 969 | 6
971 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Fri 11/14/25 | Fri 11/21/25 | 966 | 5
972 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Fri 11/14/25 | Mon 11/17/25 |  | 6
973 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Mon 11/17/25 | Mon 11/17/25 | 148;972 | 6
974 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Mon 11/17/25 | Wed 11/19/25 | 973 | 6
975 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Wed 11/19/25 | Fri 11/21/25 | 974 | 6
976 | Yes | Auto Scheduled | DR. JULIO PALMIERI FERRI FAMILY HEALTH CENTER, INC. | 16.88 days | Wed 11/19/25 | Thu 12/11/25 |  | 4
977 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Wed 11/19/25 | Thu 11/20/25 |  | 5
978 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Wed 11/19/25 | Wed 11/19/25 |  | 6
979 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Wed 11/19/25 | Thu 11/20/25 | 978 | 6
980 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Thu 11/20/25 | Thu 11/20/25 | 979 | 6 | Create Participant Profile Create ENS Work Queue
981 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Thu 11/20/25 | Thu 11/20/25 | 980 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
982 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Thu 11/20/25 | Mon 12/01/25 | 977 | 5
983 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Thu 11/20/25 | Fri 11/21/25 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
984 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Fri 11/21/25 | Mon 11/24/25 | 983 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
985 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Mon 11/24/25 | Tue 11/25/25 | 984 | 6
986 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Tue 11/25/25 | Wed 11/26/25 | 985 | 6
987 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Wed 11/26/25 | Thu 11/27/25 | 986 | 6
988 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Thu 11/27/25 | Fri 11/28/25 | 987 | 6
989 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Fri 11/28/25 | Mon 12/01/25 | 988 | 6
990 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Mon 12/01/25 | Thu 12/04/25 | 982 | 5
991 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Mon 12/01/25 | Mon 12/01/25 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
992 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Mon 12/01/25 | Tue 12/02/25 | 991 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
993 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Tue 12/02/25 | Wed 12/03/25 | 992 | 6
994 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Wed 12/03/25 | Thu 12/04/25 | 993 | 6
995 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Thu 12/04/25 | Thu 12/11/25 | 990 | 5
996 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Thu 12/04/25 | Fri 12/05/25 |  | 6
997 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Fri 12/05/25 | Fri 12/05/25 | 994;996;148 | 6
998 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Fri 12/05/25 | Tue 12/09/25 | 997 | 6
999 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Tue 12/09/25 | Thu 12/11/25 | 998 | 6
1000 | Yes | Auto Scheduled | CENTER FOR PRIMARY HEALTH SERVICES, INC. | 15 days | Mon 1/05/26 | Fri 1/23/26 |  | 4
1001 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Mon 1/05/26 | Tue 1/06/26 |  | 5
1002 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Mon 1/05/26 | Mon 1/05/26 |  | 6
1003 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Mon 1/05/26 | Tue 1/06/26 | 1002 | 6
1004 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Tue 1/06/26 | Tue 1/06/26 | 1003 | 6 | Create Participant Profile Create ENS Work Queue
1005 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Tue 1/06/26 | Tue 1/06/26 | 1004 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1006 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 5 days | Tue 1/06/26 | Tue 1/13/26 | 1001 | 5
1007 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Tue 1/06/26 | Wed 1/07/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1008 | Yes | Auto Scheduled | Give Access to The Exchange | 0 days | Wed 1/07/26 | Wed 1/07/26 | 1007 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1009 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 0 days | Wed 1/07/26 | Wed 1/07/26 | 1008 | 6
1010 | Yes | Auto Scheduled | Determine Patient Panel Size | 0 days | Wed 1/07/26 | Wed 1/07/26 | 1009 | 6
1011 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 0 days | Wed 1/07/26 | Wed 1/07/26 | 1010 | 6
1012 | Yes | Auto Scheduled | Configure and test notifications in system | 0 days | Tue 1/13/26 | Tue 1/13/26 | 1011 | 6
1013 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 0 days | Tue 1/13/26 | Tue 1/13/26 | 1012 | 6
1014 | Yes | Auto Scheduled | User Credentialing and Setup | 4.49 days | Tue 1/13/26 | Mon 1/19/26 | 1006 | 5
1015 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Tue 1/13/26 | Tue 1/13/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1016 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 0 days | Thu 1/15/26 | Thu 1/15/26 | 1015 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1017 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Thu 1/15/26 | Fri 1/16/26 | 1016 | 6
1018 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Fri 1/16/26 | Mon 1/19/26 | 1017 | 6
1019 | Yes | Auto Scheduled | System Training, Testing, and Validation | 3.12 days | Tue 1/20/26 | Fri 1/23/26 | 1014 | 5
1020 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Tue 1/20/26 | Wed 1/21/26 |  | 6
1021 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Wed 1/21/26 | Wed 1/21/26 | 1018;1020;148 | 6
1022 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Thu 1/22/26 | Fri 1/23/26 | 1021 | 6
1023 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Fri 1/23/26 | Fri 1/23/26 | 1022 | 6
1024 | Yes | Auto Scheduled | PATILLAS PRIMARY HEALTH SERVICES CENTER, INC. | 16.88 days | Fri 12/05/25 | Mon 12/29/25 |  | 4
1025 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Fri 12/05/25 | Mon 12/08/25 |  | 5
1026 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Fri 12/05/25 | Fri 12/05/25 |  | 6
1027 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Fri 12/05/25 | Mon 12/08/25 | 1026 | 6
1028 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Mon 12/08/25 | Mon 12/08/25 | 1027 | 6 | Create Participant Profile Create ENS Work Queue
1029 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Mon 12/08/25 | Mon 12/08/25 | 1028 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1030 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Mon 12/08/25 | Wed 12/17/25 | 1025 | 5
1031 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Mon 12/08/25 | Tue 12/09/25 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1032 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Tue 12/09/25 | Wed 12/10/25 | 1031 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1033 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Wed 12/10/25 | Thu 12/11/25 | 1032 | 6
1034 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Thu 12/11/25 | Fri 12/12/25 | 1033 | 6
1035 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Fri 12/12/25 | Mon 12/15/25 | 1034 | 6
1036 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Mon 12/15/25 | Tue 12/16/25 | 1035 | 6
1037 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Tue 12/16/25 | Wed 12/17/25 | 1036 | 6
1038 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Wed 12/17/25 | Mon 12/22/25 | 1030 | 5
1039 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Wed 12/17/25 | Wed 12/17/25 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1040 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Wed 12/17/25 | Thu 12/18/25 | 1039 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1041 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Thu 12/18/25 | Fri 12/19/25 | 1040 | 6
1042 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Fri 12/19/25 | Mon 12/22/25 | 1041 | 6
1043 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Mon 12/22/25 | Mon 12/29/25 | 1038 | 5
1044 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Mon 12/22/25 | Tue 12/23/25 |  | 6
1045 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Tue 12/23/25 | Tue 12/23/25 | 1042;1044;148 | 6
1046 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Tue 12/23/25 | Thu 12/25/25 | 1045 | 6
1047 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Thu 12/25/25 | Mon 12/29/25 | 1046 | 6
1048 | Yes | Auto Scheduled | INTEGRATED HEALTH SERVICES CENTERS, INC. | 16.88 days | Mon 12/29/25 | Tue 1/20/26 |  | 4
1049 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Mon 12/29/25 | Tue 12/30/25 |  | 5
1050 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Mon 12/29/25 | Mon 12/29/25 |  | 6
1051 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Mon 12/29/25 | Tue 12/30/25 | 1050 | 6
1052 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Tue 12/30/25 | Tue 12/30/25 | 1051 | 6 | Create Participant Profile Create ENS Work Queue
1053 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Tue 12/30/25 | Tue 12/30/25 | 1052 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1054 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Tue 12/30/25 | Thu 1/08/26 | 1049 | 5
1055 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Tue 12/30/25 | Wed 12/31/25 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1056 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Wed 12/31/25 | Thu 1/01/26 | 1055 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1057 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Thu 1/01/26 | Fri 1/02/26 | 1056 | 6
1058 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Fri 1/02/26 | Mon 1/05/26 | 1057 | 6
1059 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Mon 1/05/26 | Tue 1/06/26 | 1058 | 6
1060 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Tue 1/06/26 | Wed 1/07/26 | 1059 | 6
1061 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Wed 1/07/26 | Thu 1/08/26 | 1060 | 6
1062 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Thu 1/08/26 | Tue 1/13/26 | 1054 | 5
1063 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Thu 1/08/26 | Thu 1/08/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1064 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Thu 1/08/26 | Fri 1/09/26 | 1063 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1065 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Fri 1/09/26 | Mon 1/12/26 | 1064 | 6
1066 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Mon 1/12/26 | Tue 1/13/26 | 1065 | 6
1067 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Tue 1/13/26 | Tue 1/20/26 | 1062 | 5
1068 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Tue 1/13/26 | Wed 1/14/26 |  | 6
1069 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Wed 1/14/26 | Wed 1/14/26 | 1066;1068;148 | 6
1070 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Wed 1/14/26 | Fri 1/16/26 | 1069 | 6
1071 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Fri 1/16/26 | Tue 1/20/26 | 1070 | 6
1072 | Yes | Auto Scheduled | COMMUNITY HEALTH FOUNDATION OF PUERTO RICO | 16.88 days | Wed 1/14/26 | Thu 2/05/26 |  | 4
1073 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Wed 1/14/26 | Thu 1/15/26 |  | 5
1074 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Wed 1/14/26 | Wed 1/14/26 |  | 6
1075 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Wed 1/14/26 | Thu 1/15/26 | 1074 | 6
1076 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Thu 1/15/26 | Thu 1/15/26 | 1075 | 6 | Create Participant Profile Create ENS Work Queue
1077 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Thu 1/15/26 | Thu 1/15/26 | 1076 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1078 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Thu 1/15/26 | Mon 1/26/26 | 1073 | 5
1079 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Thu 1/15/26 | Fri 1/16/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1080 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Fri 1/16/26 | Mon 1/19/26 | 1079 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1081 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Mon 1/19/26 | Tue 1/20/26 | 1080 | 6
1082 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Tue 1/20/26 | Wed 1/21/26 | 1081 | 6
1083 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Wed 1/21/26 | Thu 1/22/26 | 1082 | 6
1084 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Thu 1/22/26 | Fri 1/23/26 | 1083 | 6
1085 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Fri 1/23/26 | Mon 1/26/26 | 1084 | 6
1086 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Mon 1/26/26 | Thu 1/29/26 | 1078 | 5
1087 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Mon 1/26/26 | Mon 1/26/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1088 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Mon 1/26/26 | Tue 1/27/26 | 1087 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1089 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Tue 1/27/26 | Wed 1/28/26 | 1088 | 6
1090 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Wed 1/28/26 | Thu 1/29/26 | 1089 | 6
1091 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Thu 1/29/26 | Thu 2/05/26 | 1086 | 5
1092 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Thu 1/29/26 | Fri 1/30/26 |  | 6
1093 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Fri 1/30/26 | Fri 1/30/26 | 1090;1092;148 | 6
1094 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Fri 1/30/26 | Tue 2/03/26 | 1093 | 6
1095 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Tue 2/03/26 | Thu 2/05/26 | 1094 | 6
1096 | Yes | Auto Scheduled | INTEGRAL HEALTH COUNCIL OF LOÍZA, INC. | 16.88 days | Fri 1/30/26 | Mon 2/23/26 |  | 4
1097 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Fri 1/30/26 | Mon 2/02/26 |  | 5
1098 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Fri 1/30/26 | Fri 1/30/26 |  | 6
1099 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Fri 1/30/26 | Mon 2/02/26 | 1098 | 6
1100 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Mon 2/02/26 | Mon 2/02/26 | 1099 | 6 | Create Participant Profile Create ENS Work Queue
1101 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Mon 2/02/26 | Mon 2/02/26 | 1100 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1102 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Mon 2/02/26 | Wed 2/11/26 | 1097 | 5
1103 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Mon 2/02/26 | Tue 2/03/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1104 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Tue 2/03/26 | Wed 2/04/26 | 1103 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1105 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Wed 2/04/26 | Thu 2/05/26 | 1104 | 6
1106 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Thu 2/05/26 | Fri 2/06/26 | 1105 | 6
1107 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Fri 2/06/26 | Mon 2/09/26 | 1106 | 6
1108 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Mon 2/09/26 | Tue 2/10/26 | 1107 | 6
1109 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Tue 2/10/26 | Wed 2/11/26 | 1108 | 6
1110 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Wed 2/11/26 | Mon 2/16/26 | 1102 | 5
1111 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Wed 2/11/26 | Wed 2/11/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1112 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Wed 2/11/26 | Thu 2/12/26 | 1111 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1113 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Thu 2/12/26 | Fri 2/13/26 | 1112 | 6
1114 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Fri 2/13/26 | Mon 2/16/26 | 1113 | 6
1115 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Mon 2/16/26 | Mon 2/23/26 | 1110 | 5
1116 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Mon 2/16/26 | Tue 2/17/26 |  | 6
1117 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Tue 2/17/26 | Tue 2/17/26 | 1114;1116;148 | 6
1118 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Tue 2/17/26 | Thu 2/19/26 | 1117 | 6
1119 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Thu 2/19/26 | Mon 2/23/26 | 1118 | 6
1120 | Yes | Auto Scheduled | HATILLO MEDICAL SERVICES CORPORATION, INC. | 16.88 days | Tue 2/17/26 | Wed 3/11/26 |  | 4
1121 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Tue 2/17/26 | Wed 2/18/26 |  | 5
1122 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Tue 2/17/26 | Tue 2/17/26 |  | 6
1123 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Tue 2/17/26 | Wed 2/18/26 | 1122 | 6
1124 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Wed 2/18/26 | Wed 2/18/26 | 1123 | 6 | Create Participant Profile Create ENS Work Queue
1125 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Wed 2/18/26 | Wed 2/18/26 | 1124 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1126 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Wed 2/18/26 | Fri 2/27/26 | 1121 | 5
1127 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Wed 2/18/26 | Thu 2/19/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1128 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Thu 2/19/26 | Fri 2/20/26 | 1127 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1129 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Fri 2/20/26 | Mon 2/23/26 | 1128 | 6
1130 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Mon 2/23/26 | Tue 2/24/26 | 1129 | 6
1131 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Tue 2/24/26 | Wed 2/25/26 | 1130 | 6
1132 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Wed 2/25/26 | Thu 2/26/26 | 1131 | 6
1133 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Thu 2/26/26 | Fri 2/27/26 | 1132 | 6
1134 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Fri 2/27/26 | Wed 3/04/26 | 1126 | 5
1135 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Fri 2/27/26 | Fri 2/27/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1136 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Fri 2/27/26 | Mon 3/02/26 | 1135 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1137 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Mon 3/02/26 | Tue 3/03/26 | 1136 | 6
1138 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Tue 3/03/26 | Wed 3/04/26 | 1137 | 6
1139 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Wed 3/04/26 | Wed 3/11/26 | 1134 | 5
1140 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Wed 3/04/26 | Thu 3/05/26 |  | 6
1141 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Thu 3/05/26 | Thu 3/05/26 | 1138;1140;148 | 6
1142 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Thu 3/05/26 | Mon 3/09/26 | 1141 | 6
1143 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Mon 3/09/26 | Wed 3/11/26 | 1142 | 6
1144 | Yes | Auto Scheduled | CORPORACIÓN SANOS, INC. | 16.88 days | Thu 3/05/26 | Fri 3/27/26 |  | 4
1145 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Thu 3/05/26 | Fri 3/06/26 |  | 5
1146 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Thu 3/05/26 | Thu 3/05/26 |  | 6
1147 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Thu 3/05/26 | Fri 3/06/26 | 1146 | 6
1148 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Fri 3/06/26 | Fri 3/06/26 | 1147 | 6 | Create Participant Profile Create ENS Work Queue
1149 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Fri 3/06/26 | Fri 3/06/26 | 1148 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1150 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Fri 3/06/26 | Tue 3/17/26 | 1145 | 5
1151 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Fri 3/06/26 | Mon 3/09/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1152 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Mon 3/09/26 | Tue 3/10/26 | 1151 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1153 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Tue 3/10/26 | Wed 3/11/26 | 1152 | 6
1154 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Wed 3/11/26 | Thu 3/12/26 | 1153 | 6
1155 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Thu 3/12/26 | Fri 3/13/26 | 1154 | 6
1156 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Fri 3/13/26 | Mon 3/16/26 | 1155 | 6
1157 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Mon 3/16/26 | Tue 3/17/26 | 1156 | 6
1158 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Tue 3/17/26 | Fri 3/20/26 | 1150 | 5
1159 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Tue 3/17/26 | Tue 3/17/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1160 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Tue 3/17/26 | Wed 3/18/26 | 1159 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1161 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Wed 3/18/26 | Thu 3/19/26 | 1160 | 6
1162 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Thu 3/19/26 | Fri 3/20/26 | 1161 | 6
1163 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Fri 3/20/26 | Fri 3/27/26 | 1158 | 5
1164 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Fri 3/20/26 | Mon 3/23/26 |  | 6
1165 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Mon 3/23/26 | Mon 3/23/26 | 1162;148;1164 | 6
1166 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Mon 3/23/26 | Wed 3/25/26 | 1165 | 6
1167 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Wed 3/25/26 | Fri 3/27/26 | 1166 | 6
1168 | Yes | Auto Scheduled | COSSMA, INC. | 11.88 days | Mon 3/23/26 | Tue 4/07/26 |  | 4
1169 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Mon 3/23/26 | Tue 3/24/26 |  | 5
1170 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Mon 3/23/26 | Mon 3/23/26 |  | 6
1171 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Mon 3/23/26 | Tue 3/24/26 | 1170 | 6
1172 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Tue 3/24/26 | Tue 3/24/26 | 1171 | 6 | Create Participant Profile Create ENS Work Queue
1173 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Tue 3/24/26 | Tue 3/24/26 | 1172 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1174 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Tue 3/24/26 | Thu 4/02/26 | 1169 | 5
1175 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Tue 3/24/26 | Wed 3/25/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1176 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Wed 3/25/26 | Thu 3/26/26 | 1175 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1177 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Thu 3/26/26 | Fri 3/27/26 | 1176 | 6
1178 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Fri 3/27/26 | Mon 3/30/26 | 1177 | 6
1179 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Mon 3/30/26 | Tue 3/31/26 | 1178 | 6
1180 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Tue 3/31/26 | Wed 4/01/26 | 1179 | 6
1181 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Wed 4/01/26 | Thu 4/02/26 | 1180 | 6
1182 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Thu 4/02/26 | Tue 4/07/26 | 1174 | 5
1183 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Thu 4/02/26 | Thu 4/02/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1184 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Thu 4/02/26 | Fri 4/03/26 | 1183 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1185 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Fri 4/03/26 | Mon 4/06/26 | 1184 | 6
1186 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Mon 4/06/26 | Tue 4/07/26 | 1185 | 6
1187 | Yes | Auto Scheduled | System Training, Testing, and Validation | 0 days | Tue 4/07/26 | Tue 4/07/26 | 1182 | 5
1188 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Tue 4/07/26 | Tue 4/07/26 |  | 6
1189 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Tue 4/07/26 | Tue 4/07/26 | 1186;1188;148 | 6
1190 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Tue 4/07/26 | Tue 4/07/26 | 1189 | 6
1191 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Tue 4/07/26 | Tue 4/07/26 | 1190 | 6
1192 | Yes | Auto Scheduled | COSTA SALUD COMMUNITY HEALTH CENTERS | 11.88 days | Wed 4/08/26 | Thu 4/23/26 |  | 4
1193 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Wed 4/08/26 | Thu 4/09/26 |  | 5
1194 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Wed 4/08/26 | Wed 4/08/26 |  | 6
1195 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Wed 4/08/26 | Thu 4/09/26 | 1194 | 6
1196 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Thu 4/09/26 | Thu 4/09/26 | 1195 | 6 | Create Participant Profile Create ENS Work Queue
1197 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Thu 4/09/26 | Thu 4/09/26 | 1196 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1198 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Thu 4/09/26 | Mon 4/20/26 | 1193 | 5
1199 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Thu 4/09/26 | Fri 4/10/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1200 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Fri 4/10/26 | Mon 4/13/26 | 1199 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1201 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Mon 4/13/26 | Tue 4/14/26 | 1200 | 6
1202 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Tue 4/14/26 | Wed 4/15/26 | 1201 | 6
1203 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Wed 4/15/26 | Thu 4/16/26 | 1202 | 6
1204 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Thu 4/16/26 | Fri 4/17/26 | 1203 | 6
1205 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Fri 4/17/26 | Mon 4/20/26 | 1204 | 6
1206 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Mon 4/20/26 | Thu 4/23/26 | 1198 | 5
1207 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Mon 4/20/26 | Mon 4/20/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1208 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Mon 4/20/26 | Tue 4/21/26 | 1207 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1209 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Tue 4/21/26 | Wed 4/22/26 | 1208 | 6
1210 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Wed 4/22/26 | Thu 4/23/26 | 1209 | 6
1211 | Yes | Auto Scheduled | System Training, Testing, and Validation | 0 days | Thu 4/23/26 | Thu 4/23/26 | 1206 | 5
1212 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Thu 4/23/26 | Thu 4/23/26 |  | 6
1213 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Thu 4/23/26 | Thu 4/23/26 | 1210;1212;148 | 6
1214 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Thu 4/23/26 | Thu 4/23/26 | 1213 | 6
1215 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Thu 4/23/26 | Thu 4/23/26 | 1214 | 6
1216 | Yes | Auto Scheduled | HEALTHPROMED INC. | 11.88 days | Fri 4/24/26 | Mon 5/11/26 |  | 4
1217 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Fri 4/24/26 | Mon 4/27/26 |  | 5
1218 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Fri 4/24/26 | Fri 4/24/26 |  | 6
1219 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Fri 4/24/26 | Mon 4/27/26 | 1218 | 6
1220 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Mon 4/27/26 | Mon 4/27/26 | 1219 | 6 | Create Participant Profile Create ENS Work Queue
1221 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Mon 4/27/26 | Mon 4/27/26 | 1220 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1222 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Mon 4/27/26 | Wed 5/06/26 | 1217 | 5
1223 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Mon 4/27/26 | Tue 4/28/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1224 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Tue 4/28/26 | Wed 4/29/26 | 1223 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1225 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Wed 4/29/26 | Thu 4/30/26 | 1224 | 6
1226 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Thu 4/30/26 | Fri 5/01/26 | 1225 | 6
1227 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Fri 5/01/26 | Mon 5/04/26 | 1226 | 6
1228 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Mon 5/04/26 | Tue 5/05/26 | 1227 | 6
1229 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Tue 5/05/26 | Wed 5/06/26 | 1228 | 6
1230 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Wed 5/06/26 | Mon 5/11/26 | 1222 | 5
1231 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Wed 5/06/26 | Wed 5/06/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1232 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Wed 5/06/26 | Thu 5/07/26 | 1231 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1233 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Thu 5/07/26 | Fri 5/08/26 | 1232 | 6
1234 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Fri 5/08/26 | Mon 5/11/26 | 1233 | 6
1235 | Yes | Auto Scheduled | System Training, Testing, and Validation | 0 days | Mon 5/11/26 | Mon 5/11/26 | 1230 | 5
1236 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Mon 5/11/26 | Mon 5/11/26 |  | 6
1237 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Mon 5/11/26 | Mon 5/11/26 | 1234;1236;148 | 6
1238 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Mon 5/11/26 | Mon 5/11/26 | 1237 | 6
1239 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Mon 5/11/26 | Mon 5/11/26 | 1238 | 6
1240 | Yes | Auto Scheduled | CASTAÑER GENERAL HOSPITAL, INC. | 11.88 days | Tue 5/12/26 | Wed 5/27/26 |  | 4
1241 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Tue 5/12/26 | Wed 5/13/26 |  | 5
1242 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Tue 5/12/26 | Tue 5/12/26 |  | 6
1243 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Tue 5/12/26 | Wed 5/13/26 | 1242 | 6
1244 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Wed 5/13/26 | Wed 5/13/26 | 1243 | 6 | Create Participant Profile Create ENS Work Queue
1245 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Wed 5/13/26 | Wed 5/13/26 | 1244 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1246 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Wed 5/13/26 | Fri 5/22/26 | 1241 | 5
1247 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Wed 5/13/26 | Thu 5/14/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1248 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Thu 5/14/26 | Fri 5/15/26 | 1247 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1249 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Fri 5/15/26 | Mon 5/18/26 | 1248 | 6
1250 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Mon 5/18/26 | Tue 5/19/26 | 1249 | 6
1251 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Tue 5/19/26 | Wed 5/20/26 | 1250 | 6
1252 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Wed 5/20/26 | Thu 5/21/26 | 1251 | 6
1253 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Thu 5/21/26 | Fri 5/22/26 | 1252 | 6
1254 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Fri 5/22/26 | Wed 5/27/26 | 1246 | 5
1255 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Fri 5/22/26 | Fri 5/22/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1256 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Fri 5/22/26 | Mon 5/25/26 | 1255 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1257 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Mon 5/25/26 | Tue 5/26/26 | 1256 | 6
1258 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Tue 5/26/26 | Wed 5/27/26 | 1257 | 6
1259 | Yes | Auto Scheduled | System Training, Testing, and Validation | 0 days | Wed 5/27/26 | Wed 5/27/26 | 1254 | 5
1260 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Wed 5/27/26 | Wed 5/27/26 |  | 6
1261 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Wed 5/27/26 | Wed 5/27/26 | 1258;1260;148 | 6
1262 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Wed 5/27/26 | Wed 5/27/26 | 1261 | 6
1263 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Wed 5/27/26 | Wed 5/27/26 | 1262 | 6
1264 | Yes | Auto Scheduled | MED CENTER | 11.88 days | Thu 5/28/26 | Fri 6/12/26 |  | 4
1265 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Thu 5/28/26 | Fri 5/29/26 |  | 5
1266 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Thu 5/28/26 | Thu 5/28/26 |  | 6
1267 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Thu 5/28/26 | Fri 5/29/26 | 1266 | 6
1268 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Fri 5/29/26 | Fri 5/29/26 | 1267 | 6 | Create Participant Profile Create ENS Work Queue
1269 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Fri 5/29/26 | Fri 5/29/26 | 1268 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1270 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Fri 5/29/26 | Tue 6/09/26 | 1265 | 5
1271 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Fri 5/29/26 | Mon 6/01/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1272 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Mon 6/01/26 | Tue 6/02/26 | 1271 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1273 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Tue 6/02/26 | Wed 6/03/26 | 1272 | 6
1274 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Wed 6/03/26 | Thu 6/04/26 | 1273 | 6
1275 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Thu 6/04/26 | Fri 6/05/26 | 1274 | 6
1276 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Fri 6/05/26 | Mon 6/08/26 | 1275 | 6
1277 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Mon 6/08/26 | Tue 6/09/26 | 1276 | 6
1278 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Tue 6/09/26 | Fri 6/12/26 | 1270 | 5
1279 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Tue 6/09/26 | Tue 6/09/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1280 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Tue 6/09/26 | Wed 6/10/26 | 1279 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1281 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Wed 6/10/26 | Thu 6/11/26 | 1280 | 6
1282 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Thu 6/11/26 | Fri 6/12/26 | 1281 | 6
1283 | Yes | Auto Scheduled | System Training, Testing, and Validation | 0 days | Fri 6/12/26 | Fri 6/12/26 | 1278 | 5
1284 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Fri 6/12/26 | Fri 6/12/26 |  | 6
1285 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Fri 6/12/26 | Fri 6/12/26 | 1282;1284;148 | 6
1286 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Fri 6/12/26 | Fri 6/12/26 | 1285 | 6
1287 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Fri 6/12/26 | Fri 6/12/26 | 1286 | 6
1288 | Yes | Auto Scheduled | MIGRANT HEALTH CENTER,INC. | 11.88 days | Mon 6/15/26 | Tue 6/30/26 |  | 4
1289 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Mon 6/15/26 | Tue 6/16/26 |  | 5
1290 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Mon 6/15/26 | Mon 6/15/26 |  | 6
1291 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Mon 6/15/26 | Tue 6/16/26 | 1290 | 6
1292 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Tue 6/16/26 | Tue 6/16/26 | 1291 | 6 | Create Participant Profile Create ENS Work Queue
1293 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Tue 6/16/26 | Tue 6/16/26 | 1292 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1294 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Tue 6/16/26 | Thu 6/25/26 | 1289 | 5
1295 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Tue 6/16/26 | Wed 6/17/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1296 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Wed 6/17/26 | Thu 6/18/26 | 1295 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1297 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Thu 6/18/26 | Fri 6/19/26 | 1296 | 6
1298 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Fri 6/19/26 | Mon 6/22/26 | 1297 | 6
1299 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Mon 6/22/26 | Tue 6/23/26 | 1298 | 6
1300 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Tue 6/23/26 | Wed 6/24/26 | 1299 | 6
1301 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Wed 6/24/26 | Thu 6/25/26 | 1300 | 6
1302 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Thu 6/25/26 | Tue 6/30/26 | 1294 | 5
1303 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Thu 6/25/26 | Thu 6/25/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1304 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Thu 6/25/26 | Fri 6/26/26 | 1303 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1305 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Fri 6/26/26 | Mon 6/29/26 | 1304 | 6
1306 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Mon 6/29/26 | Tue 6/30/26 | 1305 | 6
1307 | Yes | Auto Scheduled | System Training, Testing, and Validation | 0 days | Tue 6/30/26 | Tue 6/30/26 | 1302 | 5
1308 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Tue 6/30/26 | Tue 6/30/26 |  | 6
1309 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Tue 6/30/26 | Tue 6/30/26 | 1306;1308;148 | 6
1310 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Tue 6/30/26 | Tue 6/30/26 | 1309 | 6
1311 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Tue 6/30/26 | Tue 6/30/26 | 1310 | 6
1312 | Yes | Auto Scheduled | SAN JUAN HEALTH CARE FOR THE HOMELESS | 16.88 days | Mon 3/30/26 | Tue 4/21/26 |  | 4
1313 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Mon 3/30/26 | Tue 3/31/26 |  | 5
1314 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Mon 3/30/26 | Mon 3/30/26 |  | 6
1315 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Mon 3/30/26 | Tue 3/31/26 | 1314 | 6
1316 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Tue 3/31/26 | Tue 3/31/26 | 1315 | 6 | Create Participant Profile Create ENS Work Queue
1317 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Tue 3/31/26 | Tue 3/31/26 | 1316 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1318 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Tue 3/31/26 | Thu 4/09/26 | 1313 | 5
1319 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Tue 3/31/26 | Wed 4/01/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1320 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Wed 4/01/26 | Thu 4/02/26 | 1319 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1321 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Thu 4/02/26 | Fri 4/03/26 | 1320 | 6
1322 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Fri 4/03/26 | Mon 4/06/26 | 1321 | 6
1323 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Mon 4/06/26 | Tue 4/07/26 | 1322 | 6
1324 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Tue 4/07/26 | Wed 4/08/26 | 1323 | 6
1325 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Wed 4/08/26 | Thu 4/09/26 | 1324 | 6
1326 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Thu 4/09/26 | Tue 4/14/26 | 1318 | 5
1327 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Thu 4/09/26 | Thu 4/09/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1328 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Thu 4/09/26 | Fri 4/10/26 | 1327 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1329 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Fri 4/10/26 | Mon 4/13/26 | 1328 | 6
1330 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Mon 4/13/26 | Tue 4/14/26 | 1329 | 6
1331 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Tue 4/14/26 | Tue 4/21/26 | 1326 | 5
1332 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Tue 4/14/26 | Wed 4/15/26 |  | 6
1333 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Wed 4/15/26 | Wed 4/15/26 | 1330;1332;148 | 6
1334 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Wed 4/15/26 | Fri 4/17/26 | 1333 | 6
1335 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Fri 4/17/26 | Tue 4/21/26 | 1334 | 6
1336 | Yes | Auto Scheduled | PRYMED, INC. | 16.88 days | Wed 4/22/26 | Thu 5/14/26 |  | 4
1337 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Wed 4/22/26 | Thu 4/23/26 |  | 5
1338 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Wed 4/22/26 | Wed 4/22/26 |  | 6
1339 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Wed 4/22/26 | Thu 4/23/26 | 1338 | 6
1340 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Thu 4/23/26 | Thu 4/23/26 | 1339 | 6 | Create Participant Profile Create ENS Work Queue
1341 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Thu 4/23/26 | Thu 4/23/26 | 1340 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1342 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Thu 4/23/26 | Mon 5/04/26 | 1337 | 5
1343 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Thu 4/23/26 | Fri 4/24/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1344 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Fri 4/24/26 | Mon 4/27/26 | 1343 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1345 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Mon 4/27/26 | Tue 4/28/26 | 1344 | 6
1346 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Tue 4/28/26 | Wed 4/29/26 | 1345 | 6
1347 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Wed 4/29/26 | Thu 4/30/26 | 1346 | 6
1348 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Thu 4/30/26 | Fri 5/01/26 | 1347 | 6
1349 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Fri 5/01/26 | Mon 5/04/26 | 1348 | 6
1350 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Mon 5/04/26 | Thu 5/07/26 | 1342 | 5
1351 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Mon 5/04/26 | Mon 5/04/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1352 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Mon 5/04/26 | Tue 5/05/26 | 1351 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1353 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Tue 5/05/26 | Wed 5/06/26 | 1352 | 6
1354 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Wed 5/06/26 | Thu 5/07/26 | 1353 | 6
1355 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Thu 5/07/26 | Thu 5/14/26 | 1350 | 5
1356 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Thu 5/07/26 | Fri 5/08/26 |  | 6
1357 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Fri 5/08/26 | Fri 5/08/26 | 1354;1356;148 | 6
1358 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Fri 5/08/26 | Tue 5/12/26 | 1357 | 6
1359 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Tue 5/12/26 | Thu 5/14/26 | 1358 | 6
1360 | Yes | Auto Scheduled | INTEGRATIVE HEALTH IN THE MOUNTAINS, INC. | 16.88 days | Fri 5/15/26 | Mon 6/08/26 |  | 4
1361 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Fri 5/15/26 | Mon 5/18/26 |  | 5
1362 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Fri 5/15/26 | Fri 5/15/26 |  | 6
1363 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Fri 5/15/26 | Mon 5/18/26 | 1362 | 6
1364 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Mon 5/18/26 | Mon 5/18/26 | 1363 | 6 | Create Participant Profile Create ENS Work Queue
1365 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Mon 5/18/26 | Mon 5/18/26 | 1364 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1366 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Mon 5/18/26 | Wed 5/27/26 | 1361 | 5
1367 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Mon 5/18/26 | Tue 5/19/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1368 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Tue 5/19/26 | Wed 5/20/26 | 1367 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1369 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Wed 5/20/26 | Thu 5/21/26 | 1368 | 6
1370 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Thu 5/21/26 | Fri 5/22/26 | 1369 | 6
1371 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Fri 5/22/26 | Mon 5/25/26 | 1370 | 6
1372 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Mon 5/25/26 | Tue 5/26/26 | 1371 | 6
1373 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Tue 5/26/26 | Wed 5/27/26 | 1372 | 6
1374 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Wed 5/27/26 | Mon 6/01/26 | 1366 | 5
1375 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Wed 5/27/26 | Wed 5/27/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1376 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Wed 5/27/26 | Thu 5/28/26 | 1375 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1377 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Thu 5/28/26 | Fri 5/29/26 | 1376 | 6
1378 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Fri 5/29/26 | Mon 6/01/26 | 1377 | 6
1379 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Mon 6/01/26 | Mon 6/08/26 | 1374 | 5
1380 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Mon 6/01/26 | Tue 6/02/26 |  | 6
1381 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Tue 6/02/26 | Tue 6/02/26 | 1378;1380;148 | 6
1382 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Tue 6/02/26 | Thu 6/04/26 | 1381 | 6
1383 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Thu 6/04/26 | Mon 6/08/26 | 1382 | 6
1384 | Yes | Auto Scheduled | PUERTO RICO COMMUNITY NETWORK FOR CLINICAL RESEARCH (CONCRA) | 16.88 days | Tue 6/09/26 | Wed 7/01/26 |  | 4
1385 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Tue 6/09/26 | Wed 6/10/26 |  | 5
1386 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Tue 6/09/26 | Tue 6/09/26 |  | 6
1387 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Tue 6/09/26 | Wed 6/10/26 | 1386 | 6
1388 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Wed 6/10/26 | Wed 6/10/26 | 1387 | 6 | Create Participant Profile Create ENS Work Queue
1389 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Wed 6/10/26 | Wed 6/10/26 | 1388 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1390 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Wed 6/10/26 | Fri 6/19/26 | 1385 | 5
1391 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Wed 6/10/26 | Thu 6/11/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1392 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Thu 6/11/26 | Fri 6/12/26 | 1391 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1393 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Fri 6/12/26 | Mon 6/15/26 | 1392 | 6
1394 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Mon 6/15/26 | Tue 6/16/26 | 1393 | 6
1395 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Tue 6/16/26 | Wed 6/17/26 | 1394 | 6
1396 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Wed 6/17/26 | Thu 6/18/26 | 1395 | 6
1397 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Thu 6/18/26 | Fri 6/19/26 | 1396 | 6
1398 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Fri 6/19/26 | Wed 6/24/26 | 1390 | 5
1399 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Fri 6/19/26 | Fri 6/19/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1400 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Fri 6/19/26 | Mon 6/22/26 | 1399 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1401 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Mon 6/22/26 | Tue 6/23/26 | 1400 | 6
1402 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Tue 6/23/26 | Wed 6/24/26 | 1401 | 6
1403 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Wed 6/24/26 | Wed 7/01/26 | 1398 | 5
1404 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Wed 6/24/26 | Thu 6/25/26 |  | 6
1405 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Thu 6/25/26 | Thu 6/25/26 | 1402;1404;148 | 6
1406 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Thu 6/25/26 | Mon 6/29/26 | 1405 | 6
1407 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Mon 6/29/26 | Wed 7/01/26 | 1406 | 6
1408 | Yes | Auto Scheduled | MOROVIS COMMUNITY HEALTH CENTER, INC. | 16.88 days | Thu 7/02/26 | Fri 7/24/26 |  | 4
1409 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Thu 7/02/26 | Fri 7/03/26 |  | 5
1410 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Thu 7/02/26 | Thu 7/02/26 |  | 6
1411 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Thu 7/02/26 | Fri 7/03/26 | 1410 | 6
1412 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Fri 7/03/26 | Fri 7/03/26 | 1411 | 6 | Create Participant Profile Create ENS Work Queue
1413 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Fri 7/03/26 | Fri 7/03/26 | 1412 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1414 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Fri 7/03/26 | Tue 7/14/26 | 1409 | 5
1415 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Fri 7/03/26 | Mon 7/06/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1416 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Mon 7/06/26 | Tue 7/07/26 | 1415 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1417 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Tue 7/07/26 | Wed 7/08/26 | 1416 | 6
1418 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Wed 7/08/26 | Thu 7/09/26 | 1417 | 6
1419 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Thu 7/09/26 | Fri 7/10/26 | 1418 | 6
1420 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Fri 7/10/26 | Mon 7/13/26 | 1419 | 6
1421 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Mon 7/13/26 | Tue 7/14/26 | 1420 | 6
1422 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Tue 7/14/26 | Fri 7/17/26 | 1414 | 5
1423 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Tue 7/14/26 | Tue 7/14/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1424 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Tue 7/14/26 | Wed 7/15/26 | 1423 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1425 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Wed 7/15/26 | Thu 7/16/26 | 1424 | 6
1426 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Thu 7/16/26 | Fri 7/17/26 | 1425 | 6
1427 | Yes | Auto Scheduled | System Training, Testing, and Validation | 5 days | Fri 7/17/26 | Fri 7/24/26 | 1422 | 5
1428 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0.5 days | Fri 7/17/26 | Mon 7/20/26 |  | 6
1429 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0.5 days | Mon 7/20/26 | Mon 7/20/26 | 148;1428 | 6
1430 | Yes | Auto Scheduled | Complete group training of used functionality | 2 days | Mon 7/20/26 | Wed 7/22/26 | 1429 | 6
1431 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 2 days | Wed 7/22/26 | Fri 7/24/26 | 1430 | 6
1432 | Yes | Auto Scheduled | Neomed | 11.88 days | Thu 7/09/26 | Fri 7/24/26 |  | 4
1433 | Yes | Auto Scheduled | Participant Creation & Project Charter | 1.38 days | Thu 7/09/26 | Fri 7/10/26 |  | 5
1434 | Yes | Auto Scheduled | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | 1 hr | Thu 7/09/26 | Thu 7/09/26 |  | 6
1435 | Yes | Auto Scheduled | Create and review Project Charter with Participant stakeholders | 8 hrs | Thu 7/09/26 | Fri 7/10/26 | 1434 | 6
1436 | Yes | Auto Scheduled | Enter Participant into the System | 1 hr | Fri 7/10/26 | Fri 7/10/26 | 1435 | 6 | Create Participant Profile Create ENS Work Queue
1437 | Yes | Auto Scheduled | Establish Account Designee and Super Users | 1 hr | Fri 7/10/26 | Fri 7/10/26 | 1436 | 6 | Account Designee and Super users will be responsible for authenticating, activating/deactivating users, and permissions
1438 | Yes | Auto Scheduled | Community Patient Lookup & Notification Setup | 7 days | Fri 7/10/26 | Tue 7/21/26 | 1433 | 5
1439 | Yes | Auto Scheduled | Work with Account Designee to identify possible patient overlap with available community interfaces | 1 day | Fri 7/10/26 | Mon 7/13/26 |  | 6 | This step will identify the hospitals that participant location wants to receive event notification from (ENS), typically they would be hospitals around or near their base patient population.
1440 | Yes | Auto Scheduled | Give Access to The Exchange | 1 day | Mon 7/13/26 | Tue 7/14/26 | 1439 | 6 | Access to the health information exchange is user permission based and can only be granted by participant Account Designee or Super Users.
1441 | Yes | Auto Scheduled | Identify desired ADT types needed by Participant | 1 day | Tue 7/14/26 | Wed 7/15/26 | 1440 | 6
1442 | Yes | Auto Scheduled | Determine Patient Panel Size | 1 day | Wed 7/15/26 | Thu 7/16/26 | 1441 | 6
1443 | Yes | Auto Scheduled | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | 1 day | Thu 7/16/26 | Fri 7/17/26 | 1442 | 6
1444 | Yes | Auto Scheduled | Configure and test notifications in system | 1 day | Fri 7/17/26 | Mon 7/20/26 | 1443 | 6
1445 | Yes | Auto Scheduled | Start notifications and monitor for 7 days to validate | 1 day | Mon 7/20/26 | Tue 7/21/26 | 1444 | 6
1446 | Yes | Auto Scheduled | User Credentialing and Setup | 3.5 days | Tue 7/21/26 | Fri 7/24/26 | 1438 | 5
1447 | Yes | Auto Scheduled | Traing Account Designee & Super Users on User Mgt. | 0.5 days | Tue 7/21/26 | Tue 7/21/26 |  | 6 | Centralis Health account success manager will training Account Designess and Super Users on all user management functionality
1448 | Yes | Auto Scheduled | Work w/ Account Designee & Super Users on Initial Users | 1 day | Tue 7/21/26 | Wed 7/22/26 | 1447 | 6 | For initial Users registration Centralis Health's account success manager will assist to insure accuracy.
1449 | Yes | Auto Scheduled | Verify each user profile is active and password is set | 1 day | Wed 7/22/26 | Thu 7/23/26 | 1448 | 6
1450 | Yes | Auto Scheduled | Verify ability each users’ permissions and available functionality | 1 day | Thu 7/23/26 | Fri 7/24/26 | 1449 | 6
1451 | Yes | Auto Scheduled | System Training, Testing, and Validation | 0 days | Fri 7/24/26 | Fri 7/24/26 | 1446 | 5
1452 | Yes | Auto Scheduled | Work with Account Designee to setup a group training session for organization | 0 days | Fri 7/24/26 | Fri 7/24/26 |  | 6
1453 | Yes | Auto Scheduled | Identify internal coach or “power-user” | 0 days | Fri 7/24/26 | Fri 7/24/26 | 1450;1452;148 | 6
1454 | Yes | Auto Scheduled | Complete group training of used functionality | 0 days | Fri 7/24/26 | Fri 7/24/26 | 1453 | 6
1455 | Yes | Auto Scheduled | Follow-up with each user to verify for feedback on usability | 0 days | Fri 7/24/26 | Fri 7/24/26 | 1454 | 6

## Resource_Table
ID | Indicators | Resource name | Type | Material label | Initials | Group | Max.Units | Ovt.Rate | Cost/Use | Accrue At | Base Calendar | Code
1 |  | Allen Byington - CEO | Work |  | A | Centralis Health | 100% | $0.00/hr | $0.00 | Prorated | Standard
2 |  | William Dillon - General Counsil | Work |  | W | Centralis Health | 100% | $0.00/hr | $0.00 | Prorated | Standard
3 |  | Keisha Holligan - Account Success | Work |  | K | Centralis Health | 100% | $0.00/hr | $0.00 | Prorated | Standard
4 |  | Terri Glover - Account Success Mgr. | Work |  | T | Centralis Health | 100% | $0.00/hr | $0.00 | Prorated | Standard
5 |  | Scott Hall - CIO | Work |  | S | Centralis Health | 100% | $0.00/hr | $0.00 | Prorated | Standard
6 |  | Zen - Resource 1 | Work |  | Z | Centralis Health | 100% | $0.00/hr | $0.00 | Prorated | Standard
7 |  | Zen - Resource 2 | Work |  | Z | Centralis Health | 100% | $0.00/hr | $0.00 | Prorated | Standard
8 |  | Alan Uhl - Senior Developer | Work |  | A | Centralis Health | 100% | $0.00/hr | $0.00 | Prorated | Standard
9 |  | Health Gorilla | Work |  | H | Health Gorilla | 100% | $0.00/hr | $0.00 | Prorated | Standard
10 |  | Ed Wilson -vCISO | Work |  | E | Centralis Health | 100% | $0.00/hr | $0.00 | Prorated | Standard
11 |  | Tyler Harrison - Developer | Work |  | T | Centralis Health | 100% | $0.00/hr | $0.00 | Prorated | Standard
12 |  | PR -HIE Portfolio Manager | Work |  | P | PRMP | 100% | $0.00/hr | $0.00 | Prorated | Standard
13 |  | Louis Martin - Controller | Work |  | L | Centralis Health | 100% | $0.00/hr | $0.00 | Prorated | Standard
14 |  | Katie Bradley - COO | Work |  | K | Centralis Health | 100% | $0.00/hr | $0.00 | Prorated | Standard
15 |  | PR-HIE Program Director | Work |  | P |  | 100% | $0.00/hr | $0.00 | Prorated | Standard

## Assignment_Table
ID | Task name | Resource name | Work | Duration
909 | Obtain and Review Final Contract from PRMP | Katie Bradley - COO | 4 hrs | 4 hrs
910 | Centralis Exectutive Review | Allen Byington - CEO | 4 hrs | 4 hrs
911 | Centralis Legal Review | William Dillon - General Counsil | 4 hrs | 4 hrs
912 | Execute and Save Final Contract | Katie Bradley - COO | 0.5 hrs | 30 mins
913 | Add Approved Invoice Template to Quickbooks | Keisha Holligan - Account Success | 4 hrs | 4 hrs
914 | D02: PRHIE Work Plan | Katie Bradley - COO | 40 hrs | 40 hrs
915 | D01 Monthly Status Report | Katie Bradley - COO | 40 hrs | 40 hrs
970 | Traing Account Designee & Super Users on User Mgt. | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
971 | Work w/ Account Designee & Super Users on Initial Users | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
972 | Verify each user profile is active and password is set | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
973 | Verify ability each users’ permissions and available functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
974 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
975 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
976 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
977 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
986 | Hospital/Clinics 1 | Tyler Harrison - Developer | 5 hrs | 5 hrs
987 | Hospital/Clinics 2 | Tyler Harrison - Developer | 5 hrs | 5 hrs
988 | Hospital/Clinics 3 | Tyler Harrison - Developer | 5 hrs | 5 hrs
989 | Hospital/Clinics 4 | Tyler Harrison - Developer | 5 hrs | 5 hrs
990 | Hospital/Clinics 5 | Tyler Harrison - Developer | 5 hrs | 5 hrs
991 | Hospital/Clinics 6 | Tyler Harrison - Developer | 5 hrs | 5 hrs
992 | Hospital/Clinics 7 | Tyler Harrison - Developer | 5 hrs | 5 hrs
993 | Hospital/Clinics 8 | Tyler Harrison - Developer | 5 hrs | 5 hrs
994 | Hospital/Clinics 9 | Tyler Harrison - Developer | 5 hrs | 5 hrs
995 | Hospital/Clinics 10 | Tyler Harrison - Developer | 5 hrs | 5 hrs
996 | Hospital/Clinics 11 | Tyler Harrison - Developer | 5 hrs | 5 hrs
997 | Hospital/Clinics 12 | Tyler Harrison - Developer | 5 hrs | 5 hrs
998 | Hospital/Clinics 13 | Tyler Harrison - Developer | 5 hrs | 5 hrs
999 | Hospital/Clinics 14 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1000 | Hospital/Clinics 15 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1001 | Hospital/Clinics 16 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1002 | Hospital/Clinics 17 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1003 | Hospital/Clinics 18 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1004 | Hospital/Clinics 19 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1005 | Hospital/Clinics 20 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1006 | Hospital/Clinics 21 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1007 | Hospital/Clinics 22 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1008 | Hospital/Clinics 23 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1009 | Hospital/Clinics 24 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1010 | Hospital/Clinics 25 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1011 | Hospital/Clinics 26 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1012 | Hospital/Clinics 27 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1013 | Hospital/Clinics 28 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1014 | Hospital/Clinics 29 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1015 | Hospital/Clinics 30 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1016 | Hospital/Clinics 31 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1017 | Hospital/Clinics 32 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1018 | Hospital/Clinics 33 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1019 | Hospital/Clinics 34 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1020 | Hospital/Clinics 35 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1021 | Hospital/Clinics 36 | Tyler Harrison - Developer | 5 hrs | 5 hrs
1022 | Hospital/Clinics 37 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
1023 | Hospital/Clinics 38 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1024 | Hospital/Clinics 39 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1025 | Hospital/Clinics 40 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1026 | Hospital/Clinics 41 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1027 | Hospital/Clinics 42 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1028 | Hospital/Clinics 43 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1029 | Hospital/Clinics 44 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1030 | Hospital/Clinics 45 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1031 | Hospital/Clinics 46 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1032 | Hospital/Clinics 47 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1033 | Hospital/Clinics 48 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1034 | Hospital/Clinics 49 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1035 | Hospital/Clinics 50 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1036 | Hospital/Clinics 51 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1037 | Hospital/Clinics 52 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1038 | Hospital/Clinics 53 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1039 | Hospital/Clinics 54 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1040 | Hospital/Clinics 55 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1041 | Hospital/Clinics 56 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1042 | Hospital/Clinics 57 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1043 | Hospital/Clinics 58 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1044 | Hospital/Clinics 59 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1045 | Hospital/Clinics 60 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1046 | Hospital/Clinics 61 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1047 | Hospital/Clinics 62 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1048 | Hospital/Clinics 63 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1049 | FQHC 1 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1050 | FQHC 2 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1051 | FQHC 3 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1052 | FQHC 4 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1053 | FQHC 5 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1054 | FQHC 6 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1055 | FQHC 7 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1056 | FQHC 8 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1057 | FQHC 9 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1058 | LIMS 1 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1059 | LIMS 2 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
1135 | Identify Missing Data Sources | PR -HIE Portfolio Manager | 4 hrs | 0.5 days
1136 | PRMP Introductory Email | PR -HIE Portfolio Manager | 4 hrs | 0.5 days
1155 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1157 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1159 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1161 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1163 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1165 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1167 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1168 | Obtain Contract | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1169 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1171 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1173 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1174 | Obtain Contract | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1175 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1177 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1179 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1181 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1183 | Interface Activity | Scott Hall - CIO | 0 hrs | 0 days
1187 | Establish Communication Plan with PRMP | Katie Bradley - COO | 8 hrs | 1 day
1244 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1245 | Create and review Project Charter with Participant stakeholders | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1246 | Enter Participant into the System | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1247 | Establish Account Designee and Super Users | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1248 | Work with Account Designee to identify possible patient overlap with available community interfaces | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1249 | Give Access to The Exchange | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1250 | Identify desired ADT types needed by Participant | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1251 | Determine Patient Panel Size | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1252 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1255 | Traing Account Designee & Super Users on User Mgt. | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1256 | Work w/ Account Designee & Super Users on Initial Users | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1257 | Verify each user profile is active and password is set | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1258 | Verify ability each users’ permissions and available functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1259 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1260 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1261 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1262 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1263 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Terri Glover - Account Success Mgr. | 1 hr | 1 hr
1264 | Create and review Project Charter with Participant stakeholders | Terri Glover - Account Success Mgr. | 8 hrs | 8 hrs
1265 | Enter Participant into the System | Terri Glover - Account Success Mgr. | 1 hr | 1 hr
1266 | Establish Account Designee and Super Users | Terri Glover - Account Success Mgr. | 1 hr | 1 hr
1267 | Work with Account Designee to identify possible patient overlap with available community interfaces | Terri Glover - Account Success Mgr. | 8 hrs | 1 day
1268 | Give Access to The Exchange | Terri Glover - Account Success Mgr. | 8 hrs | 1 day
1269 | Identify desired ADT types needed by Participant | Terri Glover - Account Success Mgr. | 8 hrs | 1 day
1270 | Determine Patient Panel Size | Terri Glover - Account Success Mgr. | 8 hrs | 1 day
1271 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1274 | Traing Account Designee & Super Users on User Mgt. | Terri Glover - Account Success Mgr. | 4 hrs | 0.5 days
1275 | Work w/ Account Designee & Super Users on Initial Users | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1276 | Verify each user profile is active and password is set | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1277 | Verify ability each users’ permissions and available functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1278 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1279 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1280 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1281 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1283 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1284 | Create and review Project Charter with Participant stakeholders | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1285 | Enter Participant into the System | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1286 | Establish Account Designee and Super Users | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1287 | Work with Account Designee to identify possible patient overlap with available community interfaces | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1288 | Give Access to The Exchange | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1289 | Identify desired ADT types needed by Participant | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1290 | Determine Patient Panel Size | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1291 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1294 | Traing Account Designee & Super Users on User Mgt. | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1295 | Work w/ Account Designee & Super Users on Initial Users | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1296 | Verify each user profile is active and password is set | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1297 | Verify ability each users’ permissions and available functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1298 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1299 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1300 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1301 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1302 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1303 | Create and review Project Charter with Participant stakeholders | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1304 | Enter Participant into the System | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1305 | Establish Account Designee and Super Users | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1306 | Work with Account Designee to identify possible patient overlap with available community interfaces | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1315 | Verify each user profile is active and password is set | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1316 | Verify ability each users’ permissions and available functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1317 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1318 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1319 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1374 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
1375 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
1376 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
1377 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
1382 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
1383 | Give Access to The Exchange | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1385 | Determine Patient Panel Size | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1386 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1393 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
1394 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
1395 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
1396 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
1412 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
1413 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
1414 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
1415 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
1450 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
1451 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
1452 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
1453 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
1635 | Start notifications and monitor for 7 days to validate | Katie Bradley - COO | 8 hrs | 1 day
1751 | Hospital/Clinic 1 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1752 | Hospital/Clinic 2 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1753 | Hospital/Clinic 3 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1754 | Hospital/Clinic 4 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1755 | Hospital/Clinic 5 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1756 | Hospital/Clinic 6 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1757 | Hospital/Clinic 7 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1758 | Hospital/Clinic 8 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1759 | Hospital/Clinic 9 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1760 | Hospital/Clinic 10 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1761 | Hospital/Clinic 11 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1762 | Hospital/Clinic 12 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1763 | Hospital/Clinic 13 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1764 | Hospital/Clinic 14 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1765 | Hospital/Clinic 15 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1766 | Hospital/Clinic 16 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1767 | Hospital/Clinic 17 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1768 | Hospital/Clinic 18 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1769 | Hospital/Clinic 19 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1770 | Hospital/Clinic 20 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1771 | Hospital/Clinic 21 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1772 | Hospital/Clinic 22 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1773 | Hospital/Clinic 23 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1774 | Hospital/Clinic 24 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1775 | Hospital/Clinic 25 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1776 | Hospital/Clinic 26 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1777 | Hospital/Clinic 27 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1778 | Hospital/Clinic 28 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1779 | Hospital/Clinic 29 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1780 | Hospital/Clinic 30 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1781 | Hospital/Clinic 31 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1782 | Hospital/Clinic 32 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1783 | Hospital/Clinic 33 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1784 | Hospital/Clinic 34 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1785 | Hospital/Clinic 35 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1786 | Hospital/Clinic 36 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1787 | Hospital/Clinic 37 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1788 | Hospital/Clinic 38 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1789 | Hospital/Clinic 39 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1790 | Hospital/Clinic 40 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1791 | Hospital/Clinic 41 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1792 | Hospital/Clinic 42 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1793 | Hospital/Clinic 43 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1794 | Hospital/Clinic 44 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1795 | Hospital/Clinic 45 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1796 | Hospital/Clinic 46 | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
1797 | Hospital/Clinic 47 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1798 | Hospital/Clinic 48 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1799 | Hospital/Clinic 49 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1800 | Hospital/Clinic 50 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1801 | Hospital/Clinic 51 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1802 | Hospital/Clinic 52 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1803 | Hospital/Clinic 53 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1804 | Hospital/Clinic 54 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1805 | Hospital/Clinic 55 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1806 | Hospital/Clinic 56 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1807 | Hospital/Clinic 57 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1808 | Hospital/Clinic 58 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1809 | Hospital/Clinic 59 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1810 | Hospital/Clinic 60 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1811 | Hospital/Clinic 61 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1812 | Hospital/Clinic 62 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1813 | Hospital/Clinic 63 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1814 | Centros 330_FQHC 1 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1815 | Centros 330_FQHC 2 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1816 | Centros 330_FQHC 3 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1817 | Centros 330_FQHC 4 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1818 | Centros 330_FQHC 5 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1819 | Centros 330_FQHC 6 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1820 | Centros 330_FQHC 7 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1821 | Centros 330_FQHC 8 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1822 | Centros 330_FQHC 9 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1823 | Centros 330_FQHC 10 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1824 | Centros 330_FQHC 11 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1825 | Centros 330_FQHC 12 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1826 | Centros 330_FQHC 13 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1827 | Centros 330_FQHC 14 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1828 | Centros 330_FQHC 15 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1829 | Centros 330_FQHC 16 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1830 | Centros 330_FQHC 17 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1831 | LIMS 1 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1832 | LIMS 2 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1833 | LIMS 3 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1834 | LIMS 4 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1835 | LIMS 5 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1836 | LIMS 6 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1837 | LIMS 7 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1838 | LIMS 8 | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1839 | Radiology Facility | Keisha Holligan - Account Success | 3 hrs | 3 hrs
1840 | ADT 1 | Zen - Resource 1 | 5 hrs | 5 hrs
1841 | ADT 2 | Zen - Resource 1 | 5 hrs | 5 hrs
1842 | ADT 3 | Zen - Resource 1 | 5 hrs | 5 hrs
1843 | ADT 4 | Zen - Resource 1 | 5 hrs | 5 hrs
1844 | ADT 5 | Zen - Resource 1 | 5 hrs | 5 hrs
1845 | ADT 6 | Zen - Resource 1 | 5 hrs | 5 hrs
1846 | ADT 7 | Zen - Resource 1 | 5 hrs | 5 hrs
1847 | ADT 8 | Zen - Resource 1 | 5 hrs | 5 hrs
1848 | ADT 9 | Zen - Resource 1 | 5 hrs | 5 hrs
1849 | ADT 10 | Zen - Resource 1 | 5 hrs | 5 hrs
1850 | ADT 11 | Zen - Resource 1 | 0 hrs | 0 hrs
1851 | ADT 12 | Zen - Resource 1 | 0 hrs | 0 hrs
1852 | ADT 13 | Zen - Resource 1 | 0 hrs | 0 hrs
1853 | ADT 14 | Zen - Resource 1 | 0 hrs | 0 hrs
1854 | ADT 15 | Zen - Resource 1 | 0 hrs | 0 hrs
1855 | ADT 16 | Zen - Resource 1 | 0 hrs | 0 hrs
1856 | ADT 17 | Zen - Resource 1 | 0 hrs | 0 hrs
1857 | ADT 18 | Zen - Resource 1 | 0 hrs | 0 hrs
1858 | ADT 19 | Zen - Resource 1 | 0 hrs | 0 hrs
1859 | ADT 20 | Zen - Resource 1 | 0 hrs | 0 hrs
1860 | ADT 21 | Zen - Resource 1 | 0 hrs | 0 hrs
1861 | ADT 22 | Zen - Resource 1 | 0 hrs | 0 hrs
1862 | ADT 23 | Zen - Resource 1 | 0 hrs | 0 hrs
1863 | ADT 24 | Zen - Resource 1 | 0 hrs | 0 hrs
1864 | ADT 25 | Zen - Resource 1 | 0 hrs | 0 hrs
1865 | ADT 26 | Zen - Resource 1 | 0 hrs | 0 hrs
1866 | ADT 27 | Zen - Resource 1 | 0 hrs | 0 hrs
1867 | ADT 28 | Zen - Resource 1 | 0 hrs | 0 hrs
1868 | ADT 29 | Zen - Resource 1 | 0 hrs | 0 hrs
1869 | ADT 30 | Zen - Resource 1 | 0 hrs | 0 hrs
1870 | ADT 31 | Zen - Resource 1 | 0 hrs | 0 hrs
1871 | ADT 32 | Zen - Resource 1 | 0 hrs | 0 hrs
1872 | ADT 33 | Zen - Resource 1 | 0 hrs | 0 hrs
1873 | ADT 34 | Zen - Resource 1 | 0 hrs | 0 hrs
1874 | ADT 35 | Zen - Resource 1 | 0 hrs | 0 hrs
1875 | ADT 36 | Zen - Resource 1 | 0 hrs | 0 hrs
1876 | ADT 37 | Zen - Resource 1 | 0 hrs | 0 hrs
1877 | ADT 38 | Zen - Resource 1 | 0 hrs | 0 hrs
1878 | ADT 39 | Zen - Resource 1 | 0 hrs | 0 hrs
1879 | ADT 40 | Zen - Resource 1 | 0 hrs | 0 hrs
1880 | ADT 41 | Zen - Resource 1 | 0 hrs | 0 hrs
1881 | ADT 42 | Zen - Resource 1 | 0 hrs | 0 hrs
1882 | ADT 43 | Zen - Resource 1 | 0 hrs | 0 hrs
1883 | ADT 44 | Zen - Resource 1 | 0 hrs | 0 hrs
1884 | ADT 45 | Zen - Resource 1 | 0 hrs | 0 hrs
1885 | ADT 46 | Zen - Resource 1 | 0 hrs | 0 hrs
1886 | ADT 47 | Zen - Resource 1 | 0 hrs | 0 hrs
1887 | ADT 48 | Zen - Resource 1 | 0 hrs | 0 hrs
1888 | ADT 49 | Zen - Resource 1 | 0 hrs | 0 hrs
1889 | ADT 50 | Zen - Resource 1 | 0 hrs | 0 hrs
1890 | ADT 51 | Zen - Resource 1 | 0 hrs | 0 hrs
1891 | ADT 52 | Zen - Resource 1 | 0 hrs | 0 hrs
1892 | CCDA 1 | Zen - Resource 1 | 0 hrs | 0 hrs
1893 | CCDA 2 | Zen - Resource 1 | 0 hrs | 0 hrs
1894 | CCDA 3 | Zen - Resource 1 | 0 hrs | 0 hrs
1895 | CCDA 4 | Zen - Resource 1 | 0 hrs | 0 hrs
1896 | CCDA 5 | Zen - Resource 1 | 0 hrs | 0 hrs
1897 | CCDA 6 | Zen - Resource 1 | 0 hrs | 0 hrs
1898 | CCDA 7 | Zen - Resource 1 | 0 hrs | 0 hrs
1899 | CCDA 8 | Zen - Resource 1 | 0 hrs | 0 hrs
1900 | CCDA 9 | Zen - Resource 1 | 0 hrs | 0 hrs
1901 | CCDA 10 | Zen - Resource 1 | 0 hrs | 0 hrs
1902 | CCDA 11 | Zen - Resource 1 | 0 hrs | 0 hrs
1903 | CCDA 12 | Zen - Resource 1 | 0 hrs | 0 hrs
1904 | CCDA 13 | Zen - Resource 1 | 0 hrs | 0 hrs
1905 | CCDA 14 | Zen - Resource 1 | 0 hrs | 0 hrs
1906 | CCDA 15 | Zen - Resource 1 | 0 hrs | 0 hrs
1907 | CCDA 16 | Zen - Resource 1 | 0 hrs | 0 hrs
1908 | CCDA 17 | Zen - Resource 1 | 0 hrs | 0 hrs
1909 | CCDA 18 | Zen - Resource 1 | 0 hrs | 0 hrs
1910 | CCDA 19 | Zen - Resource 1 | 0 hrs | 0 hrs
1911 | CCDA 20 | Zen - Resource 1 | 0 hrs | 0 hrs
1912 | CCDA 21 | Zen - Resource 1 | 0 hrs | 0 hrs
1913 | CCDA 22 | Zen - Resource 1 | 0 hrs | 0 hrs
1914 | CCDA 23 | Zen - Resource 1 | 0 hrs | 0 hrs
1915 | CCDA 24 | Zen - Resource 1 | 0 hrs | 0 hrs
1916 | CCDA 25 | Zen - Resource 1 | 0 hrs | 0 hrs
1917 | CCDA 26 | Zen - Resource 1 | 0 hrs | 0 hrs
1918 | CCDA 27 | Zen - Resource 1 | 0 hrs | 0 hrs
1919 | CCDA 28 | Zen - Resource 1 | 0 hrs | 0 hrs
1920 | CCDA 29 | Zen - Resource 1 | 0 hrs | 0 hrs
1921 | CCDA 30 | Zen - Resource 1 | 0 hrs | 0 hrs
1922 | CCDA 31 | Zen - Resource 1 | 0 hrs | 0 hrs
1923 | CCDA 32 | Zen - Resource 1 | 0 hrs | 0 hrs
1924 | CCDA 33 | Zen - Resource 1 | 0 hrs | 0 hrs
1925 | CCDA 34 | Zen - Resource 1 | 0 hrs | 0 hrs
1926 | CCDA 35 | Zen - Resource 1 | 0 hrs | 0 hrs
1927 | CCDA 36 | Zen - Resource 1 | 0 hrs | 0 hrs
1928 | CCDA 37 | Zen - Resource 1 | 0 hrs | 0 hrs
1929 | CCDA 38 | Zen - Resource 1 | 0 hrs | 0 hrs
1930 | CCDA 39 | Zen - Resource 1 | 0 hrs | 0 hrs
1931 | CCDA 40 | Zen - Resource 1 | 0 hrs | 0 hrs
1932 | CCDA 41 | Zen - Resource 1 | 0 hrs | 0 hrs
1933 | CCDA 42 | Zen - Resource 1 | 0 hrs | 0 hrs
1934 | CCDA 43 | Zen - Resource 1 | 0 hrs | 0 hrs
1935 | CCDA 44 | Zen - Resource 1 | 0 hrs | 0 hrs
1936 | CCDA 45 | Zen - Resource 1 | 0 hrs | 0 hrs
2037 | ADT 1 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2038 | ADT 2 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2039 | ADT 3 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2040 | ADT 4 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2041 | ADT 5 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2042 | ADT 6 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2043 | ADT 7 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2044 | ADT 8 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2045 | ADT 9 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2046 | ADT 10 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2047 | ADT 11 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2048 | ADT 12 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2049 | ADT 13 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2050 | ADT 14 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2051 | ADT 15 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2052 | ADT 16 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2053 | ADT 17 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2054 | ADT 18 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2055 | ADT 19 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2056 | ADT 20 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2057 | ADT 21 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2058 | ADT 22 | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
2059 | ADT 23 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2060 | ADT 24 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2061 | ADT 25 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2062 | ADT 26 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2063 | ADT 27 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2064 | ADT 28 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2065 | ADT 29 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2066 | ADT 30 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2067 | ADT 31 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2068 | ADT 32 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2069 | ADT 33 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2070 | ADT 34 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2071 | ADT 35 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2072 | ADT 36 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2073 | ADT 37 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2074 | ADT 38 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2075 | ADT 39 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2076 | ADT 40 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2077 | ADT 41 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2078 | ADT 42 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2079 | ADT 43 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2080 | ADT 44 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2081 | ADT 45 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2082 | ADT 46 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2083 | ADT 47 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2084 | ADT 48 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2085 | ADT 49 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2086 | ADT 50 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2087 | ADT 51 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2088 | ADT 52 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2089 | CCDA 1 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2090 | CCDA 2 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2091 | CCDA 3 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2092 | CCDA 4 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2093 | CCDA 5 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2094 | CCDA 6 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2095 | CCDA 7 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2096 | CCDA 8 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2097 | CCDA 9 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2098 | CCDA 10 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2099 | CCDA 11 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2100 | CCDA 12 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2101 | CCDA 13 | Alan Uhl - Senior Developer | 0 hrs | 0 hrs
2102 | CCDA 14 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2103 | CCDA 15 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2104 | CCDA 16 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2105 | CCDA 17 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2106 | CCDA 18 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2107 | CCDA 19 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2108 | CCDA 20 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2109 | CCDA 21 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2110 | CCDA 22 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2111 | CCDA 23 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2112 | CCDA 24 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2113 | CCDA 25 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2114 | CCDA 26 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2115 | CCDA 27 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2116 | CCDA 28 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2117 | CCDA 29 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2118 | CCDA 30 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2119 | CCDA 31 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2120 | CCDA 32 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2121 | CCDA 33 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2122 | CCDA 34 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2123 | CCDA 35 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2124 | CCDA 36 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2125 | CCDA 37 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2126 | CCDA 38 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2127 | CCDA 39 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2128 | CCDA 40 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2129 | CCDA 41 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2130 | CCDA 42 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2131 | CCDA 43 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2132 | CCDA 44 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2133 | CCDA 45 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2134 | CCDA 46 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2135 | CCDA 47 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2136 | CCDA 48 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2137 | CCDA 49 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2138 | CCDA 50 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2139 | CCDA 51 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2140 | CCDA 52 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2141 | CCDA 53 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2142 | Lab 1 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2143 | Lab 2 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2144 | Lab 3 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2145 | Lab 4 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2146 | Lab 5 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2147 | Lab 6 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2148 | Lab 7 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2149 | Lab 8 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2150 | Lab 9 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2151 | Lab 10 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2152 | Lab 11 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2153 | Lab 12 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2154 | Lab 13 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2155 | Lab 14 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2156 | Lab 15 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2157 | Lab 16 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2158 | Lab 17 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2159 | Lab 18 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2160 | Lab 19 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2161 | Lab 20 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2162 | Lab 21 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2163 | Lab 22 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2164 | Lab 23 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2165 | Lab 24 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2166 | Lab 25 | Tyler Harrison - Developer | 5 hrs | 5 hrs
2167 | Lab 26 | Scott Hall - CIO | 5 hrs | 5 hrs
2168 | Lab 27 | Scott Hall - CIO | 5 hrs | 5 hrs
2169 | Lab 28 | Scott Hall - CIO | 5 hrs | 5 hrs
2170 | Lab 29 | Scott Hall - CIO | 5 hrs | 5 hrs
2171 | Lab 30 | Scott Hall - CIO | 5 hrs | 5 hrs
2172 | Lab 31 | Scott Hall - CIO | 5 hrs | 5 hrs
2173 | Lab 32 | Scott Hall - CIO | 5 hrs | 5 hrs
2174 | Lab 33 | Scott Hall - CIO | 5 hrs | 5 hrs
2175 | Lab 34 | Scott Hall - CIO | 5 hrs | 5 hrs
2176 | Lab 35 | Scott Hall - CIO | 5 hrs | 5 hrs
2177 | Lab 36 | Scott Hall - CIO | 5 hrs | 5 hrs
2178 | Lab 37 | Scott Hall - CIO | 5 hrs | 5 hrs
2179 | Lab 38 | Scott Hall - CIO | 5 hrs | 5 hrs
2180 | Lab 39 | Scott Hall - CIO | 5 hrs | 5 hrs
2181 | Lab 40 | Scott Hall - CIO | 5 hrs | 5 hrs
2182 | Lab 41 | Scott Hall - CIO | 5 hrs | 5 hrs
2183 | Lab 42 | Scott Hall - CIO | 5 hrs | 5 hrs
2184 | Lab 43 | Scott Hall - CIO | 5 hrs | 5 hrs
2185 | Lab 44 | Scott Hall - CIO | 5 hrs | 5 hrs
2186 | Lab 45 | Scott Hall - CIO | 5 hrs | 5 hrs
2187 | Lab 46 | Scott Hall - CIO | 5 hrs | 5 hrs
2188 | Lab 47 | Scott Hall - CIO | 5 hrs | 5 hrs
2189 | Lab 48 | Scott Hall - CIO | 5 hrs | 5 hrs
2190 | Lab 49 | Scott Hall - CIO | 5 hrs | 5 hrs
2191 | Lab 50 | Scott Hall - CIO | 5 hrs | 5 hrs
2192 | Lab 51 | Scott Hall - CIO | 5 hrs | 5 hrs
2193 | Lab 52 | Scott Hall - CIO | 5 hrs | 5 hrs
2194 | Lab 53 | Scott Hall - CIO | 5 hrs | 5 hrs
2195 | Lab 54 | Scott Hall - CIO | 5 hrs | 5 hrs
2196 | Lab 55 | Scott Hall - CIO | 5 hrs | 5 hrs
2197 | Lab 56 | Scott Hall - CIO | 5 hrs | 5 hrs
2198 | Lab 57 | Scott Hall - CIO | 5 hrs | 5 hrs
2199 | Lab 58 | Scott Hall - CIO | 5 hrs | 5 hrs
2200 | Lab 59 | Scott Hall - CIO | 5 hrs | 5 hrs
2201 | Rad 1 | Scott Hall - CIO | 5 hrs | 5 hrs
2202 | Rad 2 | Scott Hall - CIO | 5 hrs | 5 hrs
2203 | Rad 3 | Scott Hall - CIO | 5 hrs | 5 hrs
2204 | Rad 4 | Scott Hall - CIO | 5 hrs | 5 hrs
2205 | Rad 5 | Scott Hall - CIO | 5 hrs | 5 hrs
2206 | Rad 6 | Scott Hall - CIO | 5 hrs | 5 hrs
2207 | Rad 7 | Scott Hall - CIO | 5 hrs | 5 hrs
2208 | Rad 8 | Scott Hall - CIO | 5 hrs | 5 hrs
2209 | Rad 9 | Scott Hall - CIO | 5 hrs | 5 hrs
2210 | Rad 10 | Scott Hall - CIO | 5 hrs | 5 hrs
2211 | Rad 11 | Scott Hall - CIO | 5 hrs | 5 hrs
2212 | Rad 12 | Scott Hall - CIO | 5 hrs | 5 hrs
2213 | Rad 13 | Scott Hall - CIO | 5 hrs | 5 hrs
2214 | Rad 14 | Scott Hall - CIO | 5 hrs | 5 hrs
2215 | Rad 15 | Scott Hall - CIO | 5 hrs | 5 hrs
2216 | Rad 16 | Scott Hall - CIO | 5 hrs | 5 hrs
2217 | Rad 17 | Scott Hall - CIO | 5 hrs | 5 hrs
2218 | Rad 18 | Scott Hall - CIO | 5 hrs | 5 hrs
2219 | Rad 19 | Scott Hall - CIO | 5 hrs | 5 hrs
2220 | Rad 20 | Scott Hall - CIO | 5 hrs | 5 hrs
2221 | Rad 21 | Scott Hall - CIO | 5 hrs | 5 hrs
2222 | Rad 22 | Scott Hall - CIO | 5 hrs | 5 hrs
2223 | Rad 23 | Scott Hall - CIO | 5 hrs | 5 hrs
2224 | Rad 24 | Scott Hall - CIO | 5 hrs | 5 hrs
2225 | Rad 25 | Scott Hall - CIO | 5 hrs | 5 hrs
2226 | Rad 26 | Scott Hall - CIO | 5 hrs | 5 hrs
2227 | Rad 27 | Scott Hall - CIO | 5 hrs | 5 hrs
2228 | Rad 28 | Scott Hall - CIO | 5 hrs | 5 hrs
2229 | Rad 29 | Scott Hall - CIO | 5 hrs | 5 hrs
2230 | Rad 30 | Scott Hall - CIO | 5 hrs | 5 hrs
2231 | Rad 31 | Scott Hall - CIO | 5 hrs | 5 hrs
2232 | Rad 32 | Scott Hall - CIO | 5 hrs | 5 hrs
2233 | Rad 33 | Scott Hall - CIO | 5 hrs | 5 hrs
2234 | CCDA 46 | Zen - Resource 2 | 5 hrs | 5 hrs
2235 | CCDA 47 | Zen - Resource 2 | 5 hrs | 5 hrs
2236 | CCDA 48 | Zen - Resource 2 | 5 hrs | 5 hrs
2237 | CCDA 49 | Zen - Resource 2 | 5 hrs | 5 hrs
2238 | CCDA 50 | Zen - Resource 2 | 5 hrs | 5 hrs
2239 | CCDA 51 | Zen - Resource 2 | 5 hrs | 5 hrs
2240 | CCDA 52 | Zen - Resource 2 | 5 hrs | 5 hrs
2241 | CCDA 53 | Zen - Resource 2 | 5 hrs | 5 hrs
2242 | Lab 1 | Zen - Resource 2 | 5 hrs | 5 hrs
2243 | Lab 2 | Zen - Resource 2 | 5 hrs | 5 hrs
2244 | Lab 3 | Zen - Resource 2 | 5 hrs | 5 hrs
2245 | Lab 4 | Zen - Resource 2 | 0 hrs | 0 hrs
2246 | Lab 5 | Zen - Resource 2 | 0 hrs | 0 hrs
2247 | Lab 6 | Zen - Resource 2 | 0 hrs | 0 hrs
2248 | Lab 7 | Zen - Resource 2 | 0 hrs | 0 hrs
2249 | Lab 8 | Zen - Resource 2 | 0 hrs | 0 hrs
2250 | Lab 9 | Zen - Resource 2 | 0 hrs | 0 hrs
2251 | Lab 10 | Zen - Resource 2 | 0 hrs | 0 hrs
2252 | Lab 11 | Zen - Resource 2 | 0 hrs | 0 hrs
2253 | Lab 12 | Zen - Resource 2 | 0 hrs | 0 hrs
2254 | Lab 13 | Zen - Resource 2 | 0 hrs | 0 hrs
2255 | Lab 14 | Zen - Resource 2 | 0 hrs | 0 hrs
2256 | Lab 15 | Zen - Resource 2 | 0 hrs | 0 hrs
2257 | Lab 16 | Zen - Resource 2 | 0 hrs | 0 hrs
2258 | Lab 17 | Zen - Resource 2 | 0 hrs | 0 hrs
2259 | Lab 18 | Zen - Resource 2 | 0 hrs | 0 hrs
2260 | Lab 19 | Zen - Resource 2 | 0 hrs | 0 hrs
2261 | Lab 20 | Zen - Resource 2 | 0 hrs | 0 hrs
2262 | Lab 21 | Zen - Resource 2 | 0 hrs | 0 hrs
2263 | Lab 22 | Zen - Resource 2 | 0 hrs | 0 hrs
2264 | Lab 23 | Zen - Resource 2 | 0 hrs | 0 hrs
2265 | Lab 24 | Zen - Resource 2 | 0 hrs | 0 hrs
2266 | Lab 25 | Zen - Resource 2 | 0 hrs | 0 hrs
2267 | Lab 26 | Zen - Resource 2 | 0 hrs | 0 hrs
2268 | Lab 27 | Zen - Resource 2 | 0 hrs | 0 hrs
2269 | Lab 28 | Zen - Resource 2 | 0 hrs | 0 hrs
2270 | Lab 29 | Zen - Resource 2 | 0 hrs | 0 hrs
2271 | Lab 30 | Zen - Resource 2 | 0 hrs | 0 hrs
2272 | Lab 31 | Zen - Resource 2 | 0 hrs | 0 hrs
2273 | Lab 32 | Zen - Resource 2 | 0 hrs | 0 hrs
2274 | Lab 33 | Zen - Resource 2 | 0 hrs | 0 hrs
2275 | Lab 34 | Zen - Resource 2 | 0 hrs | 0 hrs
2276 | Lab 35 | Zen - Resource 2 | 0 hrs | 0 hrs
2277 | Lab 36 | Zen - Resource 2 | 0 hrs | 0 hrs
2278 | Lab 37 | Zen - Resource 2 | 0 hrs | 0 hrs
2279 | Lab 38 | Zen - Resource 2 | 0 hrs | 0 hrs
2280 | Lab 39 | Zen - Resource 2 | 0 hrs | 0 hrs
2281 | Lab 40 | Zen - Resource 2 | 0 hrs | 0 hrs
2282 | Lab 41 | Zen - Resource 2 | 0 hrs | 0 hrs
2283 | Lab 42 | Zen - Resource 2 | 0 hrs | 0 hrs
2284 | Lab 43 | Zen - Resource 2 | 0 hrs | 0 hrs
2285 | Lab 44 | Zen - Resource 2 | 0 hrs | 0 hrs
2286 | Lab 45 | Zen - Resource 2 | 0 hrs | 0 hrs
2287 | Lab 46 | Zen - Resource 2 | 0 hrs | 0 hrs
2288 | Lab 47 | Zen - Resource 2 | 0 hrs | 0 hrs
2289 | Lab 48 | Zen - Resource 2 | 0 hrs | 0 hrs
2290 | Lab 49 | Zen - Resource 2 | 0 hrs | 0 hrs
2291 | Lab 50 | Zen - Resource 2 | 0 hrs | 0 hrs
2292 | Lab 51 | Zen - Resource 2 | 0 hrs | 0 hrs
2293 | Lab 52 | Zen - Resource 2 | 0 hrs | 0 hrs
2294 | Lab 53 | Zen - Resource 2 | 0 hrs | 0 hrs
2295 | Lab 54 | Zen - Resource 2 | 0 hrs | 0 hrs
2296 | Lab 55 | Zen - Resource 2 | 0 hrs | 0 hrs
2297 | Lab 56 | Zen - Resource 2 | 0 hrs | 0 hrs
2298 | Lab 57 | Zen - Resource 2 | 0 hrs | 0 hrs
2299 | Lab 58 | Zen - Resource 2 | 0 hrs | 0 hrs
2300 | Lab 59 | Zen - Resource 2 | 0 hrs | 0 hrs
2301 | Rad 1 | Zen - Resource 2 | 0 hrs | 0 hrs
2302 | Rad 2 | Zen - Resource 2 | 0 hrs | 0 hrs
2303 | Rad 3 | Zen - Resource 2 | 0 hrs | 0 hrs
2304 | Rad 4 | Zen - Resource 2 | 0 hrs | 0 hrs
2305 | Rad 5 | Zen - Resource 2 | 0 hrs | 0 hrs
2306 | Rad 6 | Zen - Resource 2 | 0 hrs | 0 hrs
2307 | Rad 7 | Zen - Resource 2 | 0 hrs | 0 hrs
2308 | Rad 8 | Zen - Resource 2 | 0 hrs | 0 hrs
2309 | Rad 9 | Zen - Resource 2 | 0 hrs | 0 hrs
2310 | Rad 10 | Zen - Resource 2 | 0 hrs | 0 hrs
2311 | Rad 11 | Zen - Resource 2 | 0 hrs | 0 hrs
2312 | Rad 12 | Zen - Resource 2 | 0 hrs | 0 hrs
2313 | Rad 13 | Zen - Resource 2 | 0 hrs | 0 hrs
2314 | Rad 14 | Zen - Resource 2 | 0 hrs | 0 hrs
2315 | Rad 15 | Zen - Resource 2 | 0 hrs | 0 hrs
2316 | Rad 16 | Zen - Resource 2 | 0 hrs | 0 hrs
2317 | Rad 17 | Zen - Resource 2 | 0 hrs | 0 hrs
2318 | Rad 18 | Zen - Resource 2 | 0 hrs | 0 hrs
2319 | Rad 19 | Zen - Resource 2 | 0 hrs | 0 hrs
2320 | Rad 20 | Zen - Resource 2 | 0 hrs | 0 hrs
2321 | Rad 21 | Zen - Resource 2 | 0 hrs | 0 hrs
2322 | Rad 22 | Zen - Resource 2 | 0 hrs | 0 hrs
2323 | Rad 23 | Zen - Resource 2 | 0 hrs | 0 hrs
2324 | Rad 24 | Zen - Resource 2 | 0 hrs | 0 hrs
2325 | Rad 25 | Zen - Resource 2 | 0 hrs | 0 hrs
2326 | Rad 26 | Zen - Resource 2 | 0 hrs | 0 hrs
2327 | Rad 27 | Zen - Resource 2 | 0 hrs | 0 hrs
2328 | Rad 28 | Zen - Resource 2 | 0 hrs | 0 hrs
2329 | Rad 29 | Zen - Resource 2 | 0 hrs | 0 hrs
2330 | Rad 30 | Zen - Resource 2 | 0 hrs | 0 hrs
2331 | Rad 31 | Zen - Resource 2 | 0 hrs | 0 hrs
2332 | Rad 32 | Zen - Resource 2 | 0 hrs | 0 hrs
2333 | Rad 33 | Zen - Resource 2 | 0 hrs | 0 hrs
2388 | Generate Unique Patient ID for Medicaid Beneficiares | Tyler Harrison - Developer | 24 hrs | 3 days
2390 | Build PRMP Medicaid Beneficiary Respository | Tyler Harrison - Developer | 2 hrs | 0.25 days
2391 | Test File Upload, Receipt, and Load to Repository | Tyler Harrison - Developer | 4 hrs | 0.5 days
2392 | Population of PRMP Beneficiary Repository Logitudinal Records with Historical Data | Tyler Harrison - Developer | 40 hrs | 5 days
2393 | Establish process to obtain active MCO monthly beneficiary roster(Centralis Health Gateway or SFTP) | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
2397 | PRMP to Review and Approve Load | PR -HIE Portfolio Manager | 4 hrs | 0.5 days
2398 | Establish Beneficiary Roster Upload Schedule | PR -HIE Portfolio Manager | 4 hrs | 0.5 days
2412 | Introductions to Health Gorilla | PR -HIE Portfolio Manager | 4 hrs | 0.5 days
2414 | Introductions to Health Gorilla | Zen - Resource 1 | 4 hrs | 0.5 days
2416 | Data Transfer Test | Scott Hall - CIO | 24 hrs | 3 days
2418 | Validate Data | Scott Hall - CIO | 24 hrs | 3 days
2421 | Commense Historical Data Transfer and Integration | Scott Hall - CIO | 392 hrs | 49 days
2426 | Kick Off In-Person Meetings 2 (D03) | Katie Bradley - COO | 8 hrs | 2 days
2440 | Kick Off In-Person Meetings 1 (D03) | Katie Bradley - COO | 8 hrs | 134.25 days
2441 | Kick Off In-Person Meetings 1 (D03) | PR -HIE Portfolio Manager | 8 hrs | 134.25 days
2442 | Kick Off In-Person Meetings 1 (D03) | PR-HIE Program Director | 8 hrs | 134.25 days
2443 | Kick Off In-Person Meetings 1 (D03) | Scott Hall - CIO | 8 hrs | 134.25 days
2444 | Kick Off In-Person Meetings 2 (D03) | PR -HIE Portfolio Manager | 8 hrs | 2 days
2445 | Kick Off In-Person Meetings 2 (D03) | PR-HIE Program Director | 8 hrs | 2 days
2446 | Kick Off In-Person Meetings 2 (D03) | Scott Hall - CIO | 8 hrs | 2 days
2450 | Establish Communication Plan with PRMP | PR -HIE Portfolio Manager | 8 hrs | 1 day
2453 | Establish Beneficiary Roster Upload Schedule | Tyler Harrison - Developer | 4 hrs | 0.5 days
2454 | PRMP to Review and Approve Load | Tyler Harrison - Developer | 4 hrs | 0.5 days
2455 | Obtain Contract | Keisha Holligan - Account Success | 3.5 hrs | 3.5 hrs
2456 | Obtain Contract | Keisha Holligan - Account Success | 3.5 hrs | 3.5 hrs
2457 | Obtain Contract | Keisha Holligan - Account Success | 3.5 hrs | 3.5 hrs
2458 | Obtain Contract | Keisha Holligan - Account Success | 3.5 hrs | 3.5 hrs
2459 | Obtain Contract | Keisha Holligan - Account Success | 3.5 hrs | 3.5 hrs
2460 | Obtain Contract | Keisha Holligan - Account Success | 3.5 hrs | 3.5 hrs
2461 | Obtain Contract | Keisha Holligan - Account Success | 3.5 hrs | 3.5 hrs
2462 | Obtain Contract | Keisha Holligan - Account Success | 3.5 hrs | 3.5 hrs
2463 | Obtain Contract | Keisha Holligan - Account Success | 3.5 hrs | 3.5 hrs
2464 | Obtain Contract | Keisha Holligan - Account Success | 3.5 hrs | 3.5 hrs
2467 | Obtain Contract | Keisha Holligan - Account Success | 3.5 hrs | 3.5 hrs
2478 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2479 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2481 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2483 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2484 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2487 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2488 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2489 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2494 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2495 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2496 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2497 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2498 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2499 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2506 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2507 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2508 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2509 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
2510 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
2511 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
2512 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
2513 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2514 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2515 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
2516 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
2517 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
2518 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
2519 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2520 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2521 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2522 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2523 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2524 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2526 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2527 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2529 | Traing Account Designee & Super Users on User Mgt. | Keisha Holligan - Account Success | 4 hrs | 0.5 days
2530 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2531 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2532 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2539 | Identify desired ADT types needed by Participant | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2552 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2553 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2554 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2555 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2556 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2557 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2559 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2560 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2563 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2564 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2565 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2570 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2571 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2572 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2573 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2574 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2575 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2577 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2578 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2582 | Work w/ Account Designee & Super Users on Initial Users | Katie Bradley - COO | 8 hrs | 1 day
2583 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2584 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2585 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
2586 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
2587 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
2588 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
2589 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2590 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2591 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2592 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2593 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2594 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2596 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2597 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2601 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2602 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2603 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2604 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
2605 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
2606 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
2607 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
2608 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2609 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2610 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2611 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2612 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2613 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2615 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2616 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2619 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2620 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2621 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2626 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2627 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2628 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2629 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2630 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2631 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2633 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2634 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2637 | Traing Account Designee & Super Users on User Mgt. | Keisha Holligan - Account Success | 4 hrs | 0.5 days
2638 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2639 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2640 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2645 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2646 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2647 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2648 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2649 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2650 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2652 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2653 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2656 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2657 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2658 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2659 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2660 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2661 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2662 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2682 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2683 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2684 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2685 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2686 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2687 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2689 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2690 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2693 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2694 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2695 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2696 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2697 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2698 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2699 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2700 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2701 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2702 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2703 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2704 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2705 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2707 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2708 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2712 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2713 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2714 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2715 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2716 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2717 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2718 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2719 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2720 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2721 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2722 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2723 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2724 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2726 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2727 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2730 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2731 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2732 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2733 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2734 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2735 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2736 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2737 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2738 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2739 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2740 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2741 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2742 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2744 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2745 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2749 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2750 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2751 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2752 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2753 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2754 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2755 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2756 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Katie Bradley - COO | 1 hr | 1 hr
2757 | Create and review Project Charter with Participant stakeholders | Katie Bradley - COO | 8 hrs | 8 hrs
2758 | Enter Participant into the System | Katie Bradley - COO | 1 hr | 1 hr
2759 | Establish Account Designee and Super Users | Katie Bradley - COO | 1 hr | 1 hr
2760 | Work with Account Designee to identify possible patient overlap with available community interfaces | Katie Bradley - COO | 8 hrs | 1 day
2761 | Give Access to The Exchange | Katie Bradley - COO | 8 hrs | 1 day
2762 | Identify desired ADT types needed by Participant | Katie Bradley - COO | 8 hrs | 1 day
2763 | Determine Patient Panel Size | Katie Bradley - COO | 8 hrs | 1 day
2764 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Katie Bradley - COO | 8 hrs | 1 day
2765 | Configure and test notifications in system | Katie Bradley - COO | 8 hrs | 1 day
2766 | Traing Account Designee & Super Users on User Mgt. | Katie Bradley - COO | 4 hrs | 0.5 days
2767 | Work w/ Account Designee & Super Users on Initial Users | Katie Bradley - COO | 8 hrs | 1 day
2768 | Verify each user profile is active and password is set | Katie Bradley - COO | 8 hrs | 1 day
2769 | Verify ability each users’ permissions and available functionality | Katie Bradley - COO | 8 hrs | 1 day
2770 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
2771 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
2772 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
2773 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
2774 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Katie Bradley - COO | 1 hr | 1 hr
2775 | Create and review Project Charter with Participant stakeholders | Katie Bradley - COO | 8 hrs | 8 hrs
2776 | Enter Participant into the System | Katie Bradley - COO | 1 hr | 1 hr
2777 | Establish Account Designee and Super Users | Katie Bradley - COO | 1 hr | 1 hr
2778 | Work with Account Designee to identify possible patient overlap with available community interfaces | Katie Bradley - COO | 8 hrs | 1 day
2779 | Give Access to The Exchange | Katie Bradley - COO | 8 hrs | 1 day
2780 | Identify desired ADT types needed by Participant | Katie Bradley - COO | 8 hrs | 1 day
2781 | Determine Patient Panel Size | Katie Bradley - COO | 8 hrs | 1 day
2782 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Katie Bradley - COO | 8 hrs | 1 day
2785 | Traing Account Designee & Super Users on User Mgt. | Katie Bradley - COO | 4 hrs | 0.5 days
2786 | Work w/ Account Designee & Super Users on Initial Users | Katie Bradley - COO | 8 hrs | 1 day
2787 | Verify each user profile is active and password is set | Katie Bradley - COO | 8 hrs | 1 day
2788 | Verify ability each users’ permissions and available functionality | Katie Bradley - COO | 8 hrs | 1 day
2789 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
2790 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
2791 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
2792 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
2793 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Katie Bradley - COO | 1 hr | 1 hr
2794 | Create and review Project Charter with Participant stakeholders | Katie Bradley - COO | 8 hrs | 8 hrs
2795 | Enter Participant into the System | Katie Bradley - COO | 1 hr | 1 hr
2796 | Establish Account Designee and Super Users | Katie Bradley - COO | 1 hr | 1 hr
2797 | Work with Account Designee to identify possible patient overlap with available community interfaces | Katie Bradley - COO | 8 hrs | 1 day
2798 | Give Access to The Exchange | Katie Bradley - COO | 8 hrs | 1 day
2799 | Identify desired ADT types needed by Participant | Katie Bradley - COO | 8 hrs | 1 day
2800 | Determine Patient Panel Size | Katie Bradley - COO | 8 hrs | 1 day
2801 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Katie Bradley - COO | 8 hrs | 1 day
2803 | Traing Account Designee & Super Users on User Mgt. | Katie Bradley - COO | 4 hrs | 0.5 days
2804 | Work w/ Account Designee & Super Users on Initial Users | Katie Bradley - COO | 8 hrs | 1 day
2805 | Verify each user profile is active and password is set | Katie Bradley - COO | 8 hrs | 1 day
2806 | Verify ability each users’ permissions and available functionality | Katie Bradley - COO | 8 hrs | 1 day
2807 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
2808 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
2809 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
2810 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
2811 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Katie Bradley - COO | 1 hr | 1 hr
2812 | Create and review Project Charter with Participant stakeholders | Katie Bradley - COO | 8 hrs | 8 hrs
2813 | Enter Participant into the System | Katie Bradley - COO | 1 hr | 1 hr
2814 | Establish Account Designee and Super Users | Katie Bradley - COO | 1 hr | 1 hr
2815 | Work with Account Designee to identify possible patient overlap with available community interfaces | Katie Bradley - COO | 8 hrs | 1 day
2816 | Give Access to The Exchange | Katie Bradley - COO | 8 hrs | 1 day
2817 | Identify desired ADT types needed by Participant | Katie Bradley - COO | 8 hrs | 1 day
2818 | Determine Patient Panel Size | Katie Bradley - COO | 8 hrs | 1 day
2819 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Katie Bradley - COO | 8 hrs | 1 day
2822 | Traing Account Designee & Super Users on User Mgt. | Katie Bradley - COO | 4 hrs | 0.5 days
2823 | Work w/ Account Designee & Super Users on Initial Users | Katie Bradley - COO | 8 hrs | 1 day
2824 | Verify each user profile is active and password is set | Katie Bradley - COO | 8 hrs | 1 day
2825 | Verify ability each users’ permissions and available functionality | Katie Bradley - COO | 8 hrs | 1 day
2826 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
2827 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
2828 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
2829 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
2830 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Katie Bradley - COO | 1 hr | 1 hr
2831 | Create and review Project Charter with Participant stakeholders | Katie Bradley - COO | 8 hrs | 8 hrs
2832 | Enter Participant into the System | Katie Bradley - COO | 1 hr | 1 hr
2833 | Establish Account Designee and Super Users | Katie Bradley - COO | 1 hr | 1 hr
2834 | Work with Account Designee to identify possible patient overlap with available community interfaces | Katie Bradley - COO | 8 hrs | 1 day
2835 | Give Access to The Exchange | Katie Bradley - COO | 8 hrs | 1 day
2836 | Identify desired ADT types needed by Participant | Katie Bradley - COO | 8 hrs | 1 day
2837 | Determine Patient Panel Size | Katie Bradley - COO | 8 hrs | 1 day
2838 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Katie Bradley - COO | 8 hrs | 1 day
2840 | Traing Account Designee & Super Users on User Mgt. | Katie Bradley - COO | 4 hrs | 0.5 days
2841 | Work w/ Account Designee & Super Users on Initial Users | Katie Bradley - COO | 8 hrs | 1 day
2842 | Verify each user profile is active and password is set | Katie Bradley - COO | 8 hrs | 1 day
2843 | Verify ability each users’ permissions and available functionality | Katie Bradley - COO | 8 hrs | 1 day
2844 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
2845 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
2846 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
2847 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
2867 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2868 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2869 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2870 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2871 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2872 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2874 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2875 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2878 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2879 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2880 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2881 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
2882 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
2883 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
2884 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
2885 | Work with Account Designee to setup a group training session for organization | Katie Bradley - COO | 4 hrs | 0.5 days
2886 | Identify internal coach or “power-user” | Katie Bradley - COO | 4 hrs | 0.5 days
2887 | Complete group training of used functionality | Katie Bradley - COO | 16 hrs | 2 days
2888 | Follow-up with each user to verify for feedback on usability | Katie Bradley - COO | 16 hrs | 2 days
2889 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2890 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2891 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2892 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2893 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2894 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2896 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2897 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2900 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2901 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2902 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2903 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2904 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2905 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2906 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2935 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Keisha Holligan - Account Success | 1 hr | 1 hr
2936 | Create and review Project Charter with Participant stakeholders | Keisha Holligan - Account Success | 8 hrs | 8 hrs
2937 | Enter Participant into the System | Keisha Holligan - Account Success | 1 hr | 1 hr
2938 | Establish Account Designee and Super Users | Keisha Holligan - Account Success | 1 hr | 1 hr
2939 | Work with Account Designee to identify possible patient overlap with available community interfaces | Keisha Holligan - Account Success | 8 hrs | 1 day
2940 | Give Access to The Exchange | Keisha Holligan - Account Success | 8 hrs | 1 day
2941 | Identify desired ADT types needed by Participant | Keisha Holligan - Account Success | 8 hrs | 1 day
2942 | Determine Patient Panel Size | Keisha Holligan - Account Success | 8 hrs | 1 day
2945 | Traing Account Designee & Super Users on User Mgt. | Keisha Holligan - Account Success | 4 hrs | 0.5 days
2946 | Work w/ Account Designee & Super Users on Initial Users | Keisha Holligan - Account Success | 8 hrs | 1 day
2947 | Verify each user profile is active and password is set | Keisha Holligan - Account Success | 8 hrs | 1 day
2948 | Verify ability each users’ permissions and available functionality | Keisha Holligan - Account Success | 8 hrs | 1 day
2949 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2950 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2951 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2952 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2953 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Keisha Holligan - Account Success | 8 hrs | 1 day
2955 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Katie Bradley - COO | 1 hr | 1 hr
2956 | Create and review Project Charter with Participant stakeholders | Katie Bradley - COO | 8 hrs | 8 hrs
2957 | Enter Participant into the System | Katie Bradley - COO | 1 hr | 1 hr
2958 | Establish Account Designee and Super Users | Katie Bradley - COO | 1 hr | 1 hr
2959 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
2960 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
2961 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
2962 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
2966 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
2967 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
2968 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
2969 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
2974 | Configure and test notifications in system | Alan Uhl - Senior Developer | 0 hrs | 0 days
2975 | Start notifications and monitor for 7 days to validate | Alan Uhl - Senior Developer | 0 hrs | 0 days
2977 | Work with Account Designee to identify possible patient overlap with available community interfaces | Katie Bradley - COO | 8 hrs | 1 day
2978 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
2979 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
2982 | Determine Patient Panel Size | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2983 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
2987 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
2988 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
2989 | Configure and test notifications in system | Alan Uhl - Senior Developer | 0 hrs | 0 days
2990 | Start notifications and monitor for 7 days to validate | Alan Uhl - Senior Developer | 0 hrs | 0 days
2991 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
2992 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
2993 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
2994 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
2995 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
2996 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
2997 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
2998 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
2999 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3000 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3001 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3002 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3003 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3004 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3005 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3006 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3007 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3008 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3009 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3010 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3011 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3012 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3013 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3014 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3015 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3016 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3017 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3018 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3019 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3020 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3021 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3022 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3023 | Configure and test notifications in system | Tyler Harrison - Developer | 8 hrs | 1 day
3024 | Start notifications and monitor for 7 days to validate | Tyler Harrison - Developer | 8 hrs | 1 day
3025 | Obtain Contract | Katie Bradley - COO | 3.5 hrs | 3.5 hrs
3028 | Configure and test notifications in system | Alan Uhl - Senior Developer | 0 hrs | 0 days
3029 | Start notifications and monitor for 7 days to validate | Alan Uhl - Senior Developer | 0 hrs | 0 days
3034 | Give Access to The Exchange | Katie Bradley - COO | 8 hrs | 1 day
3035 | Identify desired ADT types needed by Participant | Keisha Holligan - Account Success | 8 hrs | 1 day
3036 | Determine Patient Panel Size | Tyler Harrison - Developer | 8 hrs | 1 day
3037 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Tyler Harrison - Developer | 8 hrs | 1 day
3043 | Traing Account Designee & Super Users on User Mgt. | Tyler Harrison - Developer | 4 hrs | 0.5 days
3044 | Work w/ Account Designee & Super Users on Initial Users | Tyler Harrison - Developer | 8 hrs | 1 day
3045 | Follow-up with each user to verify for feedback on usability | Tyler Harrison - Developer | 16 hrs | 2 days
3046 | Work w/ Account Designee & Super Users on Initial Users | Alan Uhl - Senior Developer | 0 hrs | 0 days
3047 | Verify each user profile is active and password is set | Tyler Harrison - Developer | 8 hrs | 1 day
3048 | Verify ability each users’ permissions and available functionality | Tyler Harrison - Developer | 8 hrs | 1 day
3050 | D07: Security, Privacy, and Confidentiality Plan | Ed Wilson -vCISO | 80 hrs | 10 days
3051 | D08 Staffing Management Plan | Terri Glover - Account Success Mgr. | 10 hrs | 10 hrs
3052 | D09: Incident Management Plan | Ed Wilson -vCISO | 24 hrs | 3 days
3055 | D12: Disaster Recovery and Business Continuity Plan | Ed Wilson -vCISO | 5 hrs | 5 hrs
3059 | D14: Pilot Implementation and Management Plan(s) | Terri Glover - Account Success Mgr. | 10 hrs | 10 hrs
3060 | D15: Data Transition Plan | Scott Hall - CIO | 20 hrs | 20 hrs
3063 | Dll: Data Management Plan | Alan Uhl - Senior Developer | 20 hrs | 20 hrs
3064 | D13: Public Health Systems Plan | Alan Uhl - Senior Developer | 5 hrs | 5 hrs
3065 | DIO: Training Management Plan | Keisha Holligan - Account Success | 20 hrs | 20 hrs
3078 | D05: HIE Participant Engagement and Technical Assistance Plan | Katie Bradley - COO | 30 hrs | 30 hrs
3080 | D04 Implementation Plan | Katie Bradley - COO | 20 hrs | 20 hrs
3082 | D06 Operations Management Plan | Katie Bradley - COO | 40 hrs | 40 hrs
3083 | Healthcare Providers User Agreement | Keisha Holligan - Account Success | 8 hrs | 1 day
3084 | Statement of HIPAA Compliance | Keisha Holligan - Account Success | 8 hrs | 1 day
3085 | Privacy Policy | Keisha Holligan - Account Success | 8 hrs | 1 day
3086 | Terms of Use | Keisha Holligan - Account Success | 8 hrs | 1 day
3087 | ENS FEE Schedule | Keisha Holligan - Account Success | 4 hrs | 0.5 days
3088 | HIE Participant Agreement | Keisha Holligan - Account Success | 8 hrs | 1 day
3089 | Identify desired ADT types needed by Participant | Katie Bradley - COO | 8 hrs | 1 day
3090 | Traing Account Designee & Super Users on User Mgt. | Katie Bradley - COO | 4 hrs | 0.5 days
3107 | D16: Detailed System Design Document | Scott Hall - CIO | 18 hrs | 20 hrs
3108 | D18: Outcomes Based Certification (OBC) Support Plan and Reporting | Scott Hall - CIO | 16 hrs | 20 hrs
3109 | D19: Turnover and Closeout Management Plan | Scott Hall - CIO | 16 hrs | 20 hrs
3110 | D17 Independent, Third-Party Security, and Privacy Controls Assessment Report | Ed Wilson -vCISO | 5 hrs | 5 hrs
3121 | PRMP Introduction | PR -HIE Portfolio Manager | 8 hrs | 1 day
3122 | Establish Technical Point of Contact with Vendor | Katie Bradley - COO | 8 hrs | 1 day
3123 | Establish Interface Connectivy | Alan Uhl - Senior Developer | 40 hrs | 5 days
3124 | Replicate ADT feed from PRHIE to PRMP Emergency Services | Alan Uhl - Senior Developer | 40 hrs | 5 days
3126 | File agreement, completed forms and any credentialing paperwork under Participant as per Centralis policy | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
3127 | Create and review Project Charter with Participant stakeholders | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
3128 | Enter Participant into the System | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
3129 | Establish Account Designee and Super Users | Terri Glover - Account Success Mgr. | 0 hrs | 0 hrs
3131 | Work with Account Designee to identify possible patient overlap with available community interfaces | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3132 | Give Access to The Exchange | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3133 | Identify desired ADT types needed by Participant | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3134 | Determine Patient Panel Size | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3135 | Determine panel upload mechanism (Centralis Health Gateway or SFTP) | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3137 | Traing Account Designee & Super Users on User Mgt. | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3138 | Work w/ Account Designee & Super Users on Initial Users | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3139 | Verify each user profile is active and password is set | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3140 | Verify ability each users’ permissions and available functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3142 | Work with Account Designee to setup a group training session for organization | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3143 | Identify internal coach or “power-user” | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3144 | Complete group training of used functionality | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3145 | Follow-up with each user to verify for feedback on usability | Terri Glover - Account Success Mgr. | 0 hrs | 0 days
3147 | PRMP Introduction to PRDOH | PR -HIE Portfolio Manager | 4 hrs | 0.5 days
3149 | Determine and Agree on Spec | Alan Uhl - Senior Developer | 20 hrs | 3 days
3150 | Establish and Test Connectivity btw Centralis Health and PRDOH | Alan Uhl - Senior Developer | 10 hrs | 1.5 days
3152 | Hospital/Clinic 1 | Tyler Harrison - Developer | 5 hrs | 5 hrs
3241 | Hospital/Clinic 2 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3242 | Hospital/Clinic 3 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3243 | Hospital/Clinic 4 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3244 | Hospital/Clinic 5 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3245 | Hospital/Clinic 6 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3246 | Hospital/Clinic 7 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3247 | Hospital/Clinic 8 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3248 | Hospital/Clinic 9 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3249 | Hospital/Clinic 10 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3250 | Hospital/Clinic 11 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3251 | Hospital/Clinic 12 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3252 | Hospital/Clinic 13 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3253 | Hospital/Clinic 14 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3254 | Hospital/Clinic 15 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3255 | Hospital/Clinic 16 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3256 | Hospital/Clinic 17 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3257 | Hospital/Clinic 18 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3258 | Hospital/Clinic 19 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3259 | Hospital/Clinic 20 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3260 | Hospital/Clinic 21 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3261 | Hospital/Clinic 22 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3262 | Hospital/Clinic 23 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3263 | Hospital/Clinic 24 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3264 | Hospital/Clinic 25 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3265 | Hospital/Clinic 26 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3266 | Hospital/Clinic 27 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3267 | Hospital/Clinic 28 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3268 | Hospital/Clinic 29 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3269 | Hospital/Clinic 30 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3270 | Hospital/Clinic 31 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3271 | Hospital/Clinic 32 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3272 | Hospital/Clinic 33 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3273 | Hospital/Clinic 34 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3274 | Hospital/Clinic 35 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3275 | Hospital/Clinic 36 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3276 | Hospital/Clinic 37 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3277 | Hospital/Clinic 38 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3278 | Hospital/Clinic 39 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3279 | Hospital/Clinic 40 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3280 | Hospital/Clinic 41 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3281 | Hospital/Clinic 42 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3282 | Hospital/Clinic 43 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3283 | Hospital/Clinic 44 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3284 | Hospital/Clinic 45 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3285 | Hospital/Clinic 46 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3286 | Hospital/Clinic 47 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3287 | Hospital/Clinic 48 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3288 | Hospital/Clinic 49 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3289 | Hospital/Clinic 50 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3290 | Hospital/Clinic 51 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3291 | Hospital/Clinic 52 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3292 | Hospital/Clinic 53 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3293 | Hospital/Clinic 54 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3294 | Hospital/Clinic 55 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3295 | Hospital/Clinic 56 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3296 | Hospital/Clinic 57 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3297 | Hospital/Clinic 58 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3298 | Hospital/Clinic 59 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3299 | Hospital/Clinic 60 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3300 | Hospital/Clinic 61 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3301 | Hospital/Clinic 62 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3302 | Hospital/Clinic 63 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3303 | Centros 330_FQHC 1 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3304 | Centros 330_FQHC 2 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3305 | Centros 330_FQHC 3 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3306 | Centros 330_FQHC 4 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3307 | Centros 330_FQHC 5 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3308 | Centros 330_FQHC 6 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3309 | Centros 330_FQHC 7 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3310 | Centros 330_FQHC 8 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3311 | Centros 330_FQHC 9 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3312 | Centros 330_FQHC 10 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3313 | Centros 330_FQHC 11 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3314 | Centros 330_FQHC 12 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3315 | Centros 330_FQHC 13 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3316 | Centros 330_FQHC 14 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3317 | Centros 330_FQHC 15 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3318 | Centros 330_FQHC 16 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3319 | Centros 330_FQHC 17 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3320 | LIMS 1 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3321 | LIMS 2 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3322 | LIMS 3 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3323 | LIMS 4 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3324 | LIMS 5 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3325 | LIMS 6 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3326 | LIMS 7 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3327 | LIMS 8 | Tyler Harrison - Developer | 3 hrs | 3 hrs
3328 | Radiology Facility | Tyler Harrison - Developer | 3 hrs | 3 hrs
3332 | Obtain Contract | Keisha Holligan - Account Success | 3.5 hrs | 3.5 hrs
3333 | Establish PRDOH Technical POC | Alan Uhl - Senior Developer | 4 hrs | 0.5 days
3335 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3336 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3337 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3338 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3339 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3340 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3341 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3342 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3343 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3345 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3346 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3347 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3348 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3349 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3350 | PRMP Introduction | PR -HIE Portfolio Manager | 2 hrs | 0.25 days
3353 | PRMP Introduction | PR -HIE Portfolio Manager | 0 hrs | 0 days
3355 | Establish Technical Contact with Health Gorilla | Scott Hall - CIO | 0 hrs | 1 day
3356 | Establish Technical Contact with Health Gorilla | Zen - Resource 1 | 8 hrs | 1 day
3357 | Establish Technical Contact with Health Gorilla | Health Gorilla | 8 hrs | 1 day
3358 | Add Approved Invoice Template to Quickbooks | Louis Martin - Controller | 4 hrs | 4 hrs